## ARRA6-10-11
DistEA | Contract # | Road | Work Description | Estimate | LOW BID | Low Bid | A_B | Ad Date | Bid Open | Award Date | Federal Aid No.: | Target Award Date | Target Approval Date | Notes | RM | UDBE Goal | Achievement
11288801 | 11-288804 | 11-SD-905-R9.5/R15.0 | Construct new 6 lane PCC freeway. | 62200000 | 57095736 | 57095736 |  | 2008-11-17 | 2009-04-30 | 2009-05-08 | HPLU-6211(078)N | 2009-05-08 | 2009-05-29 | Awarded 5/8/09 | #REF! | 6 | 0.38
044C15U1 | 04-4C15U4 | 04-Sol-80-15.4/20.1 | Crack seat and overlay on the mainline with shoulder backing. | 22100000 | 13359459.8 | 13359459.8 |  | 2009-01-12 | 2009-04-14 | 2009-04-21 | SARRA-080-2(356)E | 2009-05-01 | 2009-05-15 | Awarded 4/21/09 | #REF! | 6 | 1.22
03366901 | 03-366904 | 03-But-99-13.8/21.1 | Widen shoulder and place HMA over CL 2 AB. | 12500000 | 7279919 | 7279919 |  | 2009-04-06 | 2009-05-05 | 2009-06-26 | SARRA-P099(519) | 2009-05-18 | 2009-06-01 | Awarded 6/26/09 | #REF! | 5 | 0.42
01380501 | 01-380504 | 01-Men-222-1.6 | Replace Bridge (Scour) | 10500000 | 5390677 | 5390677 |  | 2009-04-06 | 2009-05-06 | 2009-05-18 | SARRA-P222(001)E | 2009-06-05 | 2009-06-19 | Awarded 5/18/09 | #REF! | 5 | 0.4
031A8411 | 03-1A8414 | 03-ED-89-0.0/8.6 | Install drainage facilities and widen with HMA over CL2 AB | 22000000 | 10856506 | 10856506 |  | 2009-04-13 | 2009-05-15 | 2009-05-29 | SARRA-P089(094)E | 2009-06-12 | 2009-06-26 | Awarded 5/29/09 | #REF! | 5 | 5
034C0301 | 03-4C0304 | 03-Pla,Sac,Yol-5, 65, 80, 99-Var | Install traffic monitoring stations. | 1800000 | 868559 | 868559 |  | 2009-04-13 | 2009-05-12 | 2009-05-15 | SARRA-000C(304)E | 2009-05-18 | 2009-06-01 | Awarded 5/15/09 | #REF! | 4 | 14.1
050L8001 | 05-0L8004 | 05-Mon-1,68-Var | Install metal beam guard railing and upgraded end treatment. | 1900000 | 1288673.5 | 1288673.5 |  | 2009-04-13 | 2009-05-22 | 2009-06-09 | SARRA-X053(022)E | 2009-06-12 | 2009-06-26 | Awarded 6/9/09 | #REF! | 5 | 1.9
030C2811 | 03-0C2814 | 03-Col,Pla,Sac-5, 51, 80, 99-Var | Install CMS and CCTV. | 5170000 | 2970631.29 | 3282547.15 |  | 2009-04-13 | 2009-05-13 | 2009-06-17 | SARRA-000C(303)E | 2009-06-12 | 2009-06-26 | Awarded 6/17/09 | #REF! | 5 | 5.3
034C0901 | 03-4C0904 | 03-ED-49-10.6/13.3 | Realign and widen roadway with HMA, constr gabion wall. | 7100000 | 4304567.8 | 4304567.8 |  | 2009-04-13 | 2009-05-13 | 2009-06-12 | SARRA-P049(143)E | 2009-06-12 | 2009-06-26 | Awarded 6/12/09 | #REF! | 5 | 1.5
033C8801 | 03-3C8804 | 03-Sut-70, 99-0.0/0.7, 0.0/8.7 | Remove and Replace OGAC | 13800000 | 8277039.2 | 8277039.2 |  | 2009-04-13 | 2009-05-15 | 2009-06-05 | SARRA-P099(520)E | 2009-06-12 | 2009-06-26 | Awarded 6/5/09 | #REF! | 4 | 4.3
06416101 | 06-416104 | 06-Mad-145-R1.3/10.9 | Asphalt concrete overlay and replace bridge. | 10900000 | 9642595.9 | 7836595.9 | A+B | 2009-04-20 | 2009-05-19 | 2009-06-08 | SARRA-P145(029)E | 2009-06-18 | 2009-07-02 | Awarded 6/8/09 | #REF! | 4 | 7.3
120J7001 | 12-0J7004 | 12-Ora-1-4.6/9.6,12.2/14.1 | Slurry seal pavement and digouts | 1820000 | 1674529 | 1674529 |  | 2009-04-20 | 2009-05-14 | 2009-06-04 | SARRA-P001(541)E | 2009-06-12 | 2009-06-26 | Awarded 6/4/09 | #REF! | 8 | 8.6
022C50U1 | 02-2C50U4 | 02-Teh-5-R22.2/R27.5 | Bridge deck maintenance and replace PCC pavement. | 34000000 | 29211926.32 | 29211926.32 |  | 2009-04-20 | 2009-06-02 | 2009-06-26 | SARRA-005-8(336)E | 2009-07-02 | 2009-07-16 | Awarded 6/25/09 | #REF! | 4 | 4.1
020E6101 | 02-0E6104 | 02-Teh,Plu-VAR-VAR | PLACE HOT MIX ASPHALT | 2520000 | 2098799 | 2098799 |  | 2009-04-20 | 2009-05-20 | 2009-06-05 | SARRA-000C(305)E | 2009-06-19 | 2009-07-03 | Awarded 6/5/09 | #REF! | 4 | 4.2
020E6501 | 02-0E6504 | 02-Las-139-40.0/53.0 | PLACE ASPHALT RUBBER SEAL COAT | 1120000 | 1216648 | 1216648 |  | 2009-04-20 | 2009-05-19 | 2009-06-09 | SARRA-P139(019)E | 2009-06-18 | 2009-07-02 | Awarded 6/9/09 | #REF! | 4 | 2.4
021E3201 | 02-1E3204 | 02-Mod-395-0.0/20.8 | PLACE SEAL COAT | 1380000 | 1906179.5 | 1906179.5 |  | 2009-04-20 | 2009-05-20 | 2009-06-08 | SARRA-P395(224)E | 2009-06-19 | 2009-07-03 | Awarded 6/8/09 | #REF! | 6 | 0.2
021E9801 | 02-1E9804 | 02-Plu-36-R12.3/R14.0 | Cold In-Place Recycle | 1540000 | 1367377.77 | 1367377.77 |  | 2009-04-20 | 2009-05-13 | 2009-06-01 | SARRA-P036(086)E | 2009-06-12 | 2009-06-26 | Awarded 6/1/09 | #REF! | 5 | 8.6
031E0301 | 03-1E0304 | 03-Col-20-R21.5/R22.4 | Reconstruct embankment slope, shoulder; and MBGR. | 7400000 | 5317623 | 5317623 |  | 2009-04-20 | 2009-05-12 | 2009-07-31 | SARRA-P020(150)E | 2009-05-18 | 2009-06-01 | Awarded 7/31/09 | #REF! | 5 | 0.2
08434301 | 08-434304 | 08-Riv-95-24.9/32.7 | Drainage Improvements | 2940000 | 1518158 | 1518158 |  | 2009-04-27 | 2009-05-28 | 2009-06-15 | SARRA-P095(020)E | 2009-06-26 | 2009-07-10 | Awarded 6/15/09 | #REF! | 5 | 3.4
04177901 | 04-177904 | 04-Ala-880-28.2/28.5 | Overlay bridge deck, replace railing, and construct approach slabs. | 6500000 | 7397807 | 6517807 | A+B | 2009-04-27 | 2009-05-26 | 2009-06-15 | SARRA-880-1(058)E | 2009-06-25 | 2009-07-09 | Awarded 6/15/09 | #REF! | 4 | 0.3
04272021 | 04-272024 | 04-SCl-280-5.1/7.8 | Existing highway to be surfaced and bridge decks to be treated. | 10803000 | 8270513 | 7575513 | A+B | 2009-04-27 | 2009-06-02 | 2009-06-19 | SARRA-280-1(119)E | 2009-07-02 | 2009-07-16 | Awarded 6/19/09 | #REF! | 7 | 0.8
06430101 | 06-430104 | 06-Ker-204-4.6/5.1 | Replace steel bridge with reinforced concrete box girder bridge. | 12830000 | 11678093 | 11678093 |  | 2009-04-27 | 2009-05-26 | 2009-06-09 | SARRA-S204(004)E | 2009-06-25 | 2009-07-09 | Awarded 6/9/09 | #REF! | 4 | 0.17
060C8001 | 06-0C8004 | 06-Ker-5-6.4/10.3 | Construct concrete and thrie beam median barrier, and widen shoulder. | 1910000 | 1100000 | 1100000 |  | 2009-04-27 | 2009-05-26 | 2009-06-23 | SARRA-005-4(182)211E | 2009-06-25 | 2009-07-09 | Awarded 6/23/09 | #REF! | 4 | 4
120J0901 | 12-0J0904 | 12-Ora-90-5.1/8.1 | Rubberized asphalt concrete overlay | 1730000 | 1165358 | 1165358 |  | 2009-04-27 | 2009-05-21 | 2009-06-11 | SARRA-P090(011)E | 2009-06-19 | 2009-07-03 | Awarded 6/11/09 | #REF! | 9 | 9.4
100S4501 | 10-0S4504 | 10-Tuo-49-18.6/R27.5 | Cold plane AC pavement and apply rubberized HMA (Gap Graded). | 1170000 | 1027942 | 1027942 |  | 2009-04-27 | 2009-05-26 | 2009-06-11 | SARRA-P049(145)E | 2009-06-25 | 2009-07-09 | Awarded 6/11/09 | #REF! | 4 | 4
09339201 | 09-339204 | 09-Mno-395-R12.6/36.1 | Construct Asphalt Rubber Chip Seal. | 2490000 | 2753542.1 | 2753542.1 |  | 2009-04-27 | 2009-05-22 | 2009-06-18 | SARRA-P395(226)E | 2009-06-19 | 2009-07-03 | Awarded 6/18/09 | #REF! | 4 | 0
060K9101 | 06-0K9104 | 06-Fre-33,198-Var | Apply rubberized HMA (gap graded) and cold plane AC pavement. | 1300000 | 1204788 | 1204788 |  | 2009-04-27 | 2009-05-20 | 2009-06-08 | SARRA-X019(021)E | 2009-06-19 | 2009-07-03 | Awarded 6/8/09 | #REF! | 4 | 16
060K7201 | 06-0K7204 | 06-Ker-14-16.3/26.6, 46.2/60.6 | Place hot mix asphalt (bonded wearing course-gap graded) on pavement. | 3480000 | 4465525 | 4465525 |  | 2009-04-27 | 2009-05-27 | 2009-06-16 | SARRA-P014(065)E | 2009-06-26 | 2009-07-10 | Awarded 6/16/09 | #REF! | 4 | 6.2
060K7401 | 06-0K7404 | 06-Ker,Kin-33, 41-Var | Place hot mix asphalt (bonded wearing course -gap graded) on pavement. | 2800000 | 3366872 | 3366872 |  | 2009-04-27 | 2009-05-26 | 2009-06-11 | SARRA-000C(306)E | 2009-06-25 | 2009-07-09 | Awarded 6/11/09 | #REF! | 4 | 9.7
100S4601 | 10-0S4604 | 10-Mer,Sta-33- R0.0/L5.6, 17.8/27.1 | Apply rubberized HMA (gap graded) and cold plane AC pavement. | 1930000 | 1847696 | 1847696 |  | 2009-04-27 | 2009-05-22 | 2009-06-16 | SARRA-P033(068)E | 2009-06-19 | 2009-07-03 | Awarded 6/16/09 | #REF! | 4 | 4
120G0301 | 12-0G0304 | 12-Ora-57-11.1/22.1 | Replace exist MBGR with conc barrier and extension of MBGR on 2 ramps | 3250000 | 1751316 | 1889971 |  | 2009-04-27 | 2009-06-04 | 2009-07-21 | SARRA-P057(053)E | 2009-07-03 | 2009-07-16 | Awarded 7/21/09 | #REF! | 6 | 6
100S4401 | 10-0S4404 | 10-Ama-88-R60.8/66.7 | Apply polymer modified seal coat and flush coat. | 300000 | 292510 | 292510 |  | 2009-04-30 | 2009-05-22 | 2009-06-11 | SARRA-P088(053)E | 2009-06-05 | 2009-06-12 | Informal, Awarded 6/11/09 | #REF! | 6 | 6.2
100S4701 | 10-0S4704 | 10-Ama-88-32.3/38.0 | Cold plane AC pavement and apply rubberized HMA (Gap Graded). | 870000 | 791115 | 791115 |  | 2009-04-30 | 2009-05-22 | 2009-06-11 | SARRA-P088(052)E | 2009-06-05 | 2009-06-12 | Informal, Awarded 6/11/09 | #REF! | 4 | 5.4
080L7501 | 08-0L7504 | 08-SBd-62-133.5/137.5 | Replace AC Surfacing at Various Locations | 750000 | 562222 | 562222 |  | 2009-04-30 | 2009-05-07 | 2009-06-03 | SARRA-P062(026)E | 2009-05-21 | 2009-05-28 | Informal, Awarded 6/3/09 | #REF! | 9 | 0
080L2801 | 08-0L2804 | 08-SBd-18-60.8/64.0,67.0/73.8 | DIGOUTS AND REPLACE ASPHALT CONCRETE SURFACING | 520000 | 499455 | 499455 |  | 2009-04-30 | 2009-05-07 | 2009-05-27 | SARRA-P018(038)E | 2009-05-21 | 2009-05-28 | Informal, Awarded 5/27/09 | #REF! | 4 | 4.3
080L7301 | 08-0L7304 | 08-Riv-15-33.2/38.3 | Replace asphalt concrete surfacing | 690000 | 454440 | 454440 |  | 2009-04-30 | 2009-05-07 | 2009-06-02 | SARRA-015-5(152)E | 2009-05-21 | 2009-05-28 | Informal, Awarded 6/2/09 | #REF! | 4 | 0
033M2001 | 03-3M2004 | 03-Sie-49-47.5/64.0 | Chip Seal | 670000 | 667661.8 | 667661.8 |  | 2009-04-30 | 2009-05-22 | 2009-06-15 | SARRA-P049(144)E | 2009-06-05 | 2009-06-12 | Informal, Awarded 6/15/09 | #REF! | 8 | 1
072Y6301 | 07-2Y6304 | 07-Ven-34-13.6/17.6 | Cold plane and place rubberized HMA (Type G). | 1260000 | 1072500 | 1072500 |  | 2009-05-04 | 2009-05-29 | 2009-06-16 | SARRA-P034(004)E | 2009-06-26 | 2009-07-10 | Awarded 6/16/09 | #REF! | 4 | 5.7
080L6801 | 08-0L6804 | 08-Riv-243-1.1/5.3, 7.5/13.3 | COLD PLANE AND HMA OVERLAY | 1780000 | 1455900 | 1455900 |  | 2009-05-04 | 2009-05-28 | 2009-06-16 | SARRA-P243(002)E | 2009-06-26 | 2009-07-10 | Awarded 6/16/09 | #REF! | 9 | 4
080K8001 | 08-0K8004 | 08-SBd-395-51.9/58.1 61.0/65.6 | Overlay rubberized hot mix asphalt and dig outs | 1820000 | 1168042 | 1168042 |  | 2009-05-04 | 2009-05-29 | 2009-06-16 | SARRA-P395(225)E | 2009-06-26 | 2009-07-10 | Awarded 6/16/09 | #REF! | 4 | 4.1
080K6201 | 08-0K6204 | 08-SBd-18-31.5/39.0 | Hot Mix Asphalt Overlay and Digouts | 1260000 | 1025000 | 1025000 |  | 2009-05-04 | 2009-05-28 | 2009-06-16 | SARRA-P018(037)E | 2009-06-26 | 2009-07-10 | Awarded 6/16/09 | #REF! | 6 | 0
11081641 | 11-081644 | 11-SD-54,805-1.6/2.5,7.6/9.2 | Construct southbound lanes and rehabilitate ramps. | 9700000 | 6354888 | 6354888 |  | 2009-05-04 | 2009-06-25 | 2009-07-23 | SARRA-805-1(608)E | 2009-07-24 | 2009-08-07 | Awarded 7/23/09 | #REF! | 7 | 5
120K2001 | 12-0K2004 | 12-Ora-73-10.0/22.5 | Hot mix asphalt overlay | 6600000 | 6996021.33 | 6996021.33 |  | 2009-05-11 | 2009-06-04 | 2009-06-25 | SARRA-P073(086)E | 2009-07-02 | 2009-07-16 | Awarded 6/25/09 | #REF! | 5 | 6.1
12085101 | 12-085104 | 12-Ora-39,72-19.2/23.2,11.4/11.9 | PAVEMENT REHABILITATION | 6700000 | 3988451.6 | 3988451.6 |  | 2009-05-11 | 2009-06-18 | 2009-07-09 | SARRA-P039(021)E | 2009-07-17 | 2009-07-31 | Awarded 7/9/09 | #REF! | 6 | 6
041E3801 | 04-1E3804 | 04-Nap-29-38.1/48.6 | Cold plane asphalt concrete pavement and place HMA (A). | 530000 | 509589 | 509589 |  | 2009-05-18 | 2009-06-17 | 2009-06-29 | SARRA-P029(105)E | 2009-07-15 | 2009-07-29 | Awarded 6/29/09 | #REF! | 5 | 9.1
050F7101 | 05-0F7104 | 05-SLO-46-49.5 | Construct new comfort station and landscape rest area. | 5940000 | 2942365.29 | 2942365.29 |  | 2009-05-18 | 2009-06-23 | 2009-07-29 | SARRA-P046(042)E | 2009-07-21 | 2009-08-04 | Awarded 7/29/09 | #REF! | 6 | 0.6
04294911 | 04-294914 | 04-CC,Ala-24-8.2/10.0,0.0/2.7 | Construct a 4th Caldecott tunnel and building. | 270000000 | 257017175 | 214806175 | A+B | 2009-05-18 | 2009-09-29 | 2009-11-10 | SARRA-P024(030)N | 2009-09-08 | 2009-09-22 | Awarded 11/10/09 | #REF! | 3 | 2.9
041E3901 | 04-1E3904 | 04-SCl-35-7.7/14.1 | Overlay roadway with rubberized hot mix asphalt (gap graded). | 1230000 | 1045045 | 1045045 |  | 2009-05-26 | 2009-06-23 | 2009-07-16 | SARRA-S035(007)E | 2009-07-21 | 2009-08-04 | Awarded 7/16/09 | #REF! | 4 | 7.8
041E2201 | 04-1E2204 | 04-Son-1-30.5/35.5,50.6/58.5 | Replace asphalt concrete surfacing | 420000 | 369030 | 369030 |  | 2009-05-26 | 2009-06-23 | 2009-07-20 | SARRA-P001(540)E | 2009-07-21 | 2009-08-04 | Awarded 7/20/09 | #REF! | 4 | 4
041E3201 | 04-1E3204 | 04-SM-101-23.0/26.1 | Cold plane and place rubberized hot mix asphalt (gap graded). | 2810000 | 2295770 | 2295770 |  | 2009-05-26 | 2009-06-24 | 2009-07-20 | SARRA-Q101(152)E | 2009-07-22 | 2009-08-05 | Awarded 7/20/09 | #REF! | 4 | 4.3
050E4701 | 05-0E4704 | 05-Mon-101-45.8/82.0 | Contruct median lane and left turn channelization. | 4280000 | 3812074 | 3812074 |  | 2009-06-01 | 2009-07-01 | 2009-07-15 | SARRA-Q101(151)E | 2009-07-29 | 2009-08-12 | Awarded 7/15/09 | #REF! | 4 | 4.1
06432101 | 06-432104 | 06-Fre-41-R25.3,R26.3/R26.5 | Widen ramps and install ramp metering system. | 3430000 | 2054022 | 2054022 |  | 2009-06-01 | 2009-07-14 | 2009-07-31 | SARRA-P041(110)E | 2009-08-11 | 2009-08-25 | Awarded 7/31/09 | #REF! | 4 | 4.8
07269001 | 07-269004 | 07-LA-710-17.9/20.8 | Place HMA over CL3 AB, construct concrete barrier and widen roadbed. | 50000000 | 38838126.9 | 38838126.9 |  | 2009-06-01 | 2009-07-23 | 2009-08-06 | SARRA-P710(014)E | 2009-08-20 | 2009-09-03 | Awarded 8/6/09 | #REF! | 4 | 0
033M6201 | 03-3M6204 | 03-Yub-20-10.2/13.4 | Hot Mix Asphalt (Bonded Wearing Course- Open Graded) | 1070000 | 875466 | 950434.6 |  | 2009-06-01 | 2009-06-24 | 2009-07-09 | SARRA-P020(151)E | 2009-07-22 | 2009-08-05 | Awarded 7/9/09 | #REF! | 4 | 2.7
120G0401 | 12-0G0404 | 12-Ora,Riv-91-15.9/18.9, 0.0/2.9 | Widen freeway and bridges. | 54000000 | 40855853 | 35575853 | A+B | 2009-06-08 | 2009-07-30 | 2009-08-28 | ARRAL-P091(127)E | 2009-08-27 | 2009-09-10 | Awarded 8/28/09 | #REF! | 6 | 0.5
073Y7901 | 07-3Y7904 | 07-LA-210-R19.9/R25.3 | Replace PCC slabs. | 410000 | 199722 | 272000 |  | 2009-06-08 | 2009-07-09 | 2009-09-03 | SARRA-210-1(795)E | 2009-08-06 | 2009-08-20 | Awarded 9/3/09 | #REF! | 3 | 3
073Y8101 | 07-3Y8104 | 07-LA-134-2.6/9.0 | Cold plane ramps and place HMA. | 1450000 | 1067000 | 1067000 |  | 2009-06-08 | 2009-07-09 | 2009-08-03 | SARRA-P134(035)E | 2009-08-06 | 2009-08-20 | Awarded 8/3/09 | #REF! | 4 | 22.3
06342511 | 06-342514 | 06-Fre-180-R106.3/116.4 | Construct 4-lanes concrete pavement expressway. | 35000000 | 27283086 | 27283086 |  | 2009-06-15 | 2009-08-12 | 2009-09-10 | ARRAL-P180(053)E | 2009-09-09 | 2009-09-23 | Awarded 9/10/09 | #REF! | 7 | 7.2
08422201 | 08-422204 | 08-Riv-78-3.3 | Replace concrete bridge. | 1670000 | 1020378.87 | 1020378.87 |  | 2009-06-22 | 2009-07-16 | 2009-08-03 | SARRA-P078(108)E | 2009-08-13 | 2009-08-27 | Awarded 8/3/09 | #REF! | 7 | 7.6
100G7701 | 10-0G7704 | 10-Sta-33-0.5/1.5,12.6/14.5 | Cold plane AC pavement and apply rubberized HMA (Gap Graded). | 2030000 | 1303729.5 | 1303729.5 |  | 2009-07-06 | 2009-08-04 | 2009-08-17 | SARRA-S033(069)E | 2009-09-01 | 2009-09-15 | Awarded 8/17/09 | #REF! | 7 | 8.3
100K0201 | 10-0K0204 | 10-Mer-99-25.4/27.8 | Replace bridge and construct roadway. | 33000000 | 20492520.2 | 20492520.2 |  | 2009-07-13 | 2009-09-23 | 2009-10-08 | SARRA-P099(521)E | 2009-09-16 | 2009-09-30 | Awarded 10/8/09 | #REF! | 5 | 0.2
07226521 | 07-226524 | 07-LA-Var-Var | Install vertical clearance and advance warning signs. | 2240000 | 561798 | 561798 |  | 2009-07-13 | 2009-08-13 | 2009-08-28 | SARRA-X037(146)E | 2009-09-10 | 2009-09-24 | Awarded 8/28/09 | #REF! | 13 | 13.3
07226541 | 07-226544 | 07-LA-Var-Var | Install vertical clearance and advance warning signs. | 1750000 | 449840 | 449840 |  | 2009-07-13 | 2009-08-06 | 2009-08-20 | SARRA-X037(148)E | 2009-09-03 | 2009-09-17 | Awarded 8/20/09 | #REF! | 11 | 36.9
100H04U1 | 10-0H04U4 | 10-SJ-4-8.7/R11.1 | Realignment to correct curve and improve intersection. | 12000000 | 6432432 | 6432432 |  | 2009-07-20 | 2009-08-26 | 2009-09-03 | SARRA-P004(133)E | 2009-09-23 | 2009-10-07 | Awarded 9/3/09 | #REF! | 6 | 6
07226531 | 07-226534 | 07-LA-Var-Var | Install vertical clearance and advance warning signs. | 1810000 | 461830 | 461830 |  | 2009-07-20 | 2009-09-03 | 2009-10-08 | SARRA-X037(147)E | 2009-10-01 | 2009-10-15 | Awarded 10/8/09 | #REF! | 13 | 0.08
07226511 | 07-226514 | 07-LA,Ven-Var-Var | Install vertical clearance and warning signs. | 910000 | 472085 | 472085 |  | 2009-07-20 | 2009-08-27 | 2009-10-01 | SARRA-X037(145)E | 2009-09-24 | 2009-10-08 | Awarded 10/1/09 | #REF! | 12 | 0
08394701 | 08-394704 | 08-SBd-18-66.6/67.2 | Replace bridge and realign curve. | 6000000 | 2572029 | 2572029 |  | 2009-07-27 | 2009-09-03 | 2009-09-25 | SARRA-P018(039)E | 2009-10-01 | 2009-10-15 | Awarded 9-25-09 | #REF! | 6 | 1
04150471 | 04-150474 | 04-SM-280-R0.0/M27.4 | Install traffic management system elements. | 1600000 | 918172.4 | 918172.4 |  | 2009-07-27 | 2009-08-26 | 2009-09-08 | SARRA-280-1(122)E | 2009-09-23 | 2009-10-07 | Awarded 9/8/09 | #REF! | 4 | 4.5
08456001 | 08-456004 | 08-Riv-10-66.5/71.7 | CONSTRUCT INTERCHANGE | 37000000 | 22428651 | 22428651 |  | 2009-08-17 | 2009-10-08 | 2009-11-16 | ARRAL-010-3(101)127E | 2009-11-05 | 2009-11-19 | Awarded 11/16/09 | #REF! | 8 | 1.2
07252711 | 07-252714 | 07-LA-5-39.4/R43.9 | Grind and replace concrete pavement. | 10000000 | 8355271.1 | 8355271.1 |  | 2009-08-17 | 2009-09-17 | 2009-09-28 | SARRA-005-3(014)E | 2009-10-15 | 2009-10-29 | Awarded 9/28/09 | #REF! | 7 | 7.5
11080101 | 11-080104 | 11-SD-76-R11.7/21.1 | To construct a 4-lane highway | 80000000 | 61023992 | 61023992 |  | 2009-09-08 | 2009-10-29 | 2009-12-23 | ARRAL-P076(024)E | 2009-11-26 | 2009-12-10 | Awarded 12/23/09 | #REF! | 10 | 0.95
07266701 | 07-266704 | 07-Ven-118-R43.3/R52.3 | Widen roadway with concrete over LCB and install concrete barrier. | 21800000 | 13844502.9 | 13844502.9 |  | 2009-09-14 | 2009-11-05 | 2009-11-24 | ARRAL-P118(058)E | 2009-12-03 | 2009-12-17 | Awarded 11/24/09 | #REF! | 6 | 9.1
09339601 | 09-339604 | 09-Iny,SBd-127,178-Var | Cold plane asphalt pavement and place HMA (open graded) overlay. | 2110000 | 1447954 | 1447954 |  | 2009-09-21 | 2009-10-21 | 2009-11-24 | SARRA-000C(307)E | 2009-11-18 | 2009-12-02 | Awarded 11/24/09 | #REF! | 4 | 4.4
04294921 | 04-294924 | 04-Ala-24-5.3/8.8 | Realign westbound Route 24 to northbound Route 13 off ramp. | 3900000 | 2429933 | 2429933 |  | 2009-10-19 | 2009-12-01 | 2009-12-22 | ARRAL-P024(031) | 2009-12-29 | 2010-01-12 | Awarded 12/22/09 | #REF! | 4 | 4.2
04294931 | 04-294934 | 04-Ala-24-R8.8 | Widen roadway and install signal and lighting. | 370000 | 311412 | 311412 |  | 2009-10-19 | 2009-11-18 | 2009-12-23 | ARRAL-P024(032) | 2009-12-16 | 2009-12-30 | Awarded 12/23/09 | #REF! | 4 | 36.1
050G0301 | 05-0G0304 | 05-SLO-101-35.6/46.3 | Crack & seat, replace PCC, place HMA on hwy & ramps and widen bridges. | 33000000 | 23899673 | 25318028.14 |  | 2009-10-26 | 2009-12-02 | 2009-12-31 | SARRA-Q101(159)N | 2009-12-30 | 2010-01-13 | Awarded 12/31/09 | #REF! | 6 | 6
024C94U1 | 02-4C94U4 | 02-Sha-44-46.6/48.3 | Improve Curve, Widen Shoulders, Add Truck Climbing Lane | 4840000 | 4113190 | 4113190 |  | 2009-11-23 | 2010-01-05 | 2010-01-21 | SARRA-P044(045)E | 2010-01-19 | 2010-02-16 | Awarded 1/21/10 | #REF! | 7 | 10.1
100L5901 | 10-0L5904 | 10-Sta-99-R16.8/R24.5 | PERFORM HIGHWAY PLANTING AND INSTALL IRRIGATION SYSTEM | 880000 | 416870.62 | 466143.5 |  | 2009-11-30 | 2010-01-13 | 2010-02-09 | SARRA-P099(522)E | 2010-02-10 | 2010-02-24 | Awarded 2/9/10 | #REF! | 5 | 0.8
120G7301 | 12-0G7304 | 12-Ora-5-6.1/31.2 | Remove and prune trees, install planting and irrigation. | 1200000 | 796199.2 | 864041.7 |  | 2009-12-07 | 2010-01-28 | 2010-04-14 | SARRAE-005-2(943)E | 2010-02-25 | 2010-03-11 | Awarded 4/14/10 | #REF! | 10 | 2.9
071219U1 | 07-1219U4 | 07-LA-5,170-58.0/63.4,R32.3/R33.1 | Construct HOV lanes, connectors and replace slabs. | 160000000 | 109299288.7 | 109299288.7 |  | 2009-12-28 | 2010-02-18 | 2010-05-06 | SARRAL-005-3(033)N | 2010-03-18 | 2010-04-01 | Awarded 5/6/10 | #REF! | 6 | 6.85
04163741 | 04-163744 | 04-SF-101-8.2/9.2 | Construct tunnel, retaining walls, roadways, bridge and substation. | 99000000 | 57712535 | 57712535 |  | 2009-12-28 | 2010-02-26 | 2010-03-23 | SARRA-Q101(153)N | 2010-03-03 | 2010-03-17 | Awarded 3/23/10 | #REF! | 5 | 6.4
04151301 | 04-151304 | 04-SCl-280-R1.0/L5.0 | Install ramp metering systems, widen ramps. | 3000000 | 1528879.5 | 1528879.5 |  | 2009-12-28 | 2010-01-27 | 2010-02-17 | ARRAL-280-1(127)E | 2010-03-09 | 2010-03-23 | Awarded 2/17/10 | #REF! | 9 | 14
04150341 | 04-150344 | 04-SCl-280-R2.0/L5.0 | Install ramp metering systems, widen onramps. | 2530000 | 1664671.59 | 1664671.59 |  | 2009-12-28 | 2010-01-26 | 2010-02-22 | ARRAL-280-1(126)E | 2010-03-03 | 2010-03-17 | Awarded 2/22/10 | #REF! | 10 | 12.5
04153401 | 04-153404 | 04-SM-280-R20.3/R27.3 | Install ramp metering systems and widen ramp. | 3680000 | 2122625 | 2122625 |  | 2010-01-04 | 2010-02-02 | 2010-02-22 | ARRAL-280-1(129)E | 2010-03-17 | 2010-03-31 | Awarded 2/22/10 | #REF! | 9 | 10.4
050P9101 | 05-0P9104 | 05-SB-154-23.0 | Construct bridge barrier. | 890000 | 648310 | 648310 |  | 2010-02-01 | 2010-02-24 | 2010-03-24 | ARRAL-P154(018)E | 2010-03-24 | 2010-04-07 | Awarded 3/24/10 | #REF! | 6 | 6.2
09327101 | 09-327104 | 09-Mno-108, 395-15.1,92.1/96.1 | Install wildlife crossings and wildlife fencing. | 2550000 | 1467525 | 1467525 |  | 2010-02-16 | 2010-03-17 | 2010-04-27 | SARRA-X051(025)E | 2010-04-14 | 2010-04-28 | Awarded 4/27/10 | #REF! | 5 | 5.1
100L5701 | 10-0L5704 | 10-SJ-205-1.7/R12.6 | PERFORM HIGHWAY PLANTING AND INSTALL IRRIGATION SYSTEMS | 1240000 | 707158.3 | 707158.3 |  | 2010-02-16 | 2010-03-16 | 2010-04-05 | SARRA-205-6(328)49E | 2010-04-13 | 2010-04-27 | Awarded 4/5/10 | #REF! | 7 | 7.1
024C5801 | 02-4C5804 | 02-Teh-99-11.6/12.6 | Install Sidewalks, Curb, Gutters, Deck Lighting & Drainage Systems | 1710000 | 1440586.5 | 1440586.5 |  | 2010-02-16 | 2010-03-23 | 2010-05-05 | ARRAL-P099(525)E | 2010-04-20 | 2010-05-04 | Awarded 5/5/10 | #REF! | 7 | 7.7
032A6901 | 03-2A6904 | 03-Nev-49-15.4/18.0 | Widen roadway with HMA over AB, const conc barrier and sound walls. | 15000000 | 8393579 | 8393579 |  | 2010-02-22 | 2010-04-21 | 2010-05-28 | SARRA-P049(148)E | 2010-05-19 | 2010-06-02 | Awarded 5/28/10 | #REF! | 4 | 4.1
031A4321 | 03-1A4324 | 03-Sut-99-10.9/14.7 | Widen to provide four lane segment. | 46000000 | 30436533.88 | 30436533.88 |  | 2010-02-22 | 2010-04-07 | 2010-07-14 | SARRA-P099(529)E | 2010-05-05 | 2010-05-19 | Awarded 7/14/10 | #REF! | 3 | 0.9
12071621 | 12-071624 | 12-Ora-22,405-R0.7/R2.9,20.4/22.3 | Widen freeway and construct bridges, retaining walls, and sound walls. | 110000000 | 65784398.7 | 65784398.7 |  | 2010-02-22 | 2010-04-15 | 2010-06-11 | ARRAL-X059(051)N | 2010-05-13 | 2010-05-27 | Awarded 6/11/10 | #REF! | 5 | 5.7
02373101 | 02-373104 | 02-Plu-70-56.5/57.2 | Construct Spanish Creek Bridge with Spandrel Column Structure. | 20200000 | 12777000 | 12777000 |  | 2010-02-22 | 2010-04-13 | 2010-05-03 | SARRA-P070(099)E | 2010-04-27 | 2010-05-11 | Awarded 5/3/10 | #REF! | 5 | 5
09345101 | 09-345104 | 09-Iny-168-13.5/15.0 | Shoulder widening and place HMA (Open Graded) overlay. | 1170000 | 776378 | 776378 |  | 2010-02-22 | 2010-03-16 | 2010-04-21 | SARRA-S168(053)E | 2010-04-13 | 2010-04-27 | Awarded 4/21/2010 | #REF! | 6 | 5.8
09333801 | 09-333804 | 09-Iny-190-47.4 | Pave and improve an intersection, access road and parking area. | 580000 | 373740 | 373740 |  | 2010-02-22 | 2010-03-23 | 2010-04-29 | SARRA-P190(013)E | 2010-04-20 | 2010-05-04 | Awarded 4/29/10 | #REF! | 4 | 0
024C9501 | 02-4C9504 | 02-Tri-299-50.7/51.5 | Traffic Calming Elements, Sidewalk and Landscape | 250000 | 221865 | 247369 |  | 2010-03-01 | 2010-03-24 | 2010-04-29 | SARRA-STPE-P299(157)E | 2010-04-21 | 2010-05-05 | Awarded 4/29/10 | #REF! | 7 | 8.9
050S2101 | 05-0S2104 | 05-SB-1-R23.3/M29.9 | Place microsurfacing seal coat on existing roadway. | 1430000 | 1372797.9 | 1372797.9 |  | 2010-03-01 | 2010-04-13 | 2010-05-10 | SARRA-P001(545)E | 2010-04-20 | 2010-05-04 | Awarded 5/10/10 | #REF! | 5 | 5
050S2201 | 05-0S2204 | 05-SB-154-23.4/32.2 | Place HMA (Open Graded) overlay on existing pavement. | 1690000 | 1498182 | 1498182 |  | 2010-03-01 | 2010-04-06 | 2010-05-05 | SARRA-P154(019)E | 2010-05-04 | 2010-05-18 | Awarded 5/5/10 | #REF! | 3 | 26.4
060A4901 | 06-0A4904 | 06-Fre-41-R30.7/R31.7 | HIGHWAY PLANTING AND IRRIGATION WITH PAVING AT EXTENDED GORE AREAS | 950000 | 611138.06 | 611138.06 |  | 2010-03-08 | 2010-04-27 | 2010-05-24 | SARRAE-P041(115)E | 2010-05-04 | 2010-05-18 | Awarded 5/24/10 | #REF! | 5 | 5
100U7001 | 10-0U7004 | 10-Alp-4-24.4/31.7 | Repair failed areas and resurface road with HMA. | 980000 | 896896 | 896896 |  | 2010-03-08 | 2010-05-11 | 2010-06-08 | SARRA-P004(135)E | 2010-05-05 | 2010-05-19 | Awarded 6/8/10 | #REF! | 3 | 3
01464301 | 01-464304 | 01-Men-101-R0.1/R101.6 | Reconstruct Metal Beam Guard Railing. | 4590000 | 4052600.78 | 4052600.78 |  | 2010-03-22 | 2010-04-20 | 2010-06-10 | SARRA-Q101(169)E | 2010-05-18 | 2010-06-01 | Awarded 6/10/10 | #REF! | 4 | 4.2
01449401 | 01-449404 | 01-Men-101-21.1/33.7 | Remove & Replace PCC Pavement and Construct Rumble Strip. | 16300000 | 10414674 | 10414674 |  | 2010-04-12 | 2010-05-04 | 2010-07-23 | NH-Q101(168)E | 2010-06-01 | 2010-06-15 | Awarded 7/23/10 | #REF! | 3 | 3.9
041A9801 | 04-1A9804 | 04-SCl-101-31.8/34.3 | Freeway to be widen and interchange to be reconstructed. | 37000000 | 26229496 | 23445671 | A+B | 2010-04-19 | 2010-07-27 | 2010-11-09 | ARRAL-Q101(164) | 2010-07-07 | 2010-07-21 | Awarded 11/9/10 | #REF! | 6 | 6.5
071218V1 | 07-1218V4 | 07-LA-5-50.8/58.0 | Const HOV lanes, retaining walls, sound walls and replace conc pvmt. | 63000000 | 52682730.56 | 52682730.56 |  | 2010-05-17 | 2010-06-10 | 2010-10-14 | SARRAL-005-3(029)N | 2010-05-20 | 2010-06-03 | Awarded 10/14/10 | #REF! | 4 | 4.3
060K8901 | 06-0K8904 | 06-Ker-5-36.1/54.2 | Replace concrete panel, reconstruct lane and shoulder. | 28000000 | 33129569 | 30378869 | A+B | 2010-09-20 | 2010-10-27 |  | IM-SARRA-005-4(185)241E | 2010-11-24 | 2010-12-04 | Awarded 12/13/10 | #REF! | 4 | 0
07252501 | 07-252504 | 07-LA-5-R59.7/R73.7 | Place rubberized HMA (Type G) and replace concrete pavement. | 19500000 | 20154165.5 | 20154165.5 |  | 2010-09-20 | 2010-11-18 |  | SARRA-IM-005-3(043)E | 2010-11-18 | 2010-11-28 | Awarded 1/19/2011 | #REF! | 5 | 11
080A6411 | 08-0A6414 | 08-SBd-15-160.9/161.5 | Constructing interpretive displays and landscaping. | 910000 | 832980 | 832980 |  | 2010-10-04 | 2010-11-04 |  | SARRAE-STPE-015-3(044)263E | 2010-12-02 | 2010-12-12 | Awarded 1/25/11 | #REF! | 4 | 5.2
031E14U1 | 03-1E14U4 | 03-ED-50-66.7/67.8 | Reconstruct concrete barrier railing and install culvert liners. | 2510000 | 1897423 | 1897423 |  | 2010-10-18 | 2010-11-17 |  | SARRA-NH-P050(125)E | 2010-12-15 | 2010-12-29 | Awarded 2/8/2011 | #REF! | 4 | 6.7
10279801 | 10-279804 | 10-Mer-165-11.7/26.7 | Existing roadway to be overlaid with HMA (Type A). | 10200000 |  | 10949891.36 |  | 2010-10-25 | 2011-05-03 |  | SARRA-STP-BRSTP-P165(011)E | 2011-06-30 | 2011-07-15 | Awarded 5/27/11 | #REF! | 5 | 5.9
080F1001 | 08-0F1004 | 08-SBd,Riv-71-4.9/8.5,0.0/1.8 | PERFORM HIGHWAY PLANTING AND INSTALL IRRIGATION SYSTEM | 820000 |  | 505166.5 |  | 2010-11-01 | 2010-12-09 |  | SARRAE-STPE-P071(058)E | 2011-01-04 | 2011-01-18 | Awarded 1/26/11 | #REF! | 3 | 6.4
060A9701 | 06-0A9704 | 06-Tul-99-22.4 | Demolish and construct new facilities and landscaping at rest area. | 8800000 |  | 8489950 |  | 2010-11-01 | 2011-03-09 |  | NH-SARRA-STPE-SARRAE- | 2011-05-09 | 2011-05-23 | Awarded 4/6/11 | #REF! | 1 | 2.4
07252101 | 07-252104 | 07-LA-101-31.1/38.2 | Cold plane AC Pvmt, place HMA, and replace concrete slabs. | 12500000 |  | 20154165.5 | A+B | 2010-11-01 | 2010-12-09 |  | SARRA-Q101(182)E | 2011-01-06 | 2011-01-20 | Awarded 2/10/11 | #REF! | 6 | 6.1
112T0401 | 11-2T0404 | 11-SD-5, 805-R49.9/R51.7, 42.6/46.5 | Construct HOV lanes and direct access ramp. | 49000000 |  | 51432888.8 | A+B | 2010-11-08 | 2010-12-16 |  | ARRAL-805(610)N | 2011-01-13 | 2011-01-27 | Awarded 1/28/11 | #REF! | 5 | 5.3
11091831 | 11-091834 | 11-SD-905,805-R8.4/R9.8,3.1/4.2 | Construct new freeway (Phase 2.) | 13700000 |  | 13639392.5 | A+B | 2010-11-22 | 2011-01-20 |  | SARRA-A905(020)N | 2011-02-17 | 2011-03-03 | Awarded 3/7/11 | #REF! | 6 | 6.2
|  |  | Sum | 1734163000 |  | 1289971500.5
Formulas:
Target Approval Date = +[Target Award Date]+14

## 1011
CONTRACT # | Goals | DBE WBE CERT. %
01-380504 | 5 | 0.4
01-449404 | 3 | 3.9
01-464304 | 4 | 4.2
02-0E6104 | 4 | 4.2
02-0E6504 | 4 | 2.4
02-1E3204 | 6 | 0.2
02-1E9804 | 5 | 8.6
02-2C50U4 | 4 | 4.1
02-373104 | 5 | 5
02-4C5804 | 7 | 7.7
02-4C94U4 | 7 | 10.1
02-4C9504 | 7 | 8.9
03-0C2814 | 5 | 5.3
03-1A4324 | 3 | 0.9
03-1A8414 | 5 | 5
03-1E0304 | 5 | 0.2
03-1E14U4 | 4 | 6.7
03-2A6904 | 4 | 4.1
03-366904 | 5 | 0.42
03-3C8804 | 4 | 4.3
03-3M2004 | 8 | 1
03-3M6204 | 4 | 2.7
03-4C0304 | 4 | 14.1
03-4C0904 | 5 | 1.5
04-150344 | 10 | 12.5
04-150474 | 4 | 4.5
04-151304 | 9 | 14
04-153404 | 9 | 10.4
04-163744 | 5 | 6.4
04-177904 | 4 | 0.3
04-1A9804 | 6 | 6.5
04-1E2204 | 4 | 4
04-1E3204 | 4 | 4.3
04-1E3804 | 5 | 9.1
04-1E3904 | 4 | 7.8
04-272024 | 7 | 0.8
04-294914 | 3 | 2.9
04-294924 | 4 | 4.2
04-294934 | 4 | 36.1
04-4C15U4 | 6 | 1.22
05-0E4704 | 4 | 4.1
05-0F7104 | 6 | 0.6
05-0G0304 | 6 | 6
05-0L8004 | 5 | 1.9
05-0P9104 | 6 | 6.2
05-0S2104 | 5 | 5
05-0S2204 | 3 | 26.4
06-0A4904 | 5 | 5
06-0A9704 | 1 | 2.4
06-0C8004 | 4 | 4
06-0K7204 | 4 | 6.2
06-0K7404 | 4 | 9.7
06-0K8904 | 4 | 0
06-0K9104 | 4 | 16
06-342514 | 7 | 7.2
06-416104 | 4 | 7.3
06-430104 | 4 | 0.17
06-432104 | 4 | 4.8
07-1218V4 | 4 | 4.3
07-1219U4 | 6 | 6.85
07-226514 | 12 | 0
07-226524 | 13 | 13.3
07-226534 | 13 | 0.08
07-226544 | 11 | 36.9
07-252104 | 6 | 6.1
07-252504 | 5 | 11
07-252714 | 7 | 7.5
07-266704 | 6 | 9.1
07-269004 | 4 | 0
07-2Y6304 | 4 | 5.7
07-3Y7904 | 3 | 3
07-3Y8104 | 4 | 22.3
08-0A6414 | 4 | 5.2
08-0F1004 | 3 | 6.4
08-0K6204 | 6 | 0
08-0K8004 | 4 | 4.1
08-0L2804 | 4 | 4.3
08-0L6804 | 9 | 4
08-0L7304 | 4 | 0
08-0L7504 | 9 | 0
08-394704 | 6 | 1
08-422204 | 7 | 7.6
08-434304 | 5 | 3.4
08-456004 | 8 | 1.2
09-327104 | 5 | 5.1
09-333804 | 4 | 0
09-339204 | 4 | 0
09-339604 | 4 | 4.4
09-345104 | 6 | 5.8
10-0G7704 | 7 | 8.3
10-0H04U4 | 6 | 6
10-0K0204 | 5 | 0.2
10-0L5704 | 7 | 7.1
10-0L5904 | 5 | 0.8
10-0S4404 | 6 | 6.2
10-0S4504 | 4 | 4
10-0S4604 | 4 | 4
10-0S4704 | 4 | 5.4
10-0U7004 | 3 | 3
10-279804 | 5
11-080104 | 10 | 0.95
11-081644 | 7 | 5
11-091834 | 6 | 6.2
11-288804 | 6 | 0.38
11-2T0404 | 5 | 5.3
12-071624 | 5 | 5.7
12-085104 | 6 | 6
12-0G0304 | 6 | 6
12-0G0404 | 6 | 0.5
12-0G7304 | 10 | 2.9
12-0J0904 | 9 | 9.4
12-0J7004 | 8 | 8.6
12-0K2004 | 5 | 6.1
C02-0E6104
C02-0E6504
C02-1E3204
C02-1E9804
C07-1218V4 | 4 | 4.7
C08-0L2804
C08-0L6804
C08-0L7304
R07-1218V4 | 4 | 4.7
R11-2T0404 | 5 | 4.6