## Sheet1
[6 empty] | Collaborators | [11 empty] | Timeline
Area | Responsible Position | Task | Phase | Area | Collaborators | Chairman | Financial Manager | Competition Manager | Venue Manager | Transportation Coordinator | Volunteers Manager | Accommodation Manager | Media/Hosting | Logistics Manager | PR Manager | Accreditation Manager | Marketing Manager | Pre-contracting | T-6 months | T-3 months | T-1 month | T-1 week | Competition | After the competition
Organizing Committee | Chairman | Develop organizational chart adapted to the event |  |  | Chairman; Financial Manager; Competition Manager; | x | x | x | [9 empty] | x | [6 empty] | Chairman; | Financial Manager; | Competition Manager;
Organizing Committee | Chairman | Appoint responsible persons for key positions. Organize initial meetings, set roles and guidelines |  |  | Chairman; | x | [11 empty] | x | x | [5 empty] | Chairman;
Organizing Committee | Chairman | Recruitment - make sure all positions are covered by appropriate people |  |  | Financial Manager; Competition Manager; Venue Manager; Transportation Coordinator; Volunteers Manager; Accommodation Manager; Media/Hosting; Logistics Manager; PR Manager; Accreditation Manager; Marketing Manager; |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x |  |  |  | Financial Manager; | Competition Manager; | Venue Manager; | Transportation Coordinator; | Volunteers Manager; | Accommodation Manager; | Media/Hosting; | Logistics Manager; | PR Manager; | Accreditation Manager; | Marketing Manager;
Finances | Chairman | Supervise the preparation of grant applications and other fundraising sources |  |  | Chairman; Financial Manager; | x | x | [10 empty] | x | x | x | x | x |  |  | Chairman; | Financial Manager;
Organizing Committee | Competition Manager | Attend previous year's edition of the event |  |  | Chairman; Venue Manager; Volunteers Manager; | x |  |  | x |  | x | [6 empty] | x | x | [5 empty] | Chairman; |  |  | Venue Manager; |  | Volunteers Manager;
Volunteers | Volunteers Manager | Develop policies and framework. Develop and communicate Volunteer Code of Conduct and plan meetings/trainings to discuss it |  |  | Chairman; Volunteers Manager; | x |  |  |  |  | x | [7 empty] | x | x | x |  |  |  | Chairman; |  |  |  |  | Volunteers Manager;
Volunteers | Volunteers Manager | Recruit volunteers |  |  | Volunteers Manager; | [5 empty] | x | [7 empty] | x | x | x | [8 empty] | Volunteers Manager;
Organizing Committee | Chairman | Develop and sign the contract with the WCF. Provide copies to the Executive Committee |  |  | Chairman; Financial Manager; Competition Manager; | x | x | x | [9 empty] | x | [6 empty] | Chairman; | Financial Manager; | Competition Manager;
Finances | Financial Manager | Liaise with WCF on local sponsorship matters. Compile and present list to the WCF |  |  | Chairman; Financial Manager; Competition Manager; Marketing Manager; | x | x | x | [8 empty] | x | x | x |  | x |  |  |  | Chairman; | Financial Manager; | Competition Manager; | [8 empty] | Marketing Manager;
Ceremonies | PR Manager | Determine the ceremonies that will be held (Opening & Closing Ceremonies, Opening & Closing Banquets/Receptions, Sponsor's Reception etc.). Book facilities for each of them, shortlist necessary logistics and address them with the Logistics Manager |  |  | Chairman; Competition Manager; Logistics Manager; | x |  | x | [5 empty] | x |  |  |  | x | x |  | x |  | x |  | Chairman; |  | Competition Manager; | [5 empty] | Logistics Manager;
Finances | Financial Manager | Develop and propose the budget |  |  | Chairman; Financial Manager; Competition Manager; | x | x | x | [9 empty] | x | [6 empty] | Chairman; | Financial Manager; | Competition Manager;
Finances | Chairman | Approve the budget and liaise with the WCF on this matter |  |  | Chairman; | x | [11 empty] | x | [6 empty] | Chairman;
Organizing Committee | PR Manager | Appoint spokesperson. Develop communication strategy |  |  | PR Manager; | [9 empty] | x |  |  |  | x | [14 empty] | PR Manager;
Media/Hosting | PR Manager | Liaise with WCF Media to determine what roles need to be covered by which party (ex: website, press releases etc.). Make sure the contract is clear on all these points |  |  | Competition Manager; Media/Hosting; PR Manager; Marketing Manager; |  |  | x |  |  |  |  | x |  | x |  | x | x | [8 empty] | Competition Manager; |  |  |  |  | Media/Hosting; |  | PR Manager; |  | Marketing Manager;
Organizing Committee | Chairman | Prepare message/speech to be inserted into the handouts (presentation document, volunteers handbook etc.) |  |  | Chairman; | x | [11 empty] | x | x | [5 empty] | Chairman;
Organizing Committee | Chairman | Organize the meetings with WCF Delegates, according to the agreed schedule |  |  | Chairman; Financial Manager; Competition Manager; | x | x | x | [9 empty] | x | x | x | x |  |  |  | Chairman; | Financial Manager; | Competition Manager;
Organizing Committee | Chairman | Organize progress meetings with the Executive Committee, initially every month and then at least once every two weeks, as the competition date approaches. Assess risks and address problems. Send minutes to the WCF TD to keep them up-to-date |  |  | Chairman; Financial Manager; Competition Manager; Venue Manager; Transportation Coordinator; Volunteers Manager; Accommodation Manager; Media/Hosting; Logistics Manager; PR Manager; Accreditation Manager; Marketing Manager; | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x |  |  |  | Chairman; | Financial Manager; | Competition Manager; | Venue Manager; | Transportation Coordinator; | Volunteers Manager; | Accommodation Manager; | Media/Hosting; | Logistics Manager; | PR Manager; | Accreditation Manager; | Marketing Manager;
Media/Hosting | Chairman | Together with PR Manager compile a list with invitations for VIPs, dignitaries, representatives |  |  | Chairman; Media/Hosting; PR Manager; Accreditation Manager; | x | [6 empty] | x |  | x | x |  |  | x | x |  |  |  |  | Chairman; | [6 empty] | Media/Hosting; |  | PR Manager; | Accreditation Manager;
Ceremonies | PR Manager | Appoint Master of Ceremonies |  |  | PR Manager; | [9 empty] | x | [5 empty] | x | x | [11 empty] | PR Manager;
Organizing Committee | Chairman | Call Walkthrough meeting. It will involve Competitions Manager, Venue Manager, Logistics Manager, Volunteers Manager and it will take form of a simulation, covering all logistic aspects of the event. It will identify areas needing improvement, conflicts and gaps in planning or responsibility and test the level of understanding and commitment of everyone involved. |  |  | Chairman; Financial Manager; Competition Manager; Venue Manager; Transportation Coordinator; Volunteers Manager; Accommodation Manager; Media/Hosting; Logistics Manager; PR Manager; Accreditation Manager; Marketing Manager; | x | x | x | x | x | x | x | x | x | x | x | x |  |  | x | x |  |  |  | Chairman; | Financial Manager; | Competition Manager; | Venue Manager; | Transportation Coordinator; | Volunteers Manager; | Accommodation Manager; | Media/Hosting; | Logistics Manager; | PR Manager; | Accreditation Manager; | Marketing Manager;
Ceremonies | Chairman | Prepare speeches for ceremonies and banquets |  |  | Chairman; PR Manager; | x | [8 empty] | x | [6 empty] | x |  |  | Chairman; | [8 empty] | PR Manager;
Organizing Committee | Chairman | Conduct daily meetings with the Executive Committee, assess risks, address problems |  |  | Chairman; Financial Manager; Competition Manager; Venue Manager; Transportation Coordinator; Volunteers Manager; Accommodation Manager; Media/Hosting; Logistics Manager; PR Manager; Accreditation Manager; Marketing Manager; | x | x | x | x | x | x | x | x | x | x | x | x | [5 empty] | x |  | Chairman; | Financial Manager; | Competition Manager; | Venue Manager; | Transportation Coordinator; | Volunteers Manager; | Accommodation Manager; | Media/Hosting; | Logistics Manager; | PR Manager; | Accreditation Manager; | Marketing Manager;
Competition | Chairman | Inspect the facility, attend to games, attend official functions and protocol (special guests, VIPs etc.) |  |  | Chairman; | x | [16 empty] | x |  | Chairman;
Competition | Competition Manager | Stones. Make sure the right stones are provided in time, that they are securely transported and stored and properly cooled down. Refer to contract |  |  | Competition Manager; Logistics Manager; |  |  | x | [5 empty] | x |  |  |  | x | x |  | x | x |  |  |  |  | Competition Manager; | [5 empty] | Logistics Manager;
Competition | Competition Manager | Check equipment list and order from the WCF any needed equipment. Address problems with TD and Chief Ice Technician |  |  | Competition Manager; Venue Manager; Logistics Manager; |  |  | x | x |  |  |  |  | x |  |  |  |  | x | x | [6 empty] | Competition Manager; | Venue Manager; |  |  |  |  | Logistics Manager;
Competition | Competition Manager | Check with Chief Ice Technician upon the timeframe for preparing the ice for the event and make sure of availability of ice and of equipment |  |  | Competition Manager; Venue Manager; Logistics Manager; |  |  | x | x |  |  |  |  | x |  |  |  |  | x | x | x | [5 empty] | Competition Manager; | Venue Manager; |  |  |  |  | Logistics Manager;
Construction & Decorations | Venue Manager | Obtain a copy of the plan/structure of the arena. Forward a copy to the Chief Ice Technician, MRO and TD |  |  | Venue Manager; |  |  |  | x | [8 empty] | x | [9 empty] | Venue Manager;
Construction & Decorations | Venue Manager | Develop an initial floor plan |  |  | Venue Manager; |  |  |  | x | [8 empty] | x | [9 empty] | Venue Manager;
Organizing Committee | Venue Manager | Negotiate terms of the contract with Arena Management, including security, access, clean up, construction, first-aid, signage, merchandising and special installations, parking etc. |  |  | Chairman; Financial Manager; Venue Manager; | x | x |  | x | [8 empty] | x | [6 empty] | Chairman; | Financial Manager; |  | Venue Manager;
Logistics | Logistics Manager | Compile a list with all needed equipment (chairs, tables, carpet, drapes, computers, printers, Internet access etc.) and keep it updated |  |  | Logistics Manager; Marketing Manager; | [8 empty] | x |  |  | x | x | x | x | x | x | [10 empty] | Logistics Manager; |  |  | Marketing Manager;
Logistics | Logistics Manager | Find suppliers for all the needed logistics |  |  | Logistics Manager; | [8 empty] | x |  |  |  | x | x | x | x | x | [10 empty] | Logistics Manager;
Construction & Decorations | Chairman | Determine if there are any special requests from sponsors (i.e. install a booth or display a product inside the arena etc.) and check with the WCF for compliancy. Assist in coordinating special requirements |  |  | Chairman; Venue Manager; Logistics Manager; Marketing Manager; | x |  |  | x |  |  |  |  | x |  |  | x |  | x | x | x |  |  |  | Chairman; |  |  | Venue Manager; |  |  |  |  | Logistics Manager; |  |  | Marketing Manager;
Transportation | Transportation Coordinator | Evaluate parking access and policy. Determine if access cards are needed and available, set rules for distributing them. If unavailable, determine if there is need to design some. Review access to the arena and parking capacity |  |  | Transportation Coordinator; |  |  |  |  | x | [8 empty] | x | x | [8 empty] | Transportation Coordinator;
Transportation | Transportation Coordinator | Determine the transport capacity needed every day and arrange proper means of transportation (buses, VIP cars etc.). Design the schedule considering draws, but keep flexibility for special situations (tiebreakers and others) |  |  | Transportation Coordinator; Marketing Manager; |  |  |  |  | x | [6 empty] | x |  | x | x | x | x | [6 empty] | Transportation Coordinator; | [6 empty] | Marketing Manager;
Transportation | Transportation Coordinator | Determine drop-in and drop-off areas for the transportation offered by the OC. Make sure they have appropriate signage and that information on transportation is distributed to all guests (through Guides/handouts plus through Accreditation desks, hotel reception, volunteers) |  |  | Venue Manager; Transportation Coordinator; Volunteers Manager; Media/Hosting; Accreditation Manager; |  |  |  | x | x | x |  | x |  |  | x |  |  |  |  | x | x | x |  |  |  |  | Venue Manager; | Transportation Coordinator; | Volunteers Manager; |  | Media/Hosting; |  |  | Accreditation Manager;
Transportation | Transportation Coordinator | Arrange airport transfer for guests. Keep a list with everyone's arrival and departure dates; make sure everybody has an emergency contact number in case of unexpected problems. Display chart in the reception area of the hotel, make sure it is still displayed during the last days |  |  | Transportation Coordinator; Accommodation Manager; |  |  |  |  | x |  | x | [8 empty] | x | x | x | x |  |  |  |  | Transportation Coordinator; |  | Accommodation Manager;
Transportation | Transportation Coordinator | Determine special transportation for VIP's. Arrange special cars |  |  | Competition Manager; Transportation Coordinator; |  |  | x |  | x | [9 empty] | x |  | x | x |  |  |  | Competition Manager; |  | Transportation Coordinator;
Transportation | Transportation Coordinator | Establish an efficient way for communication between guests and drivers. If needed, appoint one or more persons to act as dispatcher. Test and make sure it works |  |  | Transportation Coordinator; |  |  |  |  | x | [10 empty] | x | x | x | [5 empty] | Transportation Coordinator;
Logistics | Venue Manager | Cleaning. Specify in the contract with the Arena all areas that need to be cleaned and how often. |  |  | Venue Manager; Logistics Manager; |  |  |  | x |  |  |  |  | x |  |  |  |  | x | [8 empty] | Venue Manager; |  |  |  |  | Logistics Manager;
Logistics | Venue Manager | Make sure cleaning is efficient and the garbage disposal system is working properly and enough supplies are provided |  |  | Venue Manager; Logistics Manager; |  |  |  | x |  |  |  |  | x | [7 empty] | x | x | x |  |  |  | Venue Manager; |  |  |  |  | Logistics Manager;
Accreditations | Accreditation Manager | Develop accreditation plan and discuss it with the WCF Delegates. Separate areas inside the arena and design the flow of persons plus security measures |  |  | Competition Manager; Venue Manager; Accreditation Manager; |  |  | x | x | [6 empty] | x |  |  | x | [7 empty] | Competition Manager; | Venue Manager; | [6 empty] | Accreditation Manager;
Accreditations | Accreditation Manager | Make sure facility personnel has specific accreditations and they are using them |  |  | Competition Manager; Venue Manager; Accreditation Manager; |  |  | x | x | [6 empty] | x |  |  |  | x | x | x | x |  |  |  | Competition Manager; | Venue Manager; | [6 empty] | Accreditation Manager;
Logistics | Venue Manager | Develop and manage a list (critical path algorithm) with steps that need to be completed in order to have everything in place for the competition (i.e. Internet installation, decorations, carpet, lights, cameras, drapes etc.). Keep it updated as time goes by and the competition date approaches. Hold weekly meetings with responsible persons involved in the process |  |  | Competition Manager; Venue Manager; Logistics Manager; |  |  | x | x |  |  |  |  | x |  |  |  |  | x | x | x | x |  |  |  |  | Competition Manager; | Venue Manager; |  |  |  |  | Logistics Manager;
Organizing Committee | Venue Manager | Distribute final version of the floor plan (to be also displayed in appropriate areas) |  |  | Chairman; Competition Manager; Venue Manager; Volunteers Manager; Media/Hosting; Logistics Manager; PR Manager; Accreditation Manager; | x |  | x | x |  | x |  | x | x | x | x |  |  |  |  | x | x | x |  | Chairman; |  | Competition Manager; | Venue Manager; |  | Volunteers Manager; |  | Media/Hosting; | Logistics Manager; | PR Manager; | Accreditation Manager;
Organizing Committee | Venue Manager | Determine emergency procedures and responsible persons (fire, power failure, technical failures etc.). Communicate them to everybody involved |  |  | Competition Manager; Venue Manager; Transportation Coordinator; Volunteers Manager; Media/Hosting; Logistics Manager; PR Manager; Accreditation Manager; |  |  | x | x | x | x |  | x | x | x | x |  |  |  |  | x | [5 empty] | Competition Manager; | Venue Manager; | Transportation Coordinator; | Volunteers Manager; |  | Media/Hosting; | Logistics Manager; | PR Manager; | Accreditation Manager;
Competition | Venue Manager | Arrange for procurement/delivery of foam dividers, bumpers, sticky mats, carpet as required |  |  | Competition Manager; Venue Manager; Logistics Manager; |  |  | x | x |  |  |  |  | x | [5 empty] | x | x | [5 empty] | Competition Manager; | Venue Manager; |  |  |  |  | Logistics Manager;
Competition | Venue Manager | Arrange a room for Ice Technicians (4-8 people), with secure access, situated in proximity to the Field of Play |  |  | Competition Manager; Venue Manager; |  |  | x | x | [11 empty] | x | [5 empty] | Competition Manager; | Venue Manager;
Competition | Venue Manager | Secure a storage area for stones, scoreboards, equipment etc. |  |  | Competition Manager; Venue Manager; |  |  | x | x | [11 empty] | x | [5 empty] | Competition Manager; | Venue Manager;
Ceremonies | Venue Manager | Arrange for a safe/secure area to store medals and trophy |  |  | Competition Manager; Venue Manager; PR Manager; |  |  | x | x | [5 empty] | x | [5 empty] | x | [5 empty] | Competition Manager; | Venue Manager; | [5 empty] | PR Manager;
Uniforms | Logistics Manager | Order equipment for volunteers |  |  | Logistics Manager; | [8 empty] | x |  |  |  |  | x | x | x | [11 empty] | Logistics Manager;
Uniforms | Logistics Manager | Order equipment for officials and arrange for a procedure to solve fitting and replacements if needed |  |  | Competition Manager; Logistics Manager; |  |  | x | [5 empty] | x | [5 empty] | x | x | x |  |  |  |  | Competition Manager; | [5 empty] | Logistics Manager;
Construction & Decorations | Venue Manager | Link with Broadcasters and Ice Technicians to determine the timeline for installing cameras and complete the light tests. It is very important to minimize any work above the ice surface after flooding has started |  |  | Competition Manager; Venue Manager; |  |  | x | x | [11 empty] | x | x |  |  |  |  | Competition Manager; | Venue Manager;
Competition | Venue Manager | Check and confirm delivery dates and timeline for competition equipment - measurer, biter stick, handles, scrapers and blades. Inform immediately Chief Ice Technician and TD of any risks and problems that may occur. |  |  | Competition Manager; Venue Manager; Logistics Manager; |  |  | x | x |  |  |  |  | x | [5 empty] | x | x | [5 empty] | Competition Manager; | Venue Manager; |  |  |  |  | Logistics Manager;
Construction & Decorations | Venue Manager | Determine what construction works and decorations are needed to be done inside the arena and at the ice level. Make a plan. Delegate to the appointed teams and follow up frequently |  |  | Competition Manager; Venue Manager; PR Manager; |  |  | x | x | [5 empty] | x |  |  |  | x | x | x | x |  |  |  |  | Competition Manager; | Venue Manager; | [5 empty] | PR Manager;
Competition | Venue Manager | Determine and procure all materials and equipment needed for installing and maintaining the ice. Liaise with Chief Ice Technician |  |  | Competition Manager; Venue Manager; Logistics Manager; |  |  | x | x |  |  |  |  | x |  |  |  |  | x | x | x | x |  |  |  |  | Competition Manager; | Venue Manager; |  |  |  |  | Logistics Manager;
Competition | Venue Manager | Determine and procure the logos that need to be installed. Consult with Chief Ice Technician for material and providers |  |  | Competition Manager; Venue Manager; Logistics Manager; |  |  | x | x |  |  |  |  | x | [5 empty] | x | x | [5 empty] | Competition Manager; | Venue Manager; |  |  |  |  | Logistics Manager;
Construction & Decorations | Venue Manager | Determine the location of coaches' bench, media bench, timers' bench, statisticians' bench. Consult with TD, with MRO and with the Construction and Decorations team to find optimal solution |  |  | Competition Manager; Venue Manager; |  |  | x | x | [9 empty] | x | x | [6 empty] | Competition Manager; | Venue Manager;
Construction & Decorations | Venue Manager | Coordinate the construction and decoration works on the benches. Check line of sight for each |  |  | Competition Manager; Venue Manager; |  |  | x | x | [10 empty] | x | x | [5 empty] | Competition Manager; | Venue Manager;
Competition | Venue Manager | Determine place for installing time clocks and make arrangements to mount them and get them to operational status |  |  | Competition Manager; Venue Manager; Logistics Manager; |  |  | x | x |  |  |  |  | x | [6 empty] | x | x |  |  |  |  | Competition Manager; | Venue Manager; |  |  |  |  | Logistics Manager;
Competition | Venue Manager | Install scoreboards |  |  | Competition Manager; Venue Manager; Logistics Manager; |  |  | x | x |  |  |  |  | x | [6 empty] | x | x |  |  |  |  | Competition Manager; | Venue Manager; |  |  |  |  | Logistics Manager;
Logistics | Venue Manager | Make sure enough power (electricity) is available at all benches |  |  | Venue Manager; Logistics Manager; |  |  |  | x |  |  |  |  | x | [6 empty] | x | x | x |  |  |  |  | Venue Manager; |  |  |  |  | Logistics Manager;
Volunteers | Volunteers Manager | Arrange for skilled and hard working volunteers to help Ice Technicians |  |  | Competition Manager; Volunteers Manager; |  |  | x |  |  | x | [8 empty] | x | x | x | x |  |  |  | Competition Manager; |  |  | Volunteers Manager;
Volunteers | Volunteers Manager | Consult with all other managers and with the TD and put up a chart with how many volunteers are needed in each area, for each of the phases. Recruit the volunteers and keep them motivated. Keep a reserve pool, in case extras are needed |  |  | Competition Manager; Venue Manager; Transportation Coordinator; Volunteers Manager; Accommodation Manager; Media/Hosting; Logistics Manager; PR Manager; Accreditation Manager; Marketing Manager; |  |  | x | x | x | x | x | x | x | x | x | x |  | x | x | x | x | x |  |  |  | Competition Manager; | Venue Manager; | Transportation Coordinator; | Volunteers Manager; | Accommodation Manager; | Media/Hosting; | Logistics Manager; | PR Manager; | Accreditation Manager; | Marketing Manager;
Volunteers | Volunteers Manager | Organize periodic meetings (up to daily, prior to and during the event) with the volunteers, collect feedback, motivate, address problems |  |  | Volunteers Manager; | [5 empty] | x | [7 empty] | x | x | x | x | x | [6 empty] | Volunteers Manager;
Competition | Venue Manager | Arrange a meeting with PR Manager, Ceremonies and Broadcasters to make sure ice won't be affected by broadcasting or ceremonies. Consult with Chief Ice Technician |  |  | Competition Manager; Venue Manager; PR Manager; |  |  | x | x | [5 empty] | x | [5 empty] | x | x |  |  |  |  | Competition Manager; | Venue Manager; | [5 empty] | PR Manager;
Logistics | Logistics Manager | Arrange for catering/food/water for the Ice Technicians during the initial preparation of the ice. |  |  | Competition Manager; Logistics Manager; |  |  | x | [5 empty] | x | [7 empty] | x | x |  |  |  | Competition Manager; | [5 empty] | Logistics Manager;
Logistics | Logistics Manager | Arrange for catering/food/water for volunteers |  |  | Volunteers Manager; Logistics Manager; | [5 empty] | x |  |  | x | [5 empty] | x | x | x | x | [6 empty] | Volunteers Manager; |  |  | Logistics Manager;
Competition | Venue Manager | Shortlist all the logos needed to be inserted into the ice, determine who is providing them and check with the Chief Ice Technician for quality and specifications. Supervise the timeline and delivery |  |  | Competition Manager; Venue Manager; Logistics Manager; Marketing Manager; |  |  | x | x |  |  |  |  | x |  |  | x |  |  | x | x | x |  |  |  |  | Competition Manager; | Venue Manager; |  |  |  |  | Logistics Manager; |  |  | Marketing Manager;
Construction & Decorations | Venue Manager | Develop the plan (critical path) to set up, event and post-event, assess risks and determine the timeline needed to complete everything. Supervise its implementation |  |  | Chairman; Competition Manager; Logistics Manager; | x |  | x | [5 empty] | x |  |  |  |  | x | x | x | x | x | x | Chairman; |  | Competition Manager; | [5 empty] | Logistics Manager;
Communications | Logistics Manager | Arrange a conference/meeting with the TD and WCF Media to discuss all aspects regarding communications and office supplies - phone and fax lines, Internet (cable and wireless, broadband etc.), computers, printers, copiers, shredders, bins, paper, pens, clipboards etc. |  |  | Competition Manager; Venue Manager; Media/Hosting; Logistics Manager; Marketing Manager; |  |  | x | x |  |  |  | x | x |  |  | x | x | x | [7 empty] | Competition Manager; | Venue Manager; |  |  |  | Media/Hosting; | Logistics Manager; |  |  | Marketing Manager;
Communications | Logistics Manager | Determine the need of radios/communication for the organizing team and for the WCF ITO's. Ask TD about radios for the umpires and for the crew - who is providing them. Arrange for devices to be delivered and keep track of the stock |  |  | Competition Manager; Venue Manager; Volunteers Manager; Logistics Manager; |  |  | x | x |  | x |  |  | x |  |  |  | x |  |  | x | x | x | x |  |  | Competition Manager; | Venue Manager; |  | Volunteers Manager; |  |  | Logistics Manager;
Communications | Logistics Manager | Make sure all frequencies used by the radios are approved to be used according to local/national norms. Acquire appropriate temporary licenses if required |  |  | Logistics Manager; | [8 empty] | x | [5 empty] | x | x | x | [10 empty] | Logistics Manager;
Media/Hosting | Logistics Manager | Solve media room and media bench requirements |  |  | Media/Hosting; Logistics Manager; | [7 empty] | x | x | [6 empty] | x | x | x | [8 empty] | Media/Hosting; | Logistics Manager;
Logistics | Logistics Manager | Check with all the teams/departments for specific needs in terms of logistics/equipment. Ensure spare equipment is available |  |  | Competition Manager; Venue Manager; Transportation Coordinator; Volunteers Manager; Accommodation Manager; Media/Hosting; Logistics Manager; PR Manager; Accreditation Manager; Marketing Manager; |  |  | x | x | x | x | x | x | x | x | x | x |  | x |  | x | x | x |  |  |  | Competition Manager; | Venue Manager; | Transportation Coordinator; | Volunteers Manager; | Accommodation Manager; | Media/Hosting; | Logistics Manager; | PR Manager; | Accreditation Manager; | Marketing Manager;
Officials, timing, stats | Logistics Manager | Solve statisticians requirements |  |  | Competition Manager; Logistics Manager; |  |  | x | [5 empty] | x | [6 empty] | x | x | x |  |  |  | Competition Manager; | [5 empty] | Logistics Manager;
Officials, timing, stats | Logistics Manager | Solve timers requirements |  |  | Competition Manager; Logistics Manager; |  |  | x | [5 empty] | x | [6 empty] | x | x | x |  |  |  | Competition Manager; | [5 empty] | Logistics Manager;
Officials, timing, stats | Logistics Manager | Solve umpires requirements |  |  | Competition Manager; Logistics Manager; |  |  | x | [5 empty] | x | [6 empty] | x | x | x |  |  |  | Competition Manager; | [5 empty] | Logistics Manager;
Logistics | Logistics Manager | Ensure the power available is sufficient in areas where equipment is being charged |  |  | Logistics Manager; | [8 empty] | x | [6 empty] | x | x | x | [9 empty] | Logistics Manager;
Logistics | Venue Manager | If jumbo screens are provided, arrange delivery, determine their location and ensure mechanisms to secure them properly |  |  | Venue Manager; Volunteers Manager; Logistics Manager; |  |  |  | x |  | x |  |  | x | [5 empty] | x | x | [6 empty] | Venue Manager; |  | Volunteers Manager; |  |  | Logistics Manager;
Media/Hosting | Venue Manager | In case of television coverage, arrange television stands |  |  | Venue Manager; Logistics Manager; |  |  |  | x |  |  |  |  | x | [5 empty] | x | x | x | [5 empty] | Venue Manager; |  |  |  |  | Logistics Manager;
Media/Hosting | Venue Manager | In case of television coverage it would be great to arrange live feeds in the lounges and public areas |  |  | Venue Manager; Transportation Coordinator; Logistics Manager; |  |  |  | x | x |  |  |  | x | [5 empty] | x | x | x | x |  |  |  |  | Venue Manager; | Transportation Coordinator; |  |  |  | Logistics Manager;
Logistics | Venue Manager | Once sponsorship agreements have been finalized, determine and arrange places for their booths/marketing |  |  | Venue Manager; Transportation Coordinator; Logistics Manager; Marketing Manager; |  |  |  | x | x |  |  |  | x |  |  | x |  |  | x | x | x | [5 empty] | Venue Manager; | Transportation Coordinator; |  |  |  | Logistics Manager; |  |  | Marketing Manager;
Logistics | Logistics Manager | Arrange locations and cabling needed for televisions |  |  | Logistics Manager; | [8 empty] | x | [6 empty] | x | x | x | [9 empty] | Logistics Manager;
Media/Hosting | Venue Manager | In case of television coverage, arrange for commentators space |  |  | Venue Manager; Logistics Manager; |  |  |  | x |  |  |  |  | x | [5 empty] | x | x | x | [5 empty] | Venue Manager; |  |  |  |  | Logistics Manager;
Organizing Committee | Secretary | Prepare a communication directory with all contact numbers |  |  | Competition Manager; |  |  | x | [12 empty] | x | x | x |  |  |  | Competition Manager;
Organizing Committee | Secretary | Ensure all key position designated persons are available 24/7 for phone contact, in case of emergency |  |  | Competition Manager; Media/Hosting; Accreditation Manager; |  |  | x |  |  |  |  | x |  |  | x |  |  |  |  | x | x | x |  |  |  | Competition Manager; |  |  |  |  | Media/Hosting; |  |  | Accreditation Manager;
Communications | Logistics Manager | Test communication equipment is working in all areas of the arena - radios, phones, wireless Internet |  |  | Logistics Manager; | [8 empty] | x | [6 empty] | x | x | x | [9 empty] | Logistics Manager;
Logistics | Logistics Manager | Distribute the equipment to the teams. Make sure they sign for receiving. Collect them at the end and arrange the return of the loaned/rented equipment |  |  | Logistics Manager; | [8 empty] | x | [7 empty] | x | x | x | [8 empty] | Logistics Manager;
Media/Hosting | Venue Manager | Determine the location of the media room and media lounge |  |  | Venue Manager; Media/Hosting; |  |  |  | x |  |  |  | x | [6 empty] | x | x | [6 empty] | Venue Manager; |  |  |  | Media/Hosting;
Media/Hosting | Logistics Manager | Provide snacks and beverage to the media room/lounge |  |  | Media/Hosting; Logistics Manager; | [7 empty] | x | x | [8 empty] | x | [8 empty] | Media/Hosting; | Logistics Manager;
Construction & Decorations | Venue Manager | Determine the interview area/Mixed Area, at the exit of the playing field. Arrange displays/sponsors etc. |  |  | Venue Manager; Media/Hosting; |  |  |  | x |  |  |  | x | [6 empty] | x | x | x | [5 empty] | Venue Manager; |  |  |  | Media/Hosting;
Communications | Venue Manager | Determine needs for communication inside the arena and submit them to the Logistics Manager |  |  | Venue Manager; Logistics Manager; |  |  |  | x |  |  |  |  | x | [5 empty] | x | x | [6 empty] | Venue Manager; |  |  |  |  | Logistics Manager;
Competition | Venue Manager | Determine working hours (umpires, media) and arrange staffing at the arena accordingly |  |  | Competition Manager; Venue Manager; Transportation Coordinator; Volunteers Manager; |  |  | x | x | x | x | [9 empty] | x | x | x |  |  |  | Competition Manager; | Venue Manager; | Transportation Coordinator; | Volunteers Manager;
Transportation | Transportation Coordinator | Arrange transportation schedule for teams |  |  | Competition Manager; Transportation Coordinator; |  |  | x |  | x | [10 empty] | x | x | x |  |  |  | Competition Manager; |  | Transportation Coordinator;
Transportation | Transportation Coordinator | Arrange special transportation for VIP's |  |  | Competition Manager; Transportation Coordinator; |  |  | x |  | x | [10 empty] | x | x | x |  |  |  | Competition Manager; |  | Transportation Coordinator;
Transportation | Transportation Coordinator | Arrange transportation for media |  |  | Transportation Coordinator; Media/Hosting; |  |  |  |  | x |  |  | x | [7 empty] | x | x | x | [5 empty] | Transportation Coordinator; |  |  | Media/Hosting;
Transportation | Transportation Coordinator | Arrange transportation schedule for ITO's |  |  | Competition Manager; Transportation Coordinator; |  |  | x |  | x | [10 empty] | x | x | x |  |  |  | Competition Manager; |  | Transportation Coordinator;
Transportation | Transportation Coordinator | Arrange transportation schedule for volunteers |  |  | Transportation Coordinator; Volunteers Manager; |  |  |  |  | x | x | [8 empty] | x | x | x | x | [5 empty] | Transportation Coordinator; | Volunteers Manager;
Transportation | Transportation Coordinator | Arrange for parking passes and make a distribution list |  |  | Venue Manager; Transportation Coordinator; |  |  |  | x | x | [9 empty] | x | x | x | x |  |  |  |  | Venue Manager; | Transportation Coordinator;
Accreditations | Accreditation Manager | Arrange accreditations for the media |  |  | Media/Hosting; Accreditation Manager; | [7 empty] | x |  |  | x |  |  |  |  | x | x | x | [8 empty] | Media/Hosting; |  |  | Accreditation Manager;
Media/Hosting | Volunteers Manager | Arrange orientation meeting for volunteers working in the media area |  |  | Volunteers Manager; Media/Hosting; | [5 empty] | x |  | x | [8 empty] | x | [7 empty] | Volunteers Manager; |  | Media/Hosting;
Construction & Decorations | Venue Manager | Organize team to handle Construction & Decorations. Conduct orientation meetings |  |  | Venue Manager; Volunteers Manager; Logistics Manager; |  |  |  | x |  | x |  |  | x |  |  |  |  | x | x | [7 empty] | Venue Manager; |  | Volunteers Manager; |  |  | Logistics Manager;
Construction & Decorations | Venue Manager | Supervise the whole construction and decorations work. Organize progress meetings with the Construction & Decorations team. Address risks, solve problems |  |  | Venue Manager; Volunteers Manager; Logistics Manager; |  |  |  | x |  | x |  |  | x | [5 empty] | x | x | x | [5 empty] | Venue Manager; |  | Volunteers Manager; |  |  | Logistics Manager;
Construction & Decorations | Venue Manager | Check with the WCF delegates for the position and specifications for the media bench, TV cameras (including rails), commentators' booth, statisticians' bench, timers' bench, coaches and alternates' bench, WCF seating, VIP areas. For each, determine specific requirements and propose layout to the WCF |  |  | Competition Manager; Venue Manager; Media/Hosting; Logistics Manager; |  |  | x | x |  |  |  | x | x |  |  |  |  | x | [7 empty] | Competition Manager; | Venue Manager; |  |  |  | Media/Hosting; | Logistics Manager;
Construction & Decorations | Venue Manager | Meet with sponsors and other organizations that are supposed to have stands/booths during the event, determine areas and layout. Also determine their needs (utilities, furniture etc.) to be addressed by the Logistics Manager |  |  | Logistics Manager; Marketing Manager; | [8 empty] | x |  |  | x |  | x | x | [12 empty] | Logistics Manager; |  |  | Marketing Manager;
Construction & Decorations | Venue Manager | Determine who is providing the carpet for the Field of Play and address delivery with the Logistics Manager |  |  | Logistics Manager; Marketing Manager; | [8 empty] | x |  |  | x |  | x | x | [12 empty] | Logistics Manager; |  |  | Marketing Manager;
Construction & Decorations | Venue Manager | Attend tour meetings organized with the WCF, TV, sponsors |  |  | Chairman; Competition Manager; Venue Manager; Logistics Manager; | x |  | x | x |  |  |  |  | x |  |  |  | x | x | x | x |  |  |  | Chairman; |  | Competition Manager; | Venue Manager; |  |  |  |  | Logistics Manager;
Construction & Decorations | Logistics Manager | Determine the structures and materials needed to build benches, platforms etc. |  |  | Venue Manager; Logistics Manager; |  |  |  | x |  |  |  |  | x |  |  |  |  | x | [8 empty] | Venue Manager; |  |  |  |  | Logistics Manager;
Construction & Decorations | Logistics Manager | Determine the suppliers for chairs, tables, carpet, drapes, boards, bins, coat hangers, tents, printers, computers, office supplies etc. Set timeline and supervise delivery |  |  | Chairman; Competition Manager; Venue Manager; Logistics Manager; Marketing Manager; | x |  | x | x |  |  |  |  | x |  |  | x |  | x | x |  |  |  |  | Chairman; |  | Competition Manager; | Venue Manager; |  |  |  |  | Logistics Manager; |  |  | Marketing Manager;
Construction & Decorations | Venue Manager | Determine requirements and provider for flags, banners, timing equipment, umpires equipment (measurers etc.), jumbo screens. Supervise delivery, address with Logistics Manager and Competition Manager |  |  | Chairman; Competition Manager; Venue Manager; Logistics Manager; | x |  | x | x |  |  |  |  | x |  |  |  |  | x | x | x |  |  |  | Chairman; |  | Competition Manager; | Venue Manager; |  |  |  |  | Logistics Manager;
Construction & Decorations | Venue Manager | Determine specific equipment and tools needed for various tasks: drills, ladders, vacuum cleaners, hand tools etc. Address the list with Logistics Manager and supervise delivery |  |  | Venue Manager; Logistics Manager; |  |  |  | x |  |  |  |  | x |  |  |  |  | x | x | [7 empty] | Venue Manager; |  |  |  |  | Logistics Manager;
Construction & Decorations | Logistics Manager | Survey all teams to determine if there are updates on the lists of equipment they need | [17 empty] | x | x | x | x
Construction & Decorations | Logistics Manager | Begin designating equipment to all departments/areas. Check with each team |  |  | Competition Manager; Venue Manager; Volunteers Manager; Logistics Manager; Accreditation Manager; |  |  | x | x |  | x |  |  | x |  | x |  |  |  | x | x | x |  |  |  |  | Competition Manager; | Venue Manager; |  | Volunteers Manager; |  |  | Logistics Manager; |  | Accreditation Manager;
Construction & Decorations | Logistics Manager | Set up lounges - arrange furniture |  |  | Competition Manager; Venue Manager; Volunteers Manager; |  |  | x | x |  | x | [8 empty] | x | x | x |  |  |  |  | Competition Manager; | Venue Manager; |  | Volunteers Manager;
Construction & Decorations | Volunteers Manager | Volunteer team needs to be available for the set up tasks the week before the competition |  |  | Competition Manager; Venue Manager; Volunteers Manager; Logistics Manager; |  |  | x | x |  | x |  |  | x | [7 empty] | x |  |  |  |  | Competition Manager; | Venue Manager; |  | Volunteers Manager; |  |  | Logistics Manager;
Construction & Decorations | Logistics Manager | Transportation plan for equipment and supplies for set-up/tear-down |  |  | Venue Manager; Logistics Manager; |  |  |  | x |  |  |  |  | x | [6 empty] | x | x |  | x |  |  |  | Venue Manager; |  |  |  |  | Logistics Manager;
Construction & Decorations | Logistics Manager | Check for power requirements and install additional outlets if needed |  |  | Logistics Manager; | [8 empty] | x | [5 empty] | x | x | x | [10 empty] | Logistics Manager;
Construction & Decorations | Logistics Manager | Arrange food and beverages for volunteers during set-up. Also for the ice-crew |  |  | Venue Manager; Volunteers Manager; Logistics Manager; |  |  |  | x |  | x |  |  | x | [7 empty] | x | x |  |  |  |  | Venue Manager; |  | Volunteers Manager; |  |  | Logistics Manager;
Construction & Decorations | Logistics Manager | Arrange enough water, tissues and waste baskets at ice level and in the locker rooms area |  |  | Logistics Manager; | [8 empty] | x | [6 empty] | x | x | x | [9 empty] | Logistics Manager;
Construction & Decorations | Logistics Manager | Arrange podium, discuss special needs for ceremonies |  |  | Competition Manager; Logistics Manager; PR Manager; |  |  | x | [5 empty] | x | x | [5 empty] | x | x | x |  |  |  | Competition Manager; | [5 empty] | Logistics Manager; | PR Manager;
Construction & Decorations | Logistics Manager | Develop a critical path plan for set up and tear down to ensure everything will run smooth |  |  | Venue Manager; Volunteers Manager; Logistics Manager; |  |  |  | x |  | x |  |  | x | [6 empty] | x | x |  | x |  |  |  | Venue Manager; |  | Volunteers Manager; |  |  | Logistics Manager;
Signage | Venue Manager | Determine signage requirements with WCF and teams/committees |  |  | Competition Manager; Venue Manager; Volunteers Manager; Media/Hosting; PR Manager; Accreditation Manager; Marketing Manager; |  |  | x | x |  | x |  | x |  | x | x | x |  |  | x | x | [5 empty] | Competition Manager; | Venue Manager; |  | Volunteers Manager; |  | Media/Hosting; |  | PR Manager; | Accreditation Manager; | Marketing Manager;
Signage | Venue Manager | Discuss sponsor signage with Marketing Manager |  |  | Venue Manager; Marketing Manager; |  |  |  | x | [7 empty] | x |  |  | x | x | [6 empty] | Venue Manager; | [7 empty] | Marketing Manager;
Signage | Venue Manager | Coordinate arrival and production of signage and install it at the arena |  |  | Competition Manager; Venue Manager; Logistics Manager; Marketing Manager; |  |  | x | x |  |  |  |  | x |  |  | x |  |  |  | x | x |  |  |  |  | Competition Manager; | Venue Manager; |  |  |  |  | Logistics Manager; |  |  | Marketing Manager;
Officials, timing, stats | Competition Manager | Discuss with the WCF the number and requirements for officials, statisticians and timers that need to be provided by the Organizing Committee |  |  | Chairman; Competition Manager; Volunteers Manager; | x |  | x |  |  | x | [7 empty] | x | x |  |  |  |  | Chairman; |  | Competition Manager; |  |  | Volunteers Manager;
Officials, timing, stats | Competition Manager | Arrange with Volunteers Manager to recruit appropriate persons for the requested jobs (officials, assistants, statisticians, timers). If possible, have husband and wife working in same areas and same shifts, makes it easier for their own transportation to and from the venue |  |  | Competition Manager; Volunteers Manager; |  |  | x |  |  | x | [7 empty] | x | x | [6 empty] | Competition Manager; |  |  | Volunteers Manager;
Officials, timing, stats | Competition Manager | Discuss schedule of the training sessions for the staff (timers, statisticians etc.) with the TD. Set details with Volunteers Manager. Make sure everything is set up and working for trainings. |  |  | Competition Manager; Volunteers Manager; Logistics Manager; |  |  | x |  |  | x |  |  | x | [6 empty] | x | x |  |  |  |  | Competition Manager; |  |  | Volunteers Manager; |  |  | Logistics Manager;
Officials, timing, stats | Competition Manager | Ensure all operations (ice assistants, timers, statisticians) are working smooth and address any problem with the Volunteers Manager |  |  | Competition Manager; Volunteers Manager; |  |  | x |  |  | x | [11 empty] | x |  |  |  | Competition Manager; |  |  | Volunteers Manager;
Officials, timing, stats | Competition Manager | Secure the area for officials, timers and statisticians. It must be lockable, keys should be provided. It should be equipped with enough power sockets and all the needed equipment (printer, papers, clipboards etc.) |  |  | Competition Manager; Logistics Manager; |  |  | x | [5 empty] | x | [6 empty] | x | x | x |  |  |  | Competition Manager; | [5 empty] | Logistics Manager;
Officials, timing, stats | Competition Manager | Determine who is providing timing for the event. Supervise delivery of the equipment and proper installation |  |  | Competition Manager; Venue Manager; Logistics Manager; |  |  | x | x |  |  |  |  | x | [5 empty] | x | x | x |  |  |  |  | Competition Manager; | Venue Manager; |  |  |  |  | Logistics Manager;
Officials, timing, stats | Competition Manager | Check with TD and with Chief Umpire for specific requirements and address them |  |  | Competition Manager; Logistics Manager; |  |  | x | [5 empty] | x | [6 empty] | x | x |  |  |  |  | Competition Manager; | [5 empty] | Logistics Manager;
Officials, timing, stats | Competition Manager | Ensure all measuring devices are supplied to the officials - 2 measurers, one biter, two LSD measurers with batteries, triangle for line biters |  |  | Competition Manager; Logistics Manager; |  |  | x | [5 empty] | x | [6 empty] | x | x |  |  |  |  | Competition Manager; | [5 empty] | Logistics Manager;
Officials, timing, stats | Competition Manager | Confirm equipment for officials and volunteers - who is the provider, models, measures, numbers, etc. Track delivery |  |  | Competition Manager; Logistics Manager; |  |  | x | [5 empty] | x | [5 empty] | x | x | x |  |  |  |  | Competition Manager; | [5 empty] | Logistics Manager;
Officials, timing, stats | Logistics Manager | Determine requirements for office supplies - binders, clipboards, pens, printers etc. |  |  | Competition Manager; Logistics Manager; |  |  | x | [5 empty] | x | [6 empty] | x | x |  |  |  |  | Competition Manager; | [5 empty] | Logistics Manager;
Officials, timing, stats | Competition Manager | Discuss with WCF TD and determine the need for radios and communication. Determine who is providing them and supervise delivery |  |  | Competition Manager; Logistics Manager; |  |  | x | [5 empty] | x | [6 empty] | x | x |  |  |  |  | Competition Manager; | [5 empty] | Logistics Manager;
Officials, timing, stats | Competition Manager | Ensure officials, timers and stats have separate (quick) access to food |  |  | Competition Manager; Volunteers Manager; Logistics Manager; |  |  | x |  |  | x |  |  | x | [7 empty] | x | x |  |  |  | Competition Manager; |  |  | Volunteers Manager; |  |  | Logistics Manager;
Officials, timing, stats | Volunteers Manager | Schedule training sessions for volunteers, according to what was agreed with Competition Manager. Make sure transportation will be adjusted accordingly |  |  | Competition Manager; Transportation Coordinator; Volunteers Manager; Logistics Manager; |  |  | x |  | x | x |  |  | x | [7 empty] | x | x |  |  |  | Competition Manager; |  | Transportation Coordinator; | Volunteers Manager; |  |  | Logistics Manager;
Media/Hosting | Media/Hosting | Set up the Info Center and make sure all supplies are provided |  |  | Venue Manager; Transportation Coordinator; Volunteers Manager; Media/Hosting; Logistics Manager; |  |  |  | x | x | x |  | x | x | [5 empty] | x | x | x | [5 empty] | Venue Manager; | Transportation Coordinator; | Volunteers Manager; |  | Media/Hosting; | Logistics Manager;
Media/Hosting | Media/Hosting | Discuss transportation services for Media and spectators |  |  | Transportation Coordinator; Media/Hosting; |  |  |  |  | x |  |  | x | [6 empty] | x | x | [7 empty] | Transportation Coordinator; |  |  | Media/Hosting;
Media/Hosting | Media/Hosting | Discuss accreditations for Media and for volunteers involved with teams (ex: team drivers) and arrange tickets/accreditations |  |  | Media/Hosting; Accreditation Manager; | [7 empty] | x |  |  | x |  |  |  |  | x | x | [9 empty] | Media/Hosting; |  |  | Accreditation Manager;
Media/Hosting | Media/Hosting | Determine what lounges are required and their location |  |  | Venue Manager; Media/Hosting; Logistics Manager; |  |  |  | x |  |  |  | x | x |  |  |  |  | x | x | [7 empty] | Venue Manager; |  |  |  | Media/Hosting; | Logistics Manager;
Media/Hosting | Media/Hosting | Determine restrictions for food service and for alcohol at the arena. |  |  | Venue Manager; Media/Hosting; |  |  |  | x |  |  |  | x | [6 empty] | x | x | [6 empty] | Venue Manager; |  |  |  | Media/Hosting;
Media/Hosting | Media/Hosting | Determine the volunteer needs for each lounge |  |  | Volunteers Manager; Media/Hosting; | [5 empty] | x |  | x | [6 empty] | x | x | [8 empty] | Volunteers Manager; |  | Media/Hosting;
Media/Hosting | Media/Hosting | Determine furniture and equipment (TV?) requirements for each lounge |  |  | Venue Manager; Media/Hosting; Logistics Manager; |  |  |  | x |  |  |  | x | x | [5 empty] | x | x | [6 empty] | Venue Manager; |  |  |  | Media/Hosting; | Logistics Manager;
Media/Hosting | Media/Hosting | Determine the hours of operation for the lounges, according to draw times |  |  | Competition Manager; Venue Manager; Volunteers Manager; Media/Hosting; |  |  | x | x |  | x |  | x | [7 empty] | x | x |  |  |  |  | Competition Manager; | Venue Manager; |  | Volunteers Manager; |  | Media/Hosting;
Media/Hosting | Media/Hosting | Determine security requirements and access to each lounge |  |  | Venue Manager; Media/Hosting; |  |  |  | x |  |  |  | x | [7 empty] | x | x | [5 empty] | Venue Manager; |  |  |  | Media/Hosting;
Media/Hosting | Media/Hosting | Determine food and beverage requirements for each lounge/room, cooling capacities and solutions, ways to transport/deliver food and beverages. To be analyzed: Players Lounge, Media Lounge, Volunteer Lounge, Sponsors/VIP Lounge, Players' Dressing Rooms, Officials' Rooms, Ice Technicians Room, WCF Offices etc. |  |  | Venue Manager; Media/Hosting; Logistics Manager; |  |  |  | x |  |  |  | x | x | [6 empty] | x | x | [5 empty] | Venue Manager; |  |  |  | Media/Hosting; | Logistics Manager;
Media/Hosting | Media/Hosting | Discuss decoration and equipment for lounges/rooms with Venue Manager and Logistics Manager. Check lights, power supply etc. |  |  | Venue Manager; Media/Hosting; Logistics Manager; |  |  |  | x |  |  |  | x | x | [5 empty] | x | x | [6 empty] | Venue Manager; |  |  |  | Media/Hosting; | Logistics Manager;
Media/Hosting | Media/Hosting | Determine if vouchers will be used in any of the lounges. If so, arrange the system |  |  | Competition Manager; Venue Manager; Volunteers Manager; Media/Hosting; Logistics Manager; Accreditation Manager; |  |  | x | x |  | x |  | x | x |  | x |  |  |  | x | x | [5 empty] | Competition Manager; | Venue Manager; |  | Volunteers Manager; |  | Media/Hosting; | Logistics Manager; |  | Accreditation Manager;
Media/Hosting | Media/Hosting | Arrange for storage areas for lounges and for means of transportation |  |  | Venue Manager; Media/Hosting; Logistics Manager; |  |  |  | x |  |  |  | x | x | [6 empty] | x | x | [5 empty] | Venue Manager; |  |  |  | Media/Hosting; | Logistics Manager;
Media/Hosting | Media/Hosting | Set inventory procedures for products and lounge items. Track distribution daily |  |  | Venue Manager; Media/Hosting; Logistics Manager; |  |  |  | x |  |  |  | x | x | [6 empty] | x | x | x |  |  |  |  | Venue Manager; |  |  |  | Media/Hosting; | Logistics Manager;
Media/Hosting | Media/Hosting | Ensure appropriate cleaning is provided to the lounges. Determine schedule and monitoring system |  |  | Venue Manager; Volunteers Manager; Media/Hosting; |  |  |  | x |  | x |  | x | [7 empty] | x | x | x |  |  |  |  | Venue Manager; |  | Volunteers Manager; |  | Media/Hosting;
Media/Hosting | Media/Hosting | Check with WCF TD for requirements and passes for guests/sponsors/VIPs. Arrange sufficient food/beverages are available in the lounges |  |  | Media/Hosting; Accreditation Manager; | [7 empty] | x |  |  | x |  |  |  |  | x | x | x | [8 empty] | Media/Hosting; |  |  | Accreditation Manager;
Medical Support | Venue Manager | Secure an area for the medical room |  |  | Venue Manager; |  |  |  | x | [9 empty] | x | x | [7 empty] | Venue Manager;
Medical Support | Venue Manager | Make sure certified professionals are available to provide medical assistance. This can be done either by sub-contracting (sponsorship?) or by certified volunteers |  |  | Competition Manager; Venue Manager; Marketing Manager; |  |  | x | x | [7 empty] | x |  |  | x | x | [5 empty] | Competition Manager; | Venue Manager; | [7 empty] | Marketing Manager;
Medical Support | Venue Manager | Determine working hours for medical room and staff. Ensure emergency contacts and medical staff (general practitioner, surgeon, orthopedist, dentist, ophthalmologist) are available after business hours. Pass the numbers to Media/Hosting and Info Center |  |  | Competition Manager; Venue Manager; Media/Hosting; |  |  | x | x |  |  |  | x | [7 empty] | x | x |  |  |  |  | Competition Manager; | Venue Manager; |  |  |  | Media/Hosting;
Medical Support | Logistics Manager | Determine supplies for the medical room and provide them |  |  | Logistics Manager; | [8 empty] | x | [6 empty] | x | x | x | [9 empty] | Logistics Manager;
Medical Support | Competition Manager | Discuss doping control requirements with WCF. Arrange doping control room. Make sure volunteers are available as chaperones |  |  | Competition Manager; Volunteers Manager; |  |  | x |  |  | x | [8 empty] | x | x | x | x |  |  |  | Competition Manager; |  |  | Volunteers Manager;
Info Centers | Media/Hosting | Determine locations of Info Centers - arena, hotels, airport? |  |  | Competition Manager; Venue Manager; Media/Hosting; |  |  | x | x |  |  |  | x | [5 empty] | x | x | [6 empty] | Competition Manager; | Venue Manager; |  |  |  | Media/Hosting;
Info Centers | Media/Hosting | Arrange for communication services (mobiles, radios etc). Arrange for furniture, equipment (printer, computers), Internet to be available |  |  | Venue Manager; Media/Hosting; Logistics Manager; |  |  |  | x |  |  |  | x | x | [5 empty] | x | x | x | [5 empty] | Venue Manager; |  |  |  | Media/Hosting; | Logistics Manager;
Info Centers | Media/Hosting | Determine what kind of information will be offered. In case of flyers, brochures make sure enough quantities are provided and make a re-stocking plan |  |  | Competition Manager; Media/Hosting; Logistics Manager; |  |  | x |  |  |  |  | x | x | [6 empty] | x | x | x |  |  |  | Competition Manager; |  |  |  |  | Media/Hosting; | Logistics Manager;
Info Centers | Media/Hosting | Set up standing boards and set a procedure for updating them |  |  | Competition Manager; Media/Hosting; |  |  | x |  |  |  |  | x | [7 empty] | x | x | x |  |  |  | Competition Manager; |  |  |  |  | Media/Hosting;
Info Centers | Media/Hosting | Determine the needs for volunteers and train them |  |  | Volunteers Manager; Media/Hosting; | [5 empty] | x |  | x | [7 empty] | x | x | x | [6 empty] | Volunteers Manager; |  | Media/Hosting;
Transportation | Chairman | Discuss with WCF the responsibilities of the Organizing Committee regarding the transportation of teams/officials |  |  | Chairman; Transportation Coordinator; | x |  |  |  | x | [7 empty] | x | x | [5 empty] | Chairman; |  |  |  | Transportation Coordinator;
Transportation | Transportation Coordinator | Determine "points of arrival" and communicate them on the website |  |  | Transportation Coordinator; |  |  |  |  | x | [8 empty] | x | [9 empty] | Transportation Coordinator;
Transportation | Transportation Coordinator | Determine needs for transportation - airport/railway station transfer - in terms of vehicles and drivers. Discuss how to solve them (sponsor?) |  |  | Chairman; Competition Manager; Transportation Coordinator; Volunteers Manager; Logistics Manager; | x |  | x |  | x | x |  |  | x |  |  |  | x | x | x |  |  |  |  | Chairman; |  | Competition Manager; |  | Transportation Coordinator; | Volunteers Manager; |  |  | Logistics Manager;
Transportation | Transportation Coordinator | Determine types of transportation for different accreditations and make a schedule/plan for each day, according to the number of guests, their accommodation and the draw |  |  | Chairman; Competition Manager; Transportation Coordinator; Volunteers Manager; Logistics Manager; | x |  | x |  | x | x |  |  | x | [5 empty] | x | x |  |  |  | Chairman; |  | Competition Manager; |  | Transportation Coordinator; | Volunteers Manager; |  |  | Logistics Manager;
Transportation | Transportation Coordinator | Arrange special transportation for VIP's and key officials. Special cars and drivers. Refer to the contract with WCF. Make sure you set a staffing schedule for the drivers/volunteers such way it can cover 24/7 requests. Set and communicate procedures of contact, including for special situations |  |  | Chairman; Competition Manager; Transportation Coordinator; Volunteers Manager; Logistics Manager; | x |  | x |  | x | x |  |  | x | [5 empty] | x | x |  |  |  | Chairman; |  | Competition Manager; |  | Transportation Coordinator; | Volunteers Manager; |  |  | Logistics Manager;
Transportation | Transportation Coordinator | Determine transportation to/from arena for Media and spectators (buses?) |  |  | Chairman; Competition Manager; Transportation Coordinator; | x |  | x |  | x | [9 empty] | x | x |  |  |  | Chairman; |  | Competition Manager; |  | Transportation Coordinator;
Transportation | Transportation Coordinator | Arrange meetings with all drivers. Discuss dress codes, accreditation, parking, fuelling, emergency procedures etc. Discuss procedures for picking up and dropping off teams. |  |  | Chairman; Competition Manager; Transportation Coordinator; | x |  | x |  | x | [10 empty] | x | x |  |  | Chairman; |  | Competition Manager; |  | Transportation Coordinator;
Transportation | Transportation Coordinator | Check with all the teams/departments for specific needs in terms of transportation and vehicle requirements |  |  | Chairman; Competition Manager; Venue Manager; Transportation Coordinator; Volunteers Manager; Media/Hosting; Logistics Manager; | x |  | x | x | x | x |  | x | x |  |  |  |  | x | x | x |  |  |  | Chairman; |  | Competition Manager; | Venue Manager; | Transportation Coordinator; | Volunteers Manager; |  | Media/Hosting; | Logistics Manager;
Transportation | Transportation Coordinator | Arrange a dispatch/transportation center and contact persons. Carefully set the schedule (days and hours) of operation and communicate them to Media/Hosting |  |  | Chairman; Competition Manager; Transportation Coordinator; Media/Hosting; | x |  | x |  | x |  |  | x | [6 empty] | x | x |  |  |  | Chairman; |  | Competition Manager; |  | Transportation Coordinator; |  |  | Media/Hosting;
Transportation | Transportation Coordinator | Arrange for fueling, maintenance and cleaning of the vehicles. Set procedures, including for payments and reimbursement and communicate them to all the drivers |  |  | Chairman; Financial Manager; Transportation Coordinator; | x | x |  |  | x | [8 empty] | x | x |  |  |  |  | Chairman; | Financial Manager; |  |  | Transportation Coordinator;
Transportation | Transportation Coordinator | Determine needs for dispatch center (equipment, office supplies etc). Communicate them to Logistics Manager. Pay extra attention to properly sizing the communication equipment (including chargers), also for the drivers |  |  | Transportation Coordinator; Logistics Manager; |  |  |  |  | x |  |  |  | x | [5 empty] | x | x | [7 empty] | Transportation Coordinator; |  |  |  | Logistics Manager;
Transportation | Transportation Coordinator | Determine parking areas at the arena, hotels, ceremonies etc. for all event vehicles. Arrange for parking passes, if needed. Determine overnight parking places |  |  | Venue Manager; Transportation Coordinator; Media/Hosting; |  |  |  | x | x |  |  | x | [6 empty] | x | x | [6 empty] | Venue Manager; | Transportation Coordinator; |  |  | Media/Hosting;
Transportation | Transportation Coordinator | Set rules and procedures for handling the transportation requests (through dispatch center?). Communicate numbers/contacts to Media/Hosting (to be included in guides and maybe accreditations too). Foresee/analyze special situations and needs and find solutions |  |  | Transportation Coordinator; Media/Hosting; |  |  |  |  | x |  |  | x | [7 empty] | x | x | [6 empty] | Transportation Coordinator; |  |  | Media/Hosting;
Transportation | Transportation Coordinator | Take care of the signage for the vehicles |  |  | Transportation Coordinator; Logistics Manager; |  |  |  |  | x |  |  |  | x | [6 empty] | x | x | [6 empty] | Transportation Coordinator; |  |  |  | Logistics Manager;
Competition | Competition Manager | Determine requirements for the Team Meeting - equipment, catering, program etc. |  |  | Competition Manager; Logistics Manager; |  |  | x | [5 empty] | x | [6 empty] | x | x |  |  |  |  | Competition Manager; | [5 empty] | Logistics Manager;
Competition | Competition Manager | Communicate with the TD and supply information for the Competitor's Guide |  |  | Competition Manager; |  |  | x | [10 empty] | x | x | [6 empty] | Competition Manager;
Accreditations | Accreditation Manager | In case accreditations include photos to be taken, make sure enough devices and volunteers are available to handle the flow during the days before the competition. Additional accreditation offices may be useful to have at the hotels/airport for a limited time (1 day). Relate to Logistics Manager and Volunteers Manager to provide all needed equipment and people |  |  | Competition Manager; Volunteers Manager; Logistics Manager; Accreditation Manager; |  |  | x |  |  | x |  |  | x |  | x |  |  |  | x | x | x |  |  |  |  | Competition Manager; |  |  | Volunteers Manager; |  |  | Logistics Manager; |  | Accreditation Manager;
Transportation | Transportation Coordinator | Keep a schedule of arrival and departure times for teams, officials, special guests. Determine number of persons in each case, as sometimes spouses may be included. Arrange for transfers accordingly. Consider luggage capacity and find solutions |  |  | Competition Manager; Transportation Coordinator; |  |  | x |  | x | [10 empty] | x | x | x | x |  |  | Competition Manager; |  | Transportation Coordinator;
Transportation | Transportation Coordinator | Check for papers and insurances on all vehicles and drivers |  |  | Transportation Coordinator; |  |  |  |  | x | [10 empty] | x | x | [6 empty] | Transportation Coordinator;
Transportation | Transportation Coordinator | Set schedule and shifts for the drivers. Keep their contact list updated |  |  | Transportation Coordinator; Volunteers Manager; |  |  |  |  | x | x | [9 empty] | x | x | x | x |  |  |  |  | Transportation Coordinator; | Volunteers Manager;
Volunteers | Volunteers Manager | Keep a master sheet with all needed volunteers each day, role, number of hours, working interval, transportation etc. Discuss it during periodic meetings (daily during the competition). If possible, obtain the previous year's volunteers structure and requirements (ask Chairman or TD to assist) |  |  | Chairman; Volunteers Manager; | x |  |  |  |  | x | [8 empty] | x | x | x | x |  | Chairman; |  |  |  |  | Volunteers Manager;
Volunteers | Volunteers Manager | Set up volunteers enrollment procedures - application form (online?), interview, job descriptions, volunteers manual/policies, Code of Conduct |  |  | Volunteers Manager; | [5 empty] | x | [7 empty] | x | x | [9 empty] | Volunteers Manager;
Volunteers | Volunteers Manager | Determine special requirements and needs for volunteers traveling from abroad. Design packages (accommodation, food, transfer etc) |  |  | Chairman; Financial Manager; Competition Manager; Volunteers Manager; Accreditation Manager; | x | x | x |  |  | x |  |  |  |  | x |  | x | x | x |  |  |  |  | Chairman; | Financial Manager; | Competition Manager; |  |  | Volunteers Manager; |  |  |  |  | Accreditation Manager;
Volunteers | Volunteers Manager | Determine the number of volunteers needed in each area |  |  | Chairman; Financial Manager; Competition Manager; Venue Manager; Transportation Coordinator; Volunteers Manager; Accommodation Manager; Media/Hosting; Logistics Manager; PR Manager; Accreditation Manager; Marketing Manager; | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x |  |  |  |  | Chairman; | Financial Manager; | Competition Manager; | Venue Manager; | Transportation Coordinator; | Volunteers Manager; | Accommodation Manager; | Media/Hosting; | Logistics Manager; | PR Manager; | Accreditation Manager; | Marketing Manager;
Ceremonies | PR Manager | Determine what functions will take place and the place to organize them - handle the booking/contracting/menus if necessary |  |  | Chairman; Financial Manager; Competition Manager; Venue Manager; Volunteers Manager; PR Manager; | x | x | x | x |  | x |  |  |  | x |  |  | x | x | x |  |  |  |  | Chairman; | Financial Manager; | Competition Manager; | Venue Manager; |  | Volunteers Manager; |  |  |  | PR Manager;
Volunteers | Volunteers Manager | Set up a volunteers newsletter system or information board to keep all volunteers updated |  |  | Competition Manager; Venue Manager; Volunteers Manager; |  |  | x | x |  | x | [9 empty] | x | x | x |  |  |  | Competition Manager; | Venue Manager; |  | Volunteers Manager;
Volunteers | Volunteers Manager | Discuss and plan ways to acknowledge, appreciate and thank volunteers for their efforts - special moment during ceremonies or special functions, meeting with the teams (autographs) etc. Determine if volunteers get free entry at banquets (Closing Banquet?) |  |  | Chairman; Competition Manager; Volunteers Manager; PR Manager; | x |  | x |  |  | x |  |  |  | x | [5 empty] | x | x | x | x | Chairman; |  | Competition Manager; |  |  | Volunteers Manager; |  |  |  | PR Manager;
Ceremonies | PR Manager | Set meetings to determine the requirements, location and structure of Opening & Closing Ceremonies and Opening & Closing Banquets |  |  | Chairman; Competition Manager; Venue Manager; Volunteers Manager; Media/Hosting; PR Manager; | x |  | x | x |  | x |  | x |  | x |  |  |  |  | x | x |  |  |  | Chairman; |  | Competition Manager; | Venue Manager; |  | Volunteers Manager; |  | Media/Hosting; |  | PR Manager;
Ceremonies | PR Manager | Discuss the menu and beverages for the Banquets, based on the budget |  |  | Financial Manager; PR Manager; |  | x | [7 empty] | x | [5 empty] | x |  |  |  |  | Financial Manager; | [7 empty] | PR Manager;
Ceremonies | PR Manager | Design the floor plan - determine tables and capacity, their positions, podium/stage for the speeches etc. |  |  | PR Manager; | [9 empty] | x | [5 empty] | x | [12 empty] | PR Manager;
Ceremonies | PR Manager | Make sure all equipment is provided and working (audio system, lights etc.) |  |  | Logistics Manager; PR Manager; | [8 empty] | x | x | [5 empty] | x | x | [10 empty] | Logistics Manager; | PR Manager;
Ceremonies | PR Manager | Arrange for a MC/DJ for the functions and discuss with him schedule, structure, lines of the speech/announcements etc. Check with the WCF TD if the MC is provided by the WCF |  |  | Competition Manager; Volunteers Manager; PR Manager; |  |  | x |  |  | x |  |  |  | x | [5 empty] | x | x |  |  |  |  | Competition Manager; |  |  | Volunteers Manager; |  |  |  | PR Manager;
Ceremonies | Competition Manager | Discuss how the tickets for special functions will be sold/offered - prices, number, printing, distribution, selling points etc. |  |  | Financial Manager; Competition Manager; Volunteers Manager; PR Manager; Accreditation Manager; |  | x | x |  |  | x |  |  |  | x | x |  |  |  |  | x | x |  |  |  | Financial Manager; | Competition Manager; |  |  | Volunteers Manager; |  |  |  | PR Manager; | Accreditation Manager;
Ceremonies | PR Manager | Determine decorations and set up needed for the special functions. Plan and supervise execution |  |  | Competition Manager; Venue Manager; Volunteers Manager; Logistics Manager; PR Manager; |  |  | x | x |  | x |  |  | x | x | [5 empty] | x | x | x |  |  |  | Competition Manager; | Venue Manager; |  | Volunteers Manager; |  |  | Logistics Manager; | PR Manager;
Ceremonies | PR Manager | Confirm schedule and structure of the special functions with the WCF TD. Go through all the scripts/steps and plan rehearsals |  |  | Competition Manager; Venue Manager; Volunteers Manager; Logistics Manager; PR Manager; |  |  | x | x |  | x |  |  | x | x | [6 empty] | x | x |  |  |  | Competition Manager; | Venue Manager; |  | Volunteers Manager; |  |  | Logistics Manager; | PR Manager;
Ceremonies | PR Manager | Since pipers are part of the Scottish culture and curling tradition, arranging for some pipers to be part of the marching-in would be nice. If that is not possible, plan something similar - check with TD before making the decision |  |  | Competition Manager; PR Manager; |  |  | x | [6 empty] | x | [5 empty] | x | x |  |  |  |  | Competition Manager; | [6 empty] | PR Manager;
Ceremonies | PR Manager | Confirm with Chairman, Competition Manager and TD the special guests attending the special functions. Determine order of speeches and who is introduced when, obtain speeches scripts and arrange for translation. |  |  | Chairman; Competition Manager; PR Manager; | x |  | x | [6 empty] | x | [6 empty] | x | x |  | Chairman; |  | Competition Manager; | [6 empty] | PR Manager;
Ceremonies | PR Manager | Hire translators for the special functions |  |  | Volunteers Manager; PR Manager; | [5 empty] | x |  |  |  | x | [6 empty] | x | x | [6 empty] | Volunteers Manager; |  |  |  | PR Manager;
Ceremonies | PR Manager | Determine number of tickets/invitations to be offered to sponsors. Arrange for distribution |  |  | Competition Manager; Volunteers Manager; Media/Hosting; Logistics Manager; PR Manager; Accreditation Manager; |  |  | x |  |  | x |  | x | x | x | x |  |  |  |  | x | x |  |  |  |  | Competition Manager; |  |  | Volunteers Manager; |  | Media/Hosting; | Logistics Manager; | PR Manager; | Accreditation Manager;
Ceremonies | PR Manager | Determine number of invitations/complementary tickets that are going to be offered (teams, WCF, VIP, others). Arrange for distribution |  |  | Competition Manager; Volunteers Manager; Media/Hosting; Logistics Manager; PR Manager; Accreditation Manager; |  |  | x |  |  | x |  | x | x | x | x |  |  |  |  | x | x |  |  |  |  | Competition Manager; |  |  | Volunteers Manager; |  | Media/Hosting; | Logistics Manager; | PR Manager; | Accreditation Manager;
Ceremonies | PR Manager | Determine access policies for the special functions. Make sure updated lists with tables and names will be available |  |  | Volunteers Manager; PR Manager; | [5 empty] | x |  |  |  | x | [6 empty] | x | x | [6 empty] | Volunteers Manager; |  |  |  | PR Manager;
Ceremonies | PR Manager | Coordinate the process of inviting VIPs, dignitaries, past champions (?) |  |  | Competition Manager; PR Manager; |  |  | x | [6 empty] | x | [5 empty] | x | x |  |  |  |  | Competition Manager; | [6 empty] | PR Manager;
Ceremonies | PR Manager | Determine awards (plaques, trophies, certificates etc.) that are going to be offered during the special functions. Discuss them with the TD before making a decision. Coordinate the ordering process and the awarding process. Double-check all the names to avoid problems! |  |  | Chairman; Competition Manager; PR Manager; | x |  | x | [6 empty] | x | [5 empty] | x | x |  |  | Chairman; |  | Competition Manager; | [6 empty] | PR Manager;
Ceremonies | PR Manager | Plan the activities for the Patch/Lounges. Discuss if there will be concerts/bands/DJ/parties organized and plan accordingly all the details. |  |  | Chairman; Competition Manager; Venue Manager; PR Manager; | x |  | x | x | [5 empty] | x | [5 empty] | x | x |  |  | Chairman; |  | Competition Manager; | Venue Manager; | [5 empty] | PR Manager;
Ceremonies | PR Manager | Ensure the schedule for all the functions is communicated properly. Relate with the TD (to be included in the Competitor's Guide and Team Meeting) |  |  | Competition Manager; PR Manager; |  |  | x | [6 empty] | x |  |  |  |  | x | x | [5 empty] | Competition Manager; | [6 empty] | PR Manager;
Ceremonies | PR Manager | Arrange for the flag display (participating teams, WCF banner etc). Arrange for flags and country name plaques for the marching in. Arrange schedules for honoring teams during the event - make sure current anthems are available. Check with TD all these aspects |  |  | Competition Manager; Venue Manager; Logistics Manager; PR Manager; |  |  | x | x |  |  |  |  | x | x | [5 empty] | x | x | x |  |  |  | Competition Manager; | Venue Manager; |  |  |  |  | Logistics Manager; | PR Manager;
Ceremonies | PR Manager | Discuss with Chairman and Competition Manager if there is going to be a Sponsors' Reception. If so, plan accordingly (location, menu, floor plan, guests list, invitations production and distribution etc.) |  |  | Chairman; Financial Manager; Competition Manager; PR Manager; | x | x | x | [6 empty] | x |  |  |  |  | x | x | x | x |  | Chairman; | Financial Manager; | Competition Manager; | [6 empty] | PR Manager;
Enhaced experience | Competition Manager | Arrange meetings to discuss plans for enhancing the experience spectators will have. Refer to the "Jazz-up" document and plan accordingly |  |  | Chairman; Financial Manager; Competition Manager; Venue Manager; PR Manager; Marketing Manager; | x | x | x | x | [5 empty] | x |  | x | x | x | x |  |  |  |  | Chairman; | Financial Manager; | Competition Manager; | Venue Manager; | [5 empty] | PR Manager; |  | Marketing Manager;
Enhaced experience | Marketing Manager | Analyze the opportunity of implementing a "school program" - invite local schools, organize a workshops/presentations about curling etc. Coordinate the program |  |  | Chairman; Financial Manager; Competition Manager; PR Manager; Accreditation Manager; Marketing Manager; | x | x | x | [6 empty] | x | x | x | x | x | x |  |  |  |  | Chairman; | Financial Manager; | Competition Manager; | [6 empty] | PR Manager; | Accreditation Manager; | Marketing Manager;
Enhaced experience | Marketing Manager | Discuss with TD and sponsors about the plans to offer a richer experience - screens displaying matches and interviews placed in the lounges and public areas, shuffleboard and other curling-based games made available etc. Coordinate the program |  |  | Chairman; Financial Manager; Competition Manager; PR Manager; Marketing Manager; | x | x | x | [6 empty] | x |  | x |  | x | x | x |  |  |  | Chairman; | Financial Manager; | Competition Manager; | [6 empty] | PR Manager; |  | Marketing Manager;
Ceremonies | Venue Manager | Plan an area for Ceremonies Office and secure storage of all medals/trophies/awards |  |  | Venue Manager; PR Manager; |  |  |  | x | [5 empty] | x |  |  |  |  | x | x | [6 empty] | Venue Manager; | [5 empty] | PR Manager;
Ceremonies | PR Manager | Discuss ideas for "between ends" activities with TD and CU. Especially at final stages, where less (one?) games are played simultaneous and breaks may be longer, even music can be considered to be played |  |  | Competition Manager; PR Manager; |  |  | x | [6 empty] | x | [6 empty] | x | x |  |  |  | Competition Manager; | [6 empty] | PR Manager;
Uniforms | Logistics Manager | Determine the uniforms (types, number and sizes) that are going to be offered to volunteers, based on the budget. Coordinate production (get layout approved) and distribution. This can become a sponsorship opportunity |  |  | Chairman; Financial Manager; Competition Manager; Volunteers Manager; Logistics Manager; Marketing Manager; | x | x | x |  |  | x |  |  | x |  |  | x | x | x | x | x |  |  |  | Chairman; | Financial Manager; | Competition Manager; |  |  | Volunteers Manager; |  |  | Logistics Manager; |  |  | Marketing Manager;
Uniforms | Logistics Manager | Supervise the shipping, distribution, collecting and shipping back of the uniforms provided by the WCF (officials, timers, stats etc.). Keep a sizing chart |  |  | Competition Manager; Logistics Manager; |  |  | x | [5 empty] | x |  |  |  | x | x | x | x | [5 empty] | Competition Manager; | [5 empty] | Logistics Manager;
Construction & Decorations | Competition Manager | Determine the decorating plans including the logo |  |  | Chairman; Financial Manager; Competition Manager; Venue Manager; Logistics Manager; PR Manager; Marketing Manager; | x | x | x | x |  |  |  |  | x | x |  | x | x | x | x |  |  |  |  | Chairman; | Financial Manager; | Competition Manager; | Venue Manager; |  |  |  |  | Logistics Manager; | PR Manager; |  | Marketing Manager;
Construction & Decorations | Logistics Manager | Coordinate production, delivery and installation of the decorations for the venue (all areas) |  |  | Financial Manager; Competition Manager; Venue Manager; Transportation Coordinator; Logistics Manager; |  | x | x | x | x |  |  |  | x |  |  |  |  | x | x | x | x |  |  |  | Financial Manager; | Competition Manager; | Venue Manager; | Transportation Coordinator; |  |  |  | Logistics Manager;
Construction & Decorations | Logistics Manager | Part of the decorations, coordinate purchase, delivery and installation of flowers. Make sure water is provided each day - address the problem with volunteers |  |  | Financial Manager; Venue Manager; Transportation Coordinator; Volunteers Manager; Logistics Manager; |  | x |  | x | x | x |  |  | x | [7 empty] | x | x |  |  | Financial Manager; |  | Venue Manager; | Transportation Coordinator; | Volunteers Manager; |  |  | Logistics Manager;
Communications | Logistics Manager | Order high-speed Internet connections with separate access for: staff, media, live feeds, officials, spectators. Check for minimum requirements |  |  | Financial Manager; Venue Manager; Media/Hosting; Logistics Manager; |  | x |  | x |  |  |  | x | x |  |  |  |  | x | x | x |  |  |  |  | Financial Manager; |  | Venue Manager; |  |  |  | Media/Hosting; | Logistics Manager;
Communications | Logistics Manager | Make sure proper and enough technical support is provided throughout the event - contractor or qualified volunteers |  |  | Chairman; Financial Manager; Competition Manager; Volunteers Manager; Logistics Manager; | x | x | x |  |  | x |  |  | x |  |  |  |  | x | x | x | x | x |  | Chairman; | Financial Manager; | Competition Manager; |  |  | Volunteers Manager; |  |  | Logistics Manager;
Finances | Financial Manager | Determine procedures for selling and accounting (tickets, merchandising, food etc.). Investigate options for online transfers and card payments. |  |  | Chairman; Financial Manager; | x | x | [11 empty] | x | x | x | x | x |  | Chairman; | Financial Manager;
Finances | Financial Manager | Determine budgets, P&L, etc. Fill in financial reports |  |  | Chairman; Financial Manager; Competition Manager; | x | x | x | [9 empty] | x | x | x | x | x | x | x | Chairman; | Financial Manager; | Competition Manager;
Finances | Financial Manager | Coordinate fundraising activities, sponsorships, contracts |  |  | Chairman; Financial Manager; Competition Manager; Marketing Manager; | x | x | x | [8 empty] | x | x | x | x | x | x | x | x | Chairman; | Financial Manager; | Competition Manager; | [8 empty] | Marketing Manager;
Finances | Financial Manager | Part of the contract with the WCF, determine responsibilities and share of the budget for each of the partners. Analyze cash flows, discuss payments and reimbursements plan and supervise it. |  |  | Chairman; Financial Manager; Competition Manager; | x | x | x | [9 empty] | x | x | x | x | x | x | x | Chairman; | Financial Manager; | Competition Manager;
Finances | Financial Manager | Determine procedures for handling accounting - approving payments and purchases, reimburse expenses etc. |  |  | Chairman; Financial Manager; Competition Manager; Venue Manager; Transportation Coordinator; Volunteers Manager; Accommodation Manager; Media/Hosting; Logistics Manager; PR Manager; Accreditation Manager; Marketing Manager; | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [5 empty] | Chairman; | Financial Manager; | Competition Manager; | Venue Manager; | Transportation Coordinator; | Volunteers Manager; | Accommodation Manager; | Media/Hosting; | Logistics Manager; | PR Manager; | Accreditation Manager; | Marketing Manager;
Finances | Financial Manager | Coordinate all financial operations, make sure financial situations are updated and under control |  |  | Financial Manager; |  | x | [11 empty] | x | x | x | x | x | x |  | Financial Manager;
Finances | Venue Manager | Coordinate bar and restaurant activities, foresee problems and find solutions. Obtain any licenses required for selling food and beverages |  |  | Financial Manager; Venue Manager; Logistics Manager; |  | x |  | x |  |  |  |  | x | [7 empty] | x | x |  |  | Financial Manager; |  | Venue Manager; |  |  |  |  | Logistics Manager;
Finances | Financial Manager | Determine how each manager will handle inventory. Coordinate final inventory and reports |  |  | Chairman; Financial Manager; Competition Manager; Venue Manager; Transportation Coordinator; Volunteers Manager; Accommodation Manager; Media/Hosting; Logistics Manager; PR Manager; Accreditation Manager; Marketing Manager; | x | x | x | x | x | x | x | x | x | x | x | x | x | x |  |  |  | x | x | Chairman; | Financial Manager; | Competition Manager; | Venue Manager; | Transportation Coordinator; | Volunteers Manager; | Accommodation Manager; | Media/Hosting; | Logistics Manager; | PR Manager; | Accreditation Manager; | Marketing Manager;
Transportation | Transportation Coordinator | Arrange agreement with a taxi company for special requirements and spectators |  |  | Transportation Coordinator; |  |  |  |  | x | [10 empty] | x | x | x | [5 empty] | Transportation Coordinator;
Accommodation | Accommodation Manager | Determine the needs for accommodation for the following categories: teams, officials & delegates, VIPs, volunteers. Relate to the contract |  |  | Chairman; Competition Manager; Accommodation Manager; | x |  | x |  |  |  | x | [5 empty] | x | x | [5 empty] | Chairman; |  | Competition Manager; |  |  |  | Accommodation Manager;
Accommodation | Accommodation Manager | Design accommodation packages according to the numbers needed. Determine "Official Hotel". If possible, try to develop packages that include transportation and extras (curling lessons at the local club?) |  |  | Chairman; Competition Manager; Accommodation Manager; | x |  | x |  |  |  | x | [6 empty] | x | x |  |  |  |  | Chairman; |  | Competition Manager; |  |  |  | Accommodation Manager;
Accommodation | Accommodation Manager | Negotiate discounts on accommodation. Determine ways to handle the booking process. Advertise packages of accommodation through the website |  |  | Competition Manager; Accommodation Manager; Marketing Manager; |  |  | x |  |  |  | x |  |  |  |  | x |  | x | x | x | x |  |  |  |  | Competition Manager; |  |  |  | Accommodation Manager; |  |  |  |  | Marketing Manager;
Promotion and Marketing | Marketing Manager | Develop the marketing plans and promotional campaign |  |  | Chairman; Financial Manager; Competition Manager; Marketing Manager; | x | x | x | [8 empty] | x | x | x | [5 empty] | Chairman; | Financial Manager; | Competition Manager; | [8 empty] | Marketing Manager;
Promotion and Marketing | Marketing Manager | Develop stationeries and visual identity. Relate to the WCF Media & Marketing |  |  | Chairman; Financial Manager; Competition Manager; Marketing Manager; | x | x | x | [8 empty] | x | x | x | x |  |  |  |  | Chairman; | Financial Manager; | Competition Manager; | [8 empty] | Marketing Manager;
Promotion and Marketing | Marketing Manager | Attract media partners. Implement promotional and marketing campaign |  |  | Chairman; Financial Manager; Competition Manager; Marketing Manager; | x | x | x | [8 empty] | x |  | x | x | x | x |  |  | Chairman; | Financial Manager; | Competition Manager; | [8 empty] | Marketing Manager;
Promotion and Marketing | Marketing Manager | Relate with Logistics Manager to order and deliver promotional materials - flyers, banners, stickers etc. |  |  | Chairman; Financial Manager; Competition Manager; Logistics Manager; Marketing Manager; | x | x | x | [5 empty] | x |  |  | x |  | x | x | x | x |  |  | Chairman; | Financial Manager; | Competition Manager; | [5 empty] | Logistics Manager; |  |  | Marketing Manager;
Promotion and Marketing | Marketing Manager | Keep a folder with all exposure obtained (media, public displays, TV, radios etc.). |  |  | Marketing Manager; | [11 empty] | x |  | x | x | x | x | x | [12 empty] | Marketing Manager;