## Overview
Project Gate Check List
Instructions
What is a Project Gate Check List
The Project Gate Check List contains the list of items that must be completed in order for the project to complete and close off a process within the project. This information will help the project manager by showing what information is still lacking for the project to sucessfully continue.

## Definitions LvL-1
Item | Description
Pre-Initiation (Gate)
COPPAR approval | This means the project has been reviewed and approved by OA/OIT
Project Request Approval | OA/OIT has reviewed and approved the project
Product Requirements Submitted | High level requirements for the product have been collected and approved by project stakeholders
Initiation (Gate)
Scope (WBS) Complete | The WBS, representing all the deliverables for the project, has been created, reviewed and approved
Requirements Complete | Detailed product requirements have been captured, reviewed and approved by project stakeholders
Planning (Gate)
Project Schedule Complete | A project activities are created to represent the work to be performed and these activities are placed in time to show a planned start and finish date for each. CPM scheduling should be used whenever possible representing the work
Quality Activities in Schedule | A list of quality activities have been scheduled for the project
Quality Plan Complete | A complete Project Quality Plan has been established for the project
Communication Plan Complete | A Communication Plan has been established for the project
Change Management Process Complete | The process for receiving change requests, reviewing change requests and approving/denying change requests has be established and approved
Project Log Prepared | The Project Log spreadsheet has been prepared to help track and manage Risks, Action Items, Issues, Decisions, Changes and Quality Metrics
Meeting Agenda & Minute Template Copied | The Meeting Agenda and Meeting Minutes templates have been copied to the project folder ready for use
Status Report Format Copied | The project status report format has been copied to the project folder and is ready for use
Lessons Learned Documented | Lessons learned concerning the project have been documented
Monitoring & Controlling (Gate)
PM Plan Verified | ??
Sustainability Plan Verified | A Sustainability Plan has been established for the new system being developed and the correct OA/OIT personnel have reviewed the plan and agree it is appropriate
Project Log Satisfied | All Risks, Action Items, Issues, Decisions, Changes and Quality elements contained in the Project Log are satisfied and complete
Scope Verified | The project stakeholders have reviewed the deliverables for the project and agree they provide the desired result for the project
User Acceptance Testing Complete | The user community has tested the new system using pre-defined testing scripts and verify that the system performs to their desire
Customer Signoff on product or deliverable | The project sponsor agrees the product is completely delivered and signed the final document stating all deliverables have been adequately delivered
Lessons Learned Documented | Lessons learned concerning the project have been documented
Close (No Gate)
Lessons Learned Archived | Lessons learned have been archived, to be used by other project managers on future projects
Completed Closing CheckList | All items on the Closing Checklist are satisfied

## Check List LvL-1
Description | Completed | Date
Pre-Project (Gate)
COPPAR approval
Project Request Approval
Product Requirements Submitted
Initiation (Gate)
Scope (WBS) Complete
Requirements Complete
Planning (Gate)
Project Schedule Complete
Quality Activities in Schedule
Communication Plan Complete
Change Management Process Complete
Project Log Prepared
Meeting Agenda & Minute Templates Copied
Status Report format copied
Lessons Learned Documented
Monitoring & Controlling (Gate)
Project Log Satisfied
Risk Log Closed
Action Items Complete
Issues Complete
Decisions Finalized
Change Log Fulfilled
Scope Verified
User Acceptance Testing Complete
Customer Signoff on product or deliverable
Lessons Learned Documented
Close (No Gate)
Lessons Learned Archived
Completed Closing Checklist