## PMP Form (faux)
Project Management Plan (PMP)
| Project Information |  |  | Performer Information
| FOA Number: | DE-FOA-000XXXX |  | Number: | 1 | [5 empty] | 2 | [6 empty] | 3
| Project Title: | High Efficiency, Photovoltaic Model System |  | Organization: | Lead Institution | [5 empty] | Institution 2 | [6 empty] | Institution 3
|  |  |  | Point of Contact: | James Maxwell | [5 empty] | Josef Stefan | [6 empty] | Thomas Young
|  |  |  | E-mail Address: | james.maxwell@e3devices.com | [5 empty] | josef.stefan@inst2.com | [6 empty] | thomas.young@inst3.com
|  |  |  | Phone Number: | (555) 555-7743 | [5 empty] | (571) 222-2172 | [6 empty] | (112) 358-1321
Budget Period | SOPO Item Identification Number | Item Description | Tool(s) and/or Method(s) of Measurement | Item Performer | Planned
[5 empty] | Start Date | 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  |  | 2016 |  |  |  | End Date
[6 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1 | T-1 | Comprehensive Model System Design |  | 1 | 2013-10-01 | [16 empty] | 2014-06-30 | bar: 2013 Q4 to 2014 Q2
1 | ST-1.1 | Identification of necessary doping density, defect density and stoichiometry of absorber |  | 1 | 2013-10-01 | [16 empty] | 2014-06-30 | bar: 2013 Q4 to 2014 Q2
1 | ST-1.2 | Identification of capable emitter materials to compliment the chosen absorber construction (doping density, defect density, resistivity, surface passivation, depositon/growth technique, etc.) |  | 1 | 2013-10-01 | [16 empty] | 2014-06-30 | bar: 2013 Q4 to 2014 Q2
1 | ST-1.3 | Identification of absorber synthesis pathways/techniques and cell construction |  | 1 | 2014-01-01 | [16 empty] | 2014-06-30 | bar: 2014 Q1 to 2014 Q2
1 | M (T-1) | Completion of ab-initio calculations and alpha computer modeling of material systems | Report, Software Output | 1 | N/A | [16 empty] | 2014-03-30 | bar: 2014 Q1
1 | M (T-1)/ Go/No-Go | Comprehensive report of model system design with identification of cell characterizatics (doping density, defect density, interfaces, etc.) and synthesis pathway | Report | 1 | N/A | [16 empty] | 2014-09-30 | bar: 2014 Q3
1, 2 | T-2 | Cell Modeling |  | 1 & 2 | 2014-01-01 | [16 empty] | 2015-03-31 | bar: 2014 Q1 to 2015 Q1
1, 2 | ST-2.1 | Data entry and simulation for absorber characteristics. Itterations done to identify key performance characterisics (doping density, defect density, carrier lifetime, stoichiometry, etc.) | Software (Version) | 2 | 2014-04-01 | [16 empty] | 2014-12-31 | bar: 2014 Q2 to 2014 Q4
1, 2 | ST-2.2 | Develop a model for absorber and emitter interface | Software (Version) | 2 | 2014-07-01 | [16 empty] | 2014-12-31 | bar: 2014 Q3 to 2014 Q4
1, 2 | ST-2.2=3 | Develop a full cell model | Software (Version) | 2 | 2014-10-01 | [16 empty] | 2015-03-31 | bar: 2014 Q4 to 2015 Q1
1, 2 | M (T-2) | Identification of absorber which will have highest performance | Report, Software Output | 1 & 2 | N/A | [16 empty] | 2014-12-31 | bar: 2014 Q4
1, 2 | M (T-2) | Identification of cell architecture which will have highest performance | Report, Software Output | 1 & 2 | N/A | [16 empty] | 2015-03-31 | bar: 2015 Q1
2, 3 | T-3 | Material Growth and Characterization |  | 1 & 3 | 2015-04-01 | [16 empty] | 2016-03-31 | bar: 2015 Q2 to 2016 Q1
2 | ST-3.1 | Retrofit tooling for deposition/growth technique specifications needed for absorber material development | CVD Retrofit | 3 | 2015-04-01 | [16 empty] | 2015-09-30 | bar: 2015 Q2 to 2015 Q3
2 | ST-3.2 | Initial absorber growth- Doping density (XXXX), Defect Density (XXXX), carrier lifetime (XXXX), stoichiometry,etc. | CVD, SCM, XRD, SE, HRTEM, SIMS | 3 | 2015-04-01 | [16 empty] | 2015-09-30 | bar: 2015 Q2 to 2015 Q3
2 | M (ST-3.2)/ Go/No-Go | Grow/deposit absorber with carrier lifetimes >XXXX, doping density of XXXX, defect density of XXXX. Verified by NREL | Material Characterized at NREL | 3 | 2015-07-01 | [16 empty] | 2015-09-30 | bar: 2015 Q3
3 | ST-3.3 | Characterization of Interface made with absorber and emmitter of choice | SCM, XRD, SE, HRTEM, SIMS | 1 & 3 | 2015-10-01 | [16 empty] | 2016-03-31 | bar: 2015 Q4 to 2016 Q1
3 | M (ST-3.3) | Demonstrate optimized absorber XXmicron +/- X microns (Carrier lifetime XXXX, Doping Density XXXX, Defect Density XXXX, etc.) and optimized emitter XXmicron +/- X microns (sheet resistance XXXX, etc.) | Material Characterized at NREL | 1 & 3 | N/A | [16 empty] | 2016-03-31 | bar: 2016 Q1
2, 3 | T-4 | Model System Cell Synthesis and Characterization |  | 1 & 3 | 2015-04-01 | [16 empty] | 2016-09-30 | bar: 2015 Q2 to 2016 Q3
2 | ST-4.1 | Fabricate devices with 1.0 cm2 device area and at least 10% in-house certified device efficiencies. | CVD, CB, Screen Print Contact, I-V Characterization | 1 & 3 | 2015-04-01 | [16 empty] | 2015-06-30 | bar: 2015 Q2
2 | ST-4.2 | Fabricatedevices with a device area of 1.0 cm2 and an efficiency of at least 15%, in-house certified. | CVD, CB, Screen Print Contact, I-V Characterization | 1 & 3 | 2015-07-01 | [16 empty] | 2015-09-30 | bar: 2015 Q3
3 | M (T-4) | A photovoltaic cell (~1 cm2) with an NREL certified efficiency = World Record % for material system. (ASTM G173). | Device Characterization at NREL | 1 & 3 | N/A | [16 empty] | 2015-12-31 | bar: 2015 Q4
3 | ST-4.3 | Fabricate 1.0 cm2 cell > world record efficiency for material system | CVD, CB, Screen Print Contact, I-V Characterization | 1 & 3 | 2016-04-01 | [16 empty] | 2016-09-30 | bar: 2016 Q1 to 2016 Q3
3 | FM-1 | A photovoltaic cell (~1 cm2) with an NREL certified efficiency of >29% (ASTM G173). | Device Characterization at NREL | 1, 2 & 3 | N/A | [16 empty] | 2016-09-30 | bar: 2016 Q3
X | T-5, 6, 7…. | Additional Tasks- It is expected that more than 4 work tasks will be required to complete these projects. Please repeat format of above tasks until all work tasks for the proposed project have been thoroughly covered. | Examples: TRPL, SIMS, XRD, SEM, TEM, Simulation Software Version X, Report, Device, etc. | 1, 2 & 3 | N/A