## EPMO Matrix
Deliverables Matrix
Project Management Deliverables | Project Scaling
| Level One | Level Two | Level Three
PRE-INITIATION
Project Request Form **
Project Scaling Worksheet | Required | Required | Required
360 Degree Impact Assessment | Required | Required | Optional
INITIATING
Project Charter | Required | Required | Required
Project Scope | Required | Required | Optional
Requirements Document | Required | Required | Required
PLANNING
Scope Management Plan | Required | Optional | Optional
Change Management Plan | Required | Required | Required
Time Management Plan | Required | Required | Optional
Cost Management Plan | Required | Required | Optional
Quality Management Plan | Required | Required | Optional
Resource Management Plan | Required | Required | Optional
Communications Management Plan | Required | Required | Required
Risk Management Plan | Required | Required | Optional
Procurement Management Plan *** | Required | Optional | Optional
Requirements Management Plan | Required | Required | Optional
Issues Management Plan | Required | Required | Required
Document Management Plan | Required | Required | Optional
EXECUTING
Meetings (Agenda, Minutes) | Required | Required | Required
Status Reports | Required | Required | Required
Manage Deliverables (SDLC or Other)
Product Deliverables | Required | Required | Required
MONITORING & CONTROLLING
Project Log | Required | Required | Required *
Report Performance Metrics | Required | Required | Optional
CLOSING
Project Closeout CheckList | Required | Required | Optional
* For Level 3 projects a project log contains many of the project management deliverables in a single file.
** Refer to ITB-EPM006 for projects that require a Project Request Form to be approved
*** When applicable