## Project Plan
Project: | SITS Points Based Immigration Implementation
Project Manager: | Terry Madeley
Task |  | Start Date | Due Date | Date Completed | % Complete | 2012-02-13 | 2012-02-16 | 2012-02-19 | 2012-02-22 | 2012-02-25 | 2012-02-28 | 2012-03-02 | 2012-03-05 | 2012-03-08 | 2012-03-11 | 2012-03-14 | 2012-03-17 | 2012-03-20 | 2012-03-23 | 2012-03-26 | 2012-03-29 | 2012-04-01 | 2012-04-04 | 2012-04-07 | 2012-04-10 | 2012-04-13
Initiate
Task1
Task2
…
Plan
Initial SITS consultancy meeting / project meeting |  | 2012-02-13 | 2012-02-13 | 2012-02-13 | 100 | bar: 2012-02-13
Finalise project brief and project plan |  | 2012-02-13 | 2012-02-14 |  | 50 | bar: 2012-02-13
Do it
Send out course start and end date report to HoP for checking |  | 2012-02-14 | 2012-02-17 | bar: 2012-02-16 to 2012-02-19
Receive start and end date amendments back from HoPs and share with YSJ International |  | 2012-02-20 | 2012-02-24 | bar: 2012-02-19 to 2012-02-22
Develop appropriate SRF, SYP and other background records in SITS Test system |  | 2012-02-13 | 2012-03-02 | bar: 2012-02-13 to 2012-03-02
Generate full range of dummy VCR records in SITS Test |  | 2012-03-05 | 2012-03-16 | bar: 2012-03-05 to 2012-03-17
Develop SITS guides and documentation |  | 2012-03-05 | 2012-03-16 | bar: 2012-03-05 to 2012-03-17
Copy across SITS background records from Test to Live system |  | 2012-03-16 | 2012-03-16 | bar: 2012-03-17
Check it
Test Live system and refine by generating full range of dummy VCR records in SITS Live |  | 2012-03-19 | 2012-03-30 | bar: 2012-03-20 to 2012-03-29
Adjust SITS guides and documentation as required |  | 2012-03-26 | 2012-03-30 | bar: 2012-03-26 to 2012-03-29
Prior to going live, delete all existing VCRs from Live system |  | 2012-03-30 | 2012-03-30 | bar: 2012-03-29
Release
Generate live VCRs, export xml file and upload to UKBS SMS |  | 2012-04-02 | 2012-04-06 | bar: 2012-04-01 to 2012-04-04
Download and import CAS Status data from UKBA SMS |  | 2012-04-02 | 2012-04-06 | bar: 2012-04-01 to 2012-04-04
Close
Finalise SITS guides and documentation |  | 2012-04-09 | 2012-04-13 | bar: 2012-04-07 to 2012-04-13
Document lessons learnt |  | 2012-04-09 | 2012-04-13 | bar: 2012-04-07 to 2012-04-13
Scope out any ongoing Phase 2 actions |  | 2012-04-09 | 2012-04-13 | bar: 2012-04-07 to 2012-04-13
ON SCHEDULE
AT RISK
DELAYED
COMPLETE

## Example
Project: | Name of Project
Project Manager: | Name of PM |  |  |  | Click here to see how to create a plan | [6 empty] | Click here to see how to maintain a plan
Task | Start Date | Due Date | Date Completed | % Complete | 2009-02-18 | 2009-02-19 | 2009-02-20 | 2009-02-23 | 2009-02-24 | 2009-02-25 | 2009-02-26 | 2009-02-27 | 2009-03-02 | 2009-03-03 | 2009-03-04 | 2009-03-05 | 2009-03-06 | 2009-03-08 | 2009-03-09 | 2009-03-10 | 2009-03-11 | 2009-03-12 | 2009-03-13 | 2009-03-16 | 2009-03-17
Initiate
Task1 | 2009-02-18 | 2009-02-18 | 2009-02-18 | 100 | bar: 2009-02-18
Plan
Task1 | 2009-02-19 | 2009-02-20 | 2009-02-20 | 100 | bar: 2009-02-19 to 2009-02-20
Task2 | 2009-02-19 | 2009-02-20 | 2009-02-20 | 100 | bar: 2009-02-19 to 2009-02-20
Do it
Task1 | 2009-02-23 | 2009-02-25 |  | 30 | bar: 2009-02-23 to 2009-02-25
Task2 | 2009-02-25 | 2009-03-02 | bar: 2009-02-25 to 2009-03-02
Task 3 | 2009-03-03 | 2009-03-06 | bar: 2009-03-03 to 2009-03-06
Check it
Task1 | 2009-03-08 | 2009-03-09 | bar: 2009-03-08 to 2009-03-09
Release
Task1 | 2009-03-10 | 2009-03-12 | bar: 2009-03-10 to 2009-03-12
Close
Task1 | 2009-03-13 | 2009-03-17 | bar: 2009-03-13 to 2009-03-17
ON SCHEDULE
AT RISK
DELAYED
COMPLETE
Note on F2: Creating a Plan - enter the name of the project - enter the name of the project manager - enter the date range in the top line (days or week ending depending on length of project) For each task: - enter the name of the task - enter the start date and the due date - highlight the squares on the grid between the two dates - colour light green (to represent 'on schedule')
Note on M2: Maintaining a Plan Ongoing Tasks - regularly update the % complete column to show progress - highlight the squares orange if the task may become delayed ('at risk') - highlight the squares red if the task becomes delayed ('delayed') Completed Tasks - enter the date of completion - update % complete to 100% - highlight the squares blue (to represent 'complete')