## Sheet1
2013 NPNSG Schedule
2012-03-29 |  |  | Contract Due
2012-03-07 |  |  | Contracts Written (March 1 through December 31)
2012-03-04 |  |  | Grant description to Brian to Start Council Approval Process
2012-03-01 |  |  | Grants Awarded
| 2012-02-28 |  | Committee 2nd Mtg (if necessary)
| 2012-02-18 |  | Committee 1st Mtg
| 2012-02-01 |  | Grants Emailed to Committee (two weeks to score grants)
2012-01-31 |  |  | Applications Due (2 pm)
2012-01-24 |  |  | Due Date Reminder
2012-01-10 |  |  | Due Date Reminder
|  | 2012-12-10 | Announce New Committee Members & set up individual orientation
2012-12-03 |  |  | 3rd Announcement Reminder
|  | 2012-11-26 | Committee Applications Due/Applications out to readers
|  | 2012-11-01 | Select readers
|  | 2012-10-23 | Announce Committee Openings/Recruit Members
2012-10-23 |  |  | Workshop
2012-10-09 |  |  | 2nd Announcement/Reminder
2012-09-13 |  |  | Announce Grants Available (emails, letters, and posters, metro list?)/sign -up for Workshop

## Sheet2
Staff out to all NAs to present during Fall
Babs outreach