## PMP Form (faux)
Project Management Plan (PMP)
| Project Information |  |  | Performer Information
| FOA Number: | DE-FOA-000XXXX |  | Number: | 1 | [5 empty] | 2 | [6 empty] | 3
| Project Title: | High Efficiency, Solution-Processable Organic Photovoltaics Based on Earth Abundant Charge-Recombination Interlayers |  | Organization: | Lead Institution | [5 empty] | Institution 2 | [6 empty] | Institution 3
|  |  |  | Point of Contact: | James Maxwell | [5 empty] | Josef Stefan | [6 empty] | Thomas Young
|  |  |  | E-mail Address: | james.maxwell@e3devices.com | [5 empty] | josef.stefan@inst2.com | [6 empty] | thomas.young@inst3.com
|  |  |  | Phone Number: | (555) 555-7743 | [5 empty] | (571) 222-2172 | [6 empty] | (112) 358-1321
Budget Period | SOPO Item Identification Number | Item Description | Tool(s) and/or Method(s) of Measurement | Item Performer | Planned
[5 empty] | Start Date | 2012 |  |  |  | 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  |  | End Date
[6 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1 | T-1 | Synthesis development of colloidal nanoparticles | Colloidal Synthesis, TEM, XPS, UV-Vis, TGA | 1 | 2012-10-01 | [16 empty] | 2013-06-30 | bar: 2012 Q4 to 2013 Q2
1 | ST-1.1 | Synthesize ~6 nm diameter iron oxide nanoparticles. | Colloidal Synthesis | 1 | 2012-10-01 | [16 empty] | 2013-06-30 | bar: 2012 Q4 to 2013 Q2
1 | ST-1.2 | Develop synthesis of iron oxide nanoparticles of varying diameter (4, 6, 8, and 10 nm). | Colloidal Synthesis | 1 | 2013-01-01 | [16 empty] | 2013-06-30 | bar: 2013 Q1 to 2013 Q2
1 | M (T-1) | Development of four procedures for the syntheses of iron oxide nanoparticles of varying diameter (4, 6, 8, and 10 nm, +/- 1 nm). | TEM, XPS, UV-Vis, TGA | 1 | N/A | [16 empty] | 2013-06-30 | bar: 2013 Q2
1 | T-2 | Interface energetics optimization of nanoparticle/organic interface | Photoemission Techniques (UPS, IPES) | 1 & 2 | 2013-07-01 | [16 empty] | 2014-03-31 | bar: 2013 Q3 to 2014 Q1
1 | ST-2.1 | Determine work function, ionization potential, and electron affinity of iron oxide nanoparticles of different sizes. | Photoemission Techniques (UPS, IPES) | 2 | 2013-07-01 | [16 empty] | 2013-12-31 | bar: 2013 Q3 to 2013 Q4
1 | ST-2.2 | Develop a model for organic/nanoparticle/organic interface energetics. | Photoemission Techniques (UPS, IPES) | 2 | 2013-10-01 | [16 empty] | 2014-03-31 | bar: 2013 Q4 to 2014 Q1
1 | M (T-2) | Selection of a nanoparticle system that allows for favorable device operation based upon the band-edge offset diagram generated from experimental data. | Document | 1 & 2 | N/A | [16 empty] | 2014-03-31 | bar: 2014 Q1
1 | G/NG-1 | Identify the acceptor/iron oxide nanoparticle/donor system that will lead to the band-edge offset system for favorable device operation. | Publication | 1 & 2 | N/A | [16 empty] | 2014-03-31 | bar: 2014 Q1
2 | T-3 | Lab-scale nanoparticle thin-film deposition protocol | R2R Applicator, SEM, 4-point Probe, Device | 1 & 3 | 2014-04-01 | [16 empty] | 2015-03-31 | bar: 2014 Q2 to 2015 Q1
2 | ST-3.1 | Retrofit roll-to-roll (R2R) applicator with new liquid volume delivery systems and UV curing lamps. | R2R Applicator | 3 | 2014-04-01 | [16 empty] | 2014-09-30 | bar: 2014 Q2 to 2014 Q3
2 | ST-3.2 | Calibrate nanoparticle solution volume delivery. | SEM | 3 | 2014-04-01 | [16 empty] | 2014-09-30 | bar: 2014 Q2 to 2014 Q3
2 | M (ST-3.2) | Deposition of nanoparticle solution over a meter-wide flexible substrate to give a 10 nm thick film, +/- 2 nm. | R2R Applicator | 3 | 2014-07-01 | [16 empty] | 2014-09-30 | bar: 2014 Q3
2 | ST-3.3 | Measure a variety of nanoparticle thin-films via four-point probe measurements and optimize the system to obtain sheet resistance values of < 100 ohms/sq. | 4-point Probe | 1 & 3 | 2014-10-01 | [16 empty] | 2015-03-31 | bar: 2014 Q4 to 2015 Q1
2 | M (ST-3.3) | Demonstrate optimized film with both deposition of a 10 nm +/- 2 nm thin-film based on iron oxide nanoparticles of chosen size, and with a sheet resistance < 100 ohms/sq. over a substrate that is at least a meter wide. | Device | 1 & 3 | N/A | [16 empty] | 2015-03-31 | bar: 2015 Q1
2 | T-4 | Lab-scale nanoparticle thin-film deposition optimization | I-V Characterization, R2R Applicator, Device | 1 & 3 | 2015-01-01 | [16 empty] | 2015-09-30 | bar: 2015 Q1 to 2015 Q3
2 | ST-4.1 | Fabricate R2R devices with 1.0 cm2 device area and at least 10% in-house certified device efficiencies. | I-V Characterization, R2R Applicator | 1 & 3 | 2015-01-01 | [16 empty] | 2015-06-30 | bar: 2015 Q1 to 2015 Q2
2 | ST-4.2 | Fabricate R2R sub-modules with a device area of 225 cm2 and an efficiency of at least 6%, in-house certified. | I-V Characterization, R2R Applicator | 1 & 3 | 2015-04-01 | [16 empty] | 2015-06-30 | bar: 2015 Q2
2 | ST-4.3 | Obtain device (1.0 cm2) and sub-module (225 cm2) National Renewable Energy Laboratory (NREL) certified efficiencies of at least 10% and 6%, respectively. | Device | 1 & 3 | 2015-04-01 | [16 empty] | 2015-09-30 | bar: 2015 Q2 to 2015 Q3
2 | M (T-4) | A 1.0 cm2 device with an NREL certified efficiency of 9.5% under standard testing conditions (ASTM G173). | Device | 1 & 3 | N/A | [16 empty] | 2015-09-30 | bar: 2015 Q3
2 | FD-1 | A tandem organic photovoltaic device (1.0 cm2) with an NREL certified efficiency of 10%. | Device | 1, 2 & 3 | N/A | [16 empty] | 2015-09-30 | bar: 2015 Q3
2 | FD-2 | A tandem organic photovoltaic sub-module (225 cm2) with an NREL certified efficiency of 6%. | Device | 1, 2 & 3 | N/A | [16 empty] | 2015-09-30 | bar: 2015 Q3