## Overview
Project Gate Check List
Instructions
What is a Project Gate Check List
The Project Gate Check List contains the list of items that must be completed in order for the project to complete and close off a process within the project. This information will help the project manager by showing what information is still lacking for the project to sucessfully continue.

## Definitions LvL-2
Item | Description
Pre-Initiation (Gate)
Business Case Approval | This is the approval of the Business Case for the project
Organizational Readiness Confirmed | This is the review and confirmation that the organization is prepared to take ownership and responsibility for the new system to be produced during the project.
Feasibility Study Complete | The Feasibility Study for the project has been completed and results documented
High Level Estimates Complete | These are the cost estimates for the project
Funding Approval | The funding for the project has been approved by the Office of Finance
Project Scaling Complete | The project scaling spreadsheet has been filled out and the Level of the project understood
Project Request Approval | OA/OIT has reviewed and approved the project
COPPAR approval | This means the project has been reviewed and approved by OA/OIT
Product Requirements Submitted | High level requirements for the product have been collected and approved by project stakeholders
Sustainability Strategy Submitted | The strategy to sustain a new system has been reviewed and approved.
Initiating (Gate)
PM Approved | The Project Manager has been assigned to the project
Charter Approved | The Project Charter has been approved
Scope (WBS) Complete | The WBS, representing all the deliverables for the project, has been created, reviewed and approved
Requirements Complete | Detailed product requirements have been captured, reviewed and approved by project stakeholders
Planning (Gate)
Project Management Plan Complete | The different plans contained within the Project Management Plan are complete
Time Management Plan | A Time Management Plan has been created for the project
Cost Management Plan | A Cost Management Plan has been created for the project
Quality Management Plan Complete | A Quality Management Plan has been created for the project
HR Management Plan Complete | An HR Management Plan has been created for the project
Communication Management Plan Complete | A Communication Plan has been created for the project
Risk Management Plan Complete | A Risk Management Plan has been created for the project
Procurement Management Plan Complete | A Procurement Plan has been created for the project
Change Management Plan Complete | A Change Management Plan has been created for the project
Project Log Prepared | A Project Log is prepared and ready to capture Risk, Action Item, Issue, Decision, Change and Quality information about the project
ROI/Business Case Verified | The Return on Investment for the project has been validated as part of the planning process to make sure the project should continue to go further based on detailed planning
Verify the Organizational Readiness | After detailed planning has taken place, organizational readiness should be reviewed to make sure the organization is able to assume responsibility and ownership of the new system at the conclusion of the project.
Meeting Agenda & Minute Templates Copied | The Meeting Agenda and Meeting Minutes templates have been copied and modified for use during the project
Status Report format copied | The Status Report formats, for both the weekly and monthly status reports, have been copied and modified for use during the project
Lessons Learned Documented | Lessons learned concerning the project have been documented
Monitoring & Controlling (Gate)
Sustainability Plan Verified | A Sustainability Plan has been established for the new system being developed and the correct OA/OIT personnel have reviewed the plan and agree it is appropriate
Project Log Satisfied | All Risks, Action Items, Issues, Decisions, Changes and Quality elements contained in the Project Log are satisfied and complete
Risk Log Closed | All risks have been addressed and are no longer a factor for the project
Action Items Completed | All Action Items have been addressed and completed
Issues Closed | All issues have been closed off and are no longer a factor for the project
Decisions Finalized | All decisions have been implemented and are finalized
Change Log Fulfilled | All changes have logged
Scope Verified | The project stakeholders have reviewed the deliverables for the project and agree they provide the desired result for the project
User Acceptance Testing Complete | The user community has tested the new system using pre-defined testing scripts and verify that the system performs to their desire
Customer Signoff on product or deliverable | The project sponsor agrees the product is completely delivered and signed the final document stating all deliverables have been adequately delivered
Lessons Learned Documented | Lessons learned concerning the project have been documented
Close (No Gate)
Lessons Learned Archived | Lessons learned have been archived, to be used by other project managers on future projects
Completed Closing CheckList | All items on the Closing Checklist are satisfied
Transition From Project to Program Area Complete | The program area has accepted responsibility and control for the product

## Check List LvL-2
Description | Completed | Date
Pre-Initiation (Gate)
Business Case Approval
Organizational Readiness Confirmed
Feasibility Study Complete
High Level Estimates Complete
Project Scaling Complete
Funding Approval
Project Request Approval
COPPAR approval
Product Requirements Submitted
Sustainability Strategy Submitted
Initiating (Gate)
PM Approved
Charter Approved
Scope (WBS) Complete
Requirements Complete
Planning (Gate)
Project Management Plan Complete
Time Management Plan *
Cost Management Plan
Quality Management Plan
HR Management Plan
Communication Plan Complete
Risk Management Plan
Procurement Management Plan **
Change Management Plan
ROI/Business Case Verified
Verify the Organizational Readiness
Meeting Agenda & Minute Templates Copied
Status Report format copied
Lessons Learned Documented
Monitoring & Controlling (Gate)
Sustainability Plan Verified
Project Log Satisfied
Risk Log Closed
Action Items Complete
Issues Closed
Decisions Finalized
Change Log Fulfilled
Scope Verified
User Acceptance Testing Complete
Customer Signoff on product or deliverable
Lessons Learned Documented
Close (No Gate)
Lessons Learned Archived
Completed Closing Checklist
Transition From Project to Program Area Complete
* - Includes critical path.
** - If applicable to the project.