## Sheet1
City of Taylor, Commercial Projects under review, approved and under construction as of October 18, 2012
During the past year 74% of commercial projects have been reviewed within 10 days or less,
with an average review time of 7.3 days.
Project Name | Project Address | Brief Description | Date Plans | Date Plans | Date Under
|  |  | Submitted | Approved | Construction
For Review
COMMERCIAL PROJECTS
Main Street Commons | 3610 N Main | 4 story bldg for seniors | 2011-12-20 | 2012-05-03 | 2012-05-14
Alliance Geotechnical | 404 Mustang Cove | Office Building | 2011-09-19 | 2011-12-13 | 2012-03-16
Ringer Windows | Mustang Cove | Manufacture of Windows | 2012-03-02 | 2012-05-03 | 2012-05-14
McCoy's Hardware Site | 3409 N Main | Retail Store | 2012-03-01 | 2012-06-15 | 2012-06-18
McCoy's Hardware Bldg | 3409 N Main | Retail Store | 2012-06-25 | 2012-08-16 | 2012-08-30
Gemini Accessory Building | 102 Wagner Way | Utility Bldg | 2012-02-28
Masonic Lodge Expansion | 2707 Donna Dr | Expansion | 2012-01-03 | 2012-01-09 | 2012-02-01
Carl's Jr | N Main | Fast Food Store | 2010-11-01 | 2010-11-11
Wal Mart Remodel | N Main | Existing Bldg Remodel | 2011-10-11 | 2011-11-12 | 2012-02-15 | Complete
HEB Remodel | N Main | Existing Bldg Remodel | 2011-08-11 | 2011-10-12 | 2011-11-15 | Complete
First Assembly of God | Carlos G Parker Bvd | New Church | 2008-01-07 | 2012-05-25 | 2012-08-06
El Vaquerto Addition | 221 W 4th | Addition to existing restaurant | 2012-02-27
Frills | 201 W 4th | Remodel commercial for rest. | 2012-03-23 | 2012-04-30 | 2012-05-14
Randig Business Park | NE Cor. Mallard/CGP | Office Bldg | 2010-10-11 | 2011-04-07
K of C Barbeque Pits Addition | 2201 E 4th | Addition | 2012-04-24 | 2012-06-13
Beveridge Phase 2 | 1102 E 4th | New Commercial | 2012-06-05 | 2012-06-12 | 2012-06-18
Round Rock Refuse | 9979 Chandler Road | New Commercial | 2012-07-09 | 2012-08-07
Traci Qualls Pavilion | E 4th St | Add Pavilion | 2012-08-03 | 2012-08-13 | 2012-08-17 | Complete
Golden Chick | W 2nd St | New Commercial
Car Wash | N Main St | New Commercial
Big Industrial Remodel | Carlos G Parker Blvd | Remodel commercial
Community Recreation Center | Public Building |  | 2012-09-26
Blue Bonnet Remodel | 404 Carlos G Parker Blvd | Remodel commercial | 2012-09-17
The above denotes most recent plan version. Comment review time is shorter than plan approval date.
Plans may include Site Plan, Building Plans, Foundation Plans, and Fire Protection Plans