## Instructions
Project Scaling Worksheet
Instructions
What is Project Scaling ?
Project Scaling is the method that will help define the size and risk of a project as well as the amount of Project Management rigor, Governance, Documentation and Reporting needed for each project. A "Level One" scoring project is the least complex and a "Level Three" project is the most complex. The areas that will determine the project level will be the Project Complexity, Project Visibility, Project Duration and Project Cost. Some of these categories will be further broken down into subcategories. For a definition of each Category and Subcategory, please refer to the Definitions tab.
How do I determine a Project’s Level?
The Office of Policy, Planning and Performance Management has developed an easy to use Project Scaling Worksheet that analyzes project characteristics and yields a numerical score and project level.
Steps:
1. | Open the Project Scaling Worksheet
2. | Click on the Project Scaling Worksheet tab and assign a value to each of the Characteristics. The fields in orange represent columns that need to be selected.
3. | The tool will automatically add the values and display the project’s score and level in the Project Score section at the bottom of the page
4. | Once completed save and archive the file in the project's collaboration site.
5. | Once you have identified the project level, you can then review the Deliverables Matrix and the accompanying Process Flow Diagram to get an idea of the Project Management Rigor, Governance, Documentation and Reporting that will be needed for your project.

## Defintions
Project Scaling Worksheet
Definitions
Project Complexity
Sponsor | Senior manager with a vested interest in the outcome of the project. If the project is a part of a larger effort (program), then the project sponsor can be the actual program manager for the entire effort. The fewer the sponsors, the simpler the communication. If there is no sponsor, there is no clear direction. Too many sponsors could result in conflicting objectives and communication challenges.
Project Objectives | Are the project objectives clearly defined? Were clear definitions of the deliverables received for accomplishing this project?
Technical Requirements | Are the technical requirements familiar to the group? In the past, has the group developed or delivered similar requirements? Have you completed a project similar to this one in scope and complexity?
Team Location | What is the general location of the project team? Are you using internal resources only; using only contractors; or a mix of both? Are team members located in the same building, division, city or country?
Deadline | Has a firm deadline to deliver the project been established? Will the deadline allow us to complete the project in a timely manner, or is it to restrictive?
Stakeholder Involvement | Outside the project team. How many people need to be kept up to date on the project progress? How complex are the communication needs going to be?
External Dependencies | Does project success depend upon an entity outside of the commonwealth - Federal Agency, Vendor/Business Partner, local government, other states, etc.?
Project Team | How experienced is this project team using the technology associated with the project. If the project requires unfamiliar technology, the risk factor goes up.
Cross-Agency | How many agencies will collaborate to build the product?
Number of Systems Impacted | How many existing systems will be impacted by the implementation of the new system?
Organizational Risks | Is there a potential for project failure due to organizational disruptions or cultural resistance?
Project Visibility
Legislative Initiative | Is the legislature watching this project?
Governor Initiative | Is the Governor's office monitoring this project?
Federal Mandate | Did the federal government mandate this project?
Public Facing | Is this project visible to the public?
Multiple Agencies | Are multiple agencies impacted by this project?
Business Impact | Impact to business if project is successful or not successful
Project Duration
This section defines the planned duration for the overall project
Project Costs
This section defines the estimated costs for the overall project

## Project Scaling Worksheet
Project Scaling Worksheet V2
Project Complexity
|  |  | N/A | Low High
|  |  | 0 | 1 | 2 | 3 | 4 | 5 |  | Weight
| Sponsor | One | 0 | [5 empty] | More than 1 | 50%
| Project Objectives | Clear | 0 | [5 empty] | Vague | 50%
| Business Impact | Minimal | 0 | [5 empty] | Major | 50%
| Technical Requirements | Familiar | 0 | [5 empty] | Unfamiliar | 50%
| Team Location | One | 0 | [5 empty] | More than 1 | 25%
| Deadline | Loose | 0 | [5 empty] | Defined | 50%
| Stakeholder Involvement | 2 People | 0 | [5 empty] | More than 20 | 50%
| External Dependencies | None | 0 | [5 empty] | Many | 25%
| Project Team | Experienced | 0 | [5 empty] | Inexperienced | 50%
| Cross-Agency | One | 0 | [5 empty] | Many | 25%
| Number of Systems Impacted | One | 0 | [5 empty] | Many | 50%
| Organizational Risks | Not Likely | 0 | [5 empty] | Likely | 25%
| Project Complexity Score |  | 0
Project Visibility
|  |  | No |  |  | Yes
|  |  | 0 |  |  | 5 |  |  |  | Weight
| Legislative Initiative | No | 0 | [5 empty] | Yes | 50%
| Governor Initiative | No | 0 | [5 empty] | Yes | 100%
| Federal Mandate | No | 0 | [5 empty] | Yes | 70%
| Public Facing | No | 0 | [5 empty] | Yes | 70%
| Project Visibility Score |  | 0
Project Duration
|  |  | < 6 months | [5 empty] | 6 - 12 months | > 12 months
|  |  | 5 | [5 empty] | 10 | 20
Duration of the Project
Project Costs
|  |  | =<250k | [5 empty] | 250k - 1M | > 1M
|  |  | 10 | [5 empty] | 25 | 40
Cost of the Project
Project Score
| Total Calculated Score |  | 0
| Level One Project |  | < 50
| Level Two Project |  | 50 - 74
| Level Three Project |  | 75 - 100
|  | Project Complexity Values |  | 0
1
2
3
4
5
|  | Project Visibility Values |  | 0
5
|  | Project Duration |  | 5
10
20
|  | Project Costs |  | 10
25
40