## Sheet1
Washington Program Obligation Deadlines for FY 2013 |  |  |  | WA300-2014-xx - Attachment - November 5, 2013 |  |  | **UPDATED 11/5/2013**
Farm Bill Programs
1 | FINANCIAL ASSISTANCE PROGRAMS
| Program | 1st Application Batch Date (Appl. Cutoff) | Ranking and cost estimates completed | Quality Assurance and preapprovals done | 2nd Application Batch Date (Appl. Cutoff) | Ranking and cost estimates completed | Quality Assurance and preapprovals done | Statewide Sweep and reallocation | Obligation Deadline | 100% Obligation NHQ Sweeps Funds
| General EQIP (LWG), Tribal | 2013-01-17 | LWG sets | 2013-02-28 | 2013-03-21 | LWG sets | 2013-04-18 | 2013-05-16 | 2013-07-01 | 2013-07-01
| High Tunnels, Organic, Energy, Air Quality | 2013-01-17 | 2013-02-21 | 2013-02-28 | 2013-03-21 | 2013-03-28 | 2013-04-18 | 2013-05-16 | 2013-07-01 | 2013-07-01
| Green House Gas (National CIG) | NA | NA | NA | 2013-03-15 | March 22,2013 | 2013-04-05 | NA | 2013-07-01 | 2013-07-01
| AWEP (Existing Proposals) | 2013-01-17 | 2013-01-25 | February 1,2013 | 2013-02-15 | 2013-02-22 | 2013-02-28 | 2013-05-17 | 2013-07-01 | 2013-07-01
| CCPI (Existing Projects) | 2013-01-17 | 2013-01-25 | 2013-02-01 | 2013-02-15 | 2013-02-22 | 2013-02-28 | 2013-05-17 | 2013-07-01 | 2013-07-01
| National Water Quality Initiative (NWQI) | 2013-05-31 | 2013-06-14 | 2013-06-21 | NA | NA | NA | NA | 2013-08-30 | 2013-08-30
| NWQI "Edge of Field" Monitoring | 2013-06-14 | 2013-07-05 | 2013-07-26 | NA | NA | NA | NA | 2013-08-30 | 2013-08-30
| Pacific Salmon Habitat Improvement Partnership (Pilot) | 2013-04-05 | 2013-05-24 | 2013-05-31 | NA | NA | NA | NA | 2013-07-01 | 2013-07-01
| Pacific Salmon Habitat Improvement Partnership (PSHIP) | 2013-05-30 | 2013-06-07 | 2013-06-14 | NA | NA | NA | NA | 2013-07-01 | 2013-07-01
| Working Lands for Wildlife (Sagegrouse area only) | 2012-12-21 | 2013-01-25 | 2013-02-01 | 2013-02-15 | 2013-02-22 | 2013-02-28 | 2013-05-17 | 2013-07-01 | 2013-07-01
| Working Lands for Wildlife (West area only) | 2013-06-24 | 2013-06-28 | 2013-06-28 | NA | NA | NA | 2012-07-12 | 2013-08-02 | 2013-08-02
2 | STEWARDSHIP PROGRAM
| Program | Application Batch Date (Appl. Cutoff) | Application Evaluation in CMT | Application PreApproval | Complete Onsite Field Verification | Obligation Deadline | 100% Obligation NHQ Sweeps Funds
| CSP 2013 signup -1 | 2013-06-14 | 2013-07-10 | 2013-07-12 | 2013-08-02 | 2013-08-23 | 2013-08-30
3 | EASEMENT PROGRAMS
| Program | 1st Application Batch Date (Appl. Cutoff) | 2st Application Batch Date (Appl. Cutoff) | Unused Funds Returned to NHQ | Final Obligation of Funds
| FRPP | 2013-01-18 | 2013-03-15 | 2013-07-01 | 2013-09-01
| GRP | 2013-06-07 | NA | 2013-07-01 | 2013-09-01
| WRP | 2013-06-07 | NA | 2013-07-01 | 2013-09-01
4 | GRANT PROGRAMS
| Grant Type | Pre-proposal Submittal Date | Proposal Submittal Date | State Conservationist Letter of Review | Evaluation Completed | Technical Evaluation Completed | Leadership Review Completed | Announcement of Awards | Grant Agreements Obligated
| CIG National | 2013-01-11 | 2013-03-29 | 2013-05-13 | NA | June 4, 2013 | NA
CIG State Component | bar: 2013-06-14; 2013-07-12
| Note: | 2013-06-14: The "ranking completed" date is the date that all eligible applications in ProTracts will be ranked for that program