## Action Plan
[6 empty] | Drop Down List: | 1 | Complete
[7 empty] | 2 | In Progress
Action Plan | [6 empty] | 3 | Late
Topic: | Usability Testing of Library Website | Team Members: | Library Team
Start Date: |  | Objective: | To uncover design defects in the current library website as well as testing the usability of the proposed (new) library website design.
Last Updated: 02/19/2009 Version 1.3
Prepared by: | Liz McCurry
Task# | Action | When (Due by) | Who | STATUS/Follow Up | Complete
1 | Phase 1: Process Approval & Initial Survey
2 | Create Project Charter & Action Plan | 2009-02-18 | LM | In progress
3 | Literature Review | 2009-02-16 | LM | In progress
4 | Testing Proposal to include Budgetary Implications | 2009-03-16 | LM | Completed - Possible Compensation for participants only budgetary item
5 | Propose Testing to necessary parties - Bobbie, Sharon, Ryan (Bruce), Dennis | 2009-04-10 | LM, RS | RS - Proposed SR - Proposed
6 | Develop Survey for students, faculty, staff (initial feedback on usability of site). | 2009-03-27 | LM, RS | In progress
7 | Survey stakeholders (able to direct the more in-depth usability test by the initial feedback) | 04/01/2009-05/01/2009 | LM, AA, TH | This will be conducted during Library Week Activities as part of a raffle 1 ticket = 1 survey
8 | Present Findings to Rachel for preliminary website redesign/changes | 2009-06-01 | LM
9 | Phase II. Usability Testing
10 | Decide what data to collect (old vs. new website) | 2009-04-10 | LM, GZ, RM | Had a meeting with GZ/RM about website development | Complete
11 | Decide who the target goups will include | 2009-04-10 | LM, GZ | Discussion on faculty members, staff, and students for selection | Complete
12 | Develop a data collection method (the actual usability test) and a manual data collection form (observation sheet, audio recording, debriefing outline) | 2009-04-10 | LM |  | Complete
13 | Develop an orientation script | 2009-04-10 | LM |  | Complete
14 | Develop a debriefing outline | 2009-04-10 | LM |  | Complete
15 | Discuss and decide the place the data collection will take place - create the research environment - Establish protocol for observers in the room. | 2009-04-10 | LM, RH, RS | Worked with RS & IT to determine the area on where to conduct the test - settled on an office in the IT hallway | Complete
16 | Develop the demographic survey | 2009-04-10 | LM |  | Complete
17 | Test the test, testing environment, questionairre and other testing materials. *Possible to send our test out to get outside testing done on validity and credibility of questions - logical connections between the test and the desired outcomes. | 2009-04-10 | Library Team & RA | The library team completed the usability survey & provided feedback. Outside feedback from conference speakers. Feedback on tasks from GZ and outside consultants (same as survey) Sarah Edgecomb completed a preliminary test of the test on April 10th | Complete
18 | Advertise for & Seek participants (only need 8) | 04/08/2009-04/10/2009 | LM | RS provided student names. Randomly selected 7 staff & 6 faculty for advertising. Have 2 faculty & 1 staff thus far | Complete
19 | Administer & Collect background questionairre | At scheduled Test time | LM | To be done on day of testing
20 | Choose participants based on responses | 04/08/2009-04/10/2009 | LM, GZ | The participants were randomly selected based on feedback from GZ & RS. See the testing plan on how staff/faculty/students were choosen randomly. | Complete
21 | Schedule test times, leaving adequate time between tests to debrief (Use MRM to schedule the room & place any requests with IT that would be necessary) | 04/08/2009-04/10/2009 | LM | Didn't use MRM because there was an extra office available in the IT hallway. | Complete
22 | Check all equipment and testing environment | Day of test | LM | Checked before each session. | Complete
23 | Assemble all written test materals and data collection forms | 2009-04-13 | LM | In the order using an RA would be helpful during this process | Complete
24 | Contact participants to remind of test date, time, and place | Reminders to be sent out the day before the test! | LM | Reminders were sent via email one day before testing session. | Complete
25 | Create a testing checklist of tasks to be completed with the participant on the day and time of the testing | 2009-04-10 | LM |  | Complete
26 | Test each participant using the uniform methodology and checklist. Gather all information from the participants through the briefing and debriefing sessions. | 04/14/2009-04/22/2099 | Library Team | TH - 2; AA - 1; BT - 1; AM - 1; LM - 4 | Complete
27 | Phase III. Findings and Recommendations
28 | Collect and transform data into findings and recommendations | 2009-05-01 | LM, GZ, AM, RS, AA, TH
29 | Present findings and recommendations | 2009-06-01 | LM
30
31