## Process Outline
APPENDIX G
FHA TAX CREDIT PILOT PROGRAM: PROCESSING OF PROJECTS OUTSIDE OF PILOT HUB JURISDICTIONS
Rev. 10/31/12
RESPONSIBILITY-TASK | BORROWER/LENDER | HUD HQ or REGIONAL COUNSEL | ORIGINATING HUB | PROCESSING HUB
PRE-APPLICATION/CONCEPT MEETING
Preliminary Discussions/ Concept Meeting | Contacts Originating Hub's Production Chief to Arrange Meeting/Call |  | Originating Hub's Production Chief Invites Processing Hub's Pilot Designated Underwriter (DU) to Join Concept Meeting (1) | Processing Hub's Pilot Designated Underwriter (DU) Enters Project into Pilot Sharepoint Tracking Database
Eligibility and Originating Hub Staff Assignments |  |  | Originating Hub Production Chief Assigns a Coordinator to Project | Processing Hub's Pilot DU Joins Call, Confirms Project Eligibility, and Completes any necessary follow up with Lender. If Project not Eligible, Refers to Another MAP Program
HUD Counsel Assignment |  | Regional Counsel Assigns Attorney to the Project (2) |  | DU Asks Regional Counsel with Project Jurisdiction for Assignment of Attorney at Originating Hub and Invites Attorney to Join Concept Meeting/Call
ASSET MANAGEMENT (AM) WORK
Rent Increase | Borrower Requests Rent Increase, if any, and if it is a Section 8 Project, Borrower makes request 120 Days Prior to Application | Asset Management Point of Contact Oversees all AM Tasks to Ensure Conformity to Processing Time Frames | Production Chief Notifies Asset Management Point of Contact that Project is Entering Pipeline, Noting Asset Management Roles
Prepayment | Borrower Requests Prepayment of First Mortgage, if applicable, at least 120 Days Prior to Application.
Other Waivers | Lender Confirms and Advises Borrower and HUD regarding Contract Replacement, Additional Waivers, etc. in Application |  | Originating Hub Asset Management Staff Oversee Completion of All AM-Related Project Tasks: Rent Increase, Contract Replacement, Waivers and Prepayment
APPLICATION
Pre-Notification | Notifies HQ Pilot Staff One Week in Advance of Submission
Submission | Submits Application Electronically to Originating Hub and to HQ (only if Project not Located in a Pilot Hub Jursidiction)
Distribution/Legal |  | Attorney Assigned to Project Completes Initial Document Review, Attends Project Meetings |  | DU Delivers Organizational Docs, Title and Survey to Counsel Assigned
PILOT HUB SELECTION & STAFFING ASSIGNMENTS
Hub Assignment |  | HQ Pilot Staff Selects Final Processing Hub Based on Proximity, Review of Workloads, Other Factors, and Confers with Hub |  | Confers with HQ Regarding Capacity, Availability of Staff for Project
Notification & Delivery |  | HQ Pilot Staff Notifies all Other Parties of Assignment, & Forwards Application to Processing Hub |  | DU Begins Processing, Reviews Application and Confirms Project's Eligibilty for Pilot
Originating Hub Staffing Assignments |  |  | Assigns Appraiser | DU requests Originating Hub to Assign Appraiser to complete Environmental Review
(1) See Pilot Processing Hub Assignments by State Worksheet. Originating Hub will always go first to Processing Hub identified in this chart for preliminary project reviews. However, final assignments to Pilot Processing Hubs after full application is submitted may change.
(2) Regional Counsel Contacts are to be Identified for Projects based on the states in which they are located, on the "Pilot Hub Assignments by State" worksheet.
Continued Below
FHA TAX CREDIT PILOT PROGRAM: PROCESSING OF PROJECTS OUTSIDE OF PILOT HUB JURISDICTIONS (Continued)
Rev. 10/31/12
RESPONSIBILITY-TASK | BORROWER/LENDER | HUD HQ or REGIONAL COUNSEL | ORIGINATING HUB | PROCESSING HUB
UNDERWRITING REVIEW
Application Screening and Acceptance or Referral | Provides additional information as needed throughout |  |  | DU Thoroughly Reviews Package, Accepts or Refers Project to MAP, Enters Project into DAP if Accepted, and Keeps Pilot Tracker Current
Environmental | Provides additional information as needed throughout | Counsel Reviews organizational documents and if provided, draft closing documents and HQ Provides Technical Assistance/General Support as Needed & Monitors timing | Appraiser Conducts Environmental Review
Site Visit |  |  | Processing Hub's DU Conducts Site Visit if Possible, Otherwise Closest Available Environmental Officer/Appraiser completes Environmental Review and Originating Hub's Production Chief Assigns Staff for Site Visit | DU Reviews Reports
All Other Elements |  |  |  | DU Coordinates all Other Offices' Work, Completes Technical Reviews, Mortgage Credit, Appraisal, etc.
APPROVALS
Hub Director Approval | Provides additional information as needed throughout | Provides Technical Assistance/General Support as Needed | Director Reviews Loan Recommendation | DU Submits Recommendation and Draft Firm Commitment to Originating Hub Coordinator and Originating Hub Director
Hub Pilot Committee Approval |  |  | Pilot Loan Committee Reviews Loan
Firm Commitment |  |  | If Loan Approved, Director Issues Firm Commitment
PRECLOSING
Organizational Call |  |  | Counsel and Coordinator Participate | DU Sets Meeting/Call
Status Call | Lender & Borrower Participate |  | Counsel and Coordinator Participate | DU Sets Meeting/Call
CLOSING
Closing | Lender & Borrower Participate | Counsel Assigned by OGC Conducts Closing In Originating Hub Office | Assists Closing | DU Assists Closing Remotely

## Pilot Hub Assignments by State
TAX CREDIT PILOT PROGRAM HUB JURISDICTIONS, ORIGINATING HUB
STATE ASSIGNMENTS AND REGIONAL COUNSEL ASSIGNMENT CONTACTS
| Tax Credit Pilot Processing Hubs | States/Areas Within Pilot Processing Hub Jurisdiction | Additional States Assigned to Processing Hubs & Their HUD Region (1) | Tax Credit Pilot Processing Hubs | States/Areas Within Pilot Processing Hub Jurisdiction | Additional States Assigned to Processing Hubs & Their HUD Region (1) | Regional Counsel Contacts for Pilot Project Assignments
| Atlanta | Georgia | Alabama IV | Detroit | Michigan | Ohio V | Miniard Culpepper | Region I
|  | Kentucky | Florida IV |  |  | Virginia III | John Cahill | Region II
|  | Puerto Rico | North Carolina IV |  |  | West Virginia III | Sheryl Johnson | Region III
|  | Tennessee | South Carolina IV |  |  |  | Sharon Swain | Region IV
|  |  |  | Fort Worth | Arkansas | Mississippi IV | Courtney Minor | Region V
| Boston | Connecticut | Delaware III |  | Lousiana |  | William Daley | Region VI
|  | Maine | Maryland III |  | New Mexico |  | Tom Coleman | Region VII
|  | Massachusets | New Jersey II |  | Oklahoma |  | Ellen Dole | Region VIII
|  | New Hampshire | New York II |  | Texas |  | Kimberly Nash | Region IX
|  | Rhode Island | Pennsylvania III | Los Angeles | Southern California Counties (2) |  | Mona Fandel | Region X
Vermont
| Chicago | Illinois | Indiana V
|  |  | Iowa VII | San Francisco | Northern California Counties (2)
Minnesota V
|  |  | Missouri VII |  | Arizona
|  |  | Wisconsin V |  | Hawaii
| Denver | Colorado | Nebraska VII |  | Nevada
|  | Montana | Kansas VII
|  | North Dakota |  | Seattle | Alaska
|  | Sount Dakota |  |  | Idaho
|  | Utah |  |  | Oregon
|  | Wyoming |  |  | Washington
(1) Regions are identified because Regional Counsel will make assignments of Projects from Originating Hubs (i.e. Hubs not designated as Pilot Processing Hubs) to Field Counsel staff.
(2) L.A.'s Southern California jurisdiction includes Imperial, Inyo, Kern, Los Angeles, Mono, Orange, Riverside, San Bernardino, San Diego, San Luis Obispo, Santa Barbara and Ventura Counties. All other California Counties fall within the jurisdiction of Northern California's San Francisco office.
Rev. 10/31/12