## TIMELINE
Office for Nursing Research (ONR)
Today's Date:
Pre-Award Timeline
*Fill in yellow boxes |  |  | Yes/No
PI Name: |  |  | New?
Grant Title: |  |  | Resubmission?
Funding Agency: |  |  | Noncompeting Renewal?
RFA/ RFP/ PA: |  |  | RFA Open?
Enter Due Date Here | General Tasks |  | Notes & Who will be responsible?
Before 12 weeks | Complete this form and send to your Dept Administrator or Grants Manager to request staff support
Write first draft of aims & methods
12 weeks before | Schedule meeting with Vice Chair for Research (VCR) within 2 weeks
Schedule modeling party if appropriate (email Crystal Welliver to schedule); invite mentor, VCR, co-Is & external reviewer
11 weeks before | Work with Dept Administrator to make sure PI & staff are paid on department budget for % FTE spent working on grant proposal
10 weeks before | Start developing budget
9 weeks before | Check with dept administrator for administrative review of resources (space, staffing, etc.)
8 weeks before | Request letters of support, letters of agreement and biosketches
Submit nearly final draft of research plan for review by VCR; Submit draft of grant to external reviewers - request feedback in one week
If asking for $500,000 or more direct costs in any year, contact the IC program staff 8 weeks BEFORE submitting the application, to obtain agreement the IC will accept your application for consideration for award
5 weeks before | Check with Lab Manager & TIER for adequacy of budget for lab & tech costs
Finalize budget and personnel (pending VCR review)
Submit to human subjects/animal studies if not JIT
4 weeks before | Finish collecting all biosketches; make sure biosketches have PMCID #s for publications as appropriate
Provide appendices to staff for formatting & upload
Finish collecting letters of support
3 weeks before | Finish all forms
Finish almost-final draft, send to Chair & senior faculty
Fill out eGC1
2 weeks before | Dept routing begins with FINAL budget
eGC1 signed off by all departments & at OSP
1 week before | Finish final science & write cover letter
Upload all PDF files & attach FINAL version to eGC1
Notify OSP administrator when final
Due Date | Due at Sponsor Agency

## NIH Attachment Checklist
Attachment | File Names | Complete?
OTHER ATTACHMENTS
Abstract | Abstract
Project Narrative | Narrative
References | References
Resources (if applicable) | Resources
Equipment (if applicable) | Equipment
Other Attachments (if applicable - see RFA)
RESEARCH PLAN
Introduction (resubmission or revision only) | Introduction
Specific Aims | Aims
Research Strategy | Strategy
Inclusion Enrollment Report (renewals or revisions only) | Inclusion
Progress Report Publication List (renewals only) | Progress
Protection of Human Subjects | HumanSubjects
Inclusion of Women & Minorities | HS_WandM
Targeted Enrollment Table | HS_Enrollment
Inclusion of Children | HS_Children
Vertebrate Animals (if applicable) | Animals
Select Agents (if applicable) | Agents
Multiple PD/PI Plan (if applicable) | MultiplePI
Consortium/ Contractual Arrangements | Consortium
Letters of Support | Support
Resource Sharing Plan (if applicable) | Sharing
Appendices | Appendix_A, etc
BUDGET
Detailed Budget
Budget Justification | BudgetJust
Consortium Justification | ConsortiumJust
Modular Budget
Personnel Justification | PersonnelJust
Consortium Justification | ConsortiumJust
Additional Narrative Justification | AdditionalJust
SENIOR/ KEY PERSONNEL
PI Biosketch | Bio_LastName
Co-Investigator Biosketches
Consultant Biosketches
Subocontract Biosketches
MISC. ATTACHMENTS
Cover Letter | Cover
Project/Performance Site Info (if more than 8 sites) | ProjectSites