## SPED End of Year defects
Special Education End of Year defect status 6/26/2014
Bug Number | Edit Number | Error or Warning | Edit Message | Summary | *please note upgrades to Data Pipeline are every Tuesday.
2762 | SY168 | E | If Reason for Delay in IEP Implementation [Path 2] is 01, then Eligibility and Services [Path 2] must be 00. | Fixed; moving to production on 7/1
3382 | SY226 | E | Hours of Special Education Services is required if Current Eligibility and Services is 02 or 03, unless an IEP was not implemented. | Fixed; moved to production on 6/26
2854 | SY250 | E | Calculated age is outside of the expected range for grade level. Please verify that the grade and birth date are correct and refer to the Exception Request Instructions document on how to request a Grade-to-Age exception. | Fixed; moved to production on 6/26
1752 | SY267 | E | At least one Racial Category must be selected for each student. | Should be working?
2889 | SY268 | E | Grade level must be a valid grade level for the reported school based on the School Master Table. | Fixed; moving to production on 7/1
2896 | SY271 | E | SASID is required if Special Education/Part C Referral is 06. | Not fixed yet

## Student Profile defects (hidden)
Student Profile known defects - 3/12/2014
Collection | Bug Number | Edit Number | Error or Warning | Description | Summary
Student Interchange | 2919 | SP315 | E | Students must be at least age 16 to take the GED (Exit Type Code 93 or 94) or transfer into a GED program (70) | Needs to allow exceptions
Student Interchange | 2918 | SP293 | E | Students reported as graduated in Colorado (Exit Code=90,91) in the most recent prior year for which the student has a detail record may not be included in the current collection unless they have Entry Type = 90 or 91 in the first detail record. | Not working
Student Interchange | 2661 | SP330 | E | Exit Type Code 06 is not allowed for students in grades 7-12. | Closed 2/24/14
Student Interchange | 2661 | SP331 | E | Exit Type Code 06 is not allowed for students in 7th grade exiting prior to October 1. | Closed 2/24/14
Student Interchange | 2593 | SP166 | E | Student was identified as ELL prior year and this year the student is coded as Not applicable (for grades 1 and above) | Enhancement - For exception
Student Interchange | 1936 | SP160 | E | Pupils reported as being monitored or exited from a Bilingual Program must be reported as FEP. Pupils who were never an English Language Learner must NOT be reported as exited. | Enhancement - Typo
Student Interchange | 2592 | SP88 | E | Based on the results of the ACCESS for ELLs exam this student must be coded with a language proficiency of 1, 2, or 3. | Not working
Student Interchange | 2664 | sp306 | E | If Exit Type is 01, then student must be at least age 21. | Move to production
Student Interchange | 2602 | sp390 | E | Preschool Special education students are not allowed to be funded with Colorado Preschool Program Funds. Preschool Special Education students should be coded with a funding code of 84. | Not working
Student Interchange | 2510 | sp400 | E | ??? | Not working
Student Interchange | 2297 | sp173 | W | Student cannot be Continuous in Colorado for three years and continue to be classified as an Immigrant. | Resolved
Student Interchange | 2287 | sp277 | E | Summer Dropout (Exit Type = 40) are reported only for 8th-12th grade students. | Not working
Student Interchange | 2284 | sp141 | E | A funding code of 80-85, 90-95 may not be used if a student has already graduated. | Not working
Student Interchange | 2195 | sp169 | E |  | Not working