## Sheet1
|  |  | Bonneville Power Administration Interconnection Request Queue |  |  |  |  | 08/30/2014 08:03
Note: Requests with queue positions lower than 200 were submitted prior to adoption of LGIP/SGIP.
Request Number | Request Date | Project Name | Requestor | State | County | Point of Interconnection | Status | Connection Type | Requested In-Service Date | Agreed To: (Blank=TBD) | Max Outputs Summer | Winter | Interconnection Type | Generating Facility Type | Related Transmission Request | Comments | Reason Not Completed
L0376 | 2014-08-14 07:00 | Grandview Substation | US DOI Bureau of Reclamation |  |  | BPA's Grandview Substation | STUDY | LL | 2016-05-02 | 2016-05-01 17:00 | [6 empty] | .
G0498 | 2014-08-12 18:45 |  |  | WA | Mason | BPA Potlatch Substation | STUDY COMPLETED | GI | 2014-10-20 |  | 2 | 2 | ERIS | Hydro |  | 1.75 MW Request | .
L0374 | 2014-07-07 19:00 | Phillips Substation | Public Utility District No. 1 of Benton County |  |  | Franklin-Hedges 115kV | STUDY | LL | 2017-10-01 | [7 empty] | .
L0375 | 2014-07-07 19:00 | Beck Road Switching Station | Public Utility District No. 1 of Benton County |  |  | McNary-Badger Canyon 115kV | STUDY | LL | 2017-10-01 | [7 empty] | .
L0373 | 2014-06-26 | Grand Ridge Substation | Puget Sound Energy, Inc. |  |  | BPA's Sammamish-Maple Valley 230kV line | STUDY | LL | 2016-10-01 | 2017-09-30 17:00 | [6 empty] | .
L0371 | 2014-06-03 16:00 | Clodfelter Substation | Public Utility District No. 1 of Benton County |  |  | BPA's Franklin-Badger Canyon #1 115kV line | STUDY | LL | 2017-10-01 | [7 empty] | .
L0372 | 2014-06-03 16:00 | Southridge Substation | Public Utility District No. 1 of Benton County |  |  | BPA's Franklin-Badger Canyon #1 115kV line | STUDY | LL | 2017-10-01 | [7 empty] | .
L0370 | 2014-05-23 16:00 | Lyons Ferry Substation | Columbia Rural Electric Association |  |  | BPA's Central Ferry Substation | STUDY | LL | 2015-12-31 | [7 empty] | .
L0369 | 2014-03-21 09:00 | South Fork Substation | Public Utility District No. 2 of Pacific County |  |  | BPA Raymond Substation | RECEIVED | LL | 2017-10-01 | [7 empty] | .
L0368 | 2014-03-12 15:00 | Lower Monumental Substation | BPA Power Services |  |  | Lower Monumental Substation | STUDY | LL | 2017-10-01 | [7 empty] | .
L0367 | 2014-03-04 14:39 | Rachel Road | City of Richland, Washington |  |  | BPA's Badger Canyon Substation | RECEIVED | LL | 2017-10-01 | [7 empty] | .
G0497 | 2014-01-12 09:46 |  |  | ID | Cassia | Bridge Substation (or new substation nearby) | STUDY | GI | 2016-01-01 |  | 38 | 45 | NRIS & ERIS | Geothermal |  |  | .
L0366 | 2014-01-10 10:00 | New Commercial Load | Blachly-Lane Electric Cooperative |  |  | Albany-Eugene 115kV #1, mile 37, between towers 4&5. | STUDY | LL | 2017-10-02 | [7 empty] | Customer Delay
G0496 | 2013-12-12 18:00 |  |  | WA | Pend Oreille | Boundary 230 kV Switchyard | WITHDRAWN | GI | 2014-03-30 |  | 70 | 70 | ERIS | Hydro |  |  | .
G0495 | 2013-12-09 14:18 |  |  | WA | Clark | Troutdale, OR or Camas, WA | WITHDRAWN | GI | 2016-01-01 |  | 60 | 60 | ERIS | Combined cycle |  | FES Report issued | .
L0365 | 2013-10-25 10:00 | Blue Lake | Portland General Electric Company |  |  | BPA's Troutdale Substation | STUDY | LL | 2017-06-01 | [7 empty] | .
L0364 | 2013-09-17 12:00 | Long Canyon | Wells Rural Electric Company |  |  | BPA's West Wendover Substation | STUDY | LL | 2017-10-01 | [7 empty] | .
L0363 | 2013-08-27 17:00 | Oregon LNG | LNG Development Company, LLC |  |  | BPA's Clatsop Substation | WITHDRAWN | LL | 2016-10-03 | [6 empty] | Withdrawn by BPA 4/30/14 | .
G0494 | 2013-08-22 12:41 |  |  | OR | Malheur | Harney Substation | STUDY | GI | 2015-05-01 |  | 3 | 3 | ERIS | Hydro |  | Generator Nameplate Rating: 2.75 MW | .
G0493 | 2013-08-06 13:01 |  |  | ID | Cassia | At or near BPA's Bridge Substation. | WITHDRAWN | GI | 2016-01-01 |  | 30 | 30 | NRIS & ERIS | Geothermal |  | Withdrawn 6/2/2014 | .
G0492 | 2013-08-02 15:22 | Dworshak Fourth Unit | BPA Power Services | ID | Clearwater | Dworshak Substation. | STUDY | GI | 2019-07-01 |  | 300 | 300 | NRIS | Hydro |  | ISIS Report issued 2/4/2014, no impact | .
G0491 | 2013-07-29 09:04 |  |  | OR | Gilliam | Alkali Canyon Substation on BPA's Tower Road-Alkali Canyon 115 kV line. | STUDY COMPLETED | GI | 2014-03-01 |  | 7 | 7 | ERIS | Biogas |  |  | .
L0362 | 2013-07-22 10:00 | Neskowin Substation | Tillamook People's Utility District |  |  | BPA Tillamook-Boyer 115 kV Line | STUDY | LL | 2016-10-03 | [7 empty] | .
G0490 | 2013-07-05 15:05 |  |  | WA | Douglas |  | STUDY | GI | 2022-01-02 |  | 345 | 345 | ERIS | Hydro |  | FAS Report issued 12/8/2013, no impact | .
L0361 | 2013-06-27 10:00 | Network Load Expansion Phase 2 | Northern Wasco County People's Utility District |  |  | Discovery Substation | STUDY | LL | 2015-10-01 | [7 empty] | .
L0360 | 2013-06-12 12:23 | EWEB Leaburg | Eugene Water & Electric Board |  |  | CUGR THUR1 28 1 A | STUDY | LL | 2015-10-01 | [7 empty] | .
G0489 | 2013-06-06 11:02 |  |  | OR | Gilliam | Low side of existing Wheatfield Wind Power Project, LLC 34.5 kV / 230 kV substation. | WITHDRAWN | GI | 2015-12-15 |  | 5 | 5 | ERIS | Solar |  |  | .
L0359 | 2013-06-05 14:05 | PSE Cherry Point | Puget Sound Energy, Inc. |  |  | Loop in of BPA Intalco-Custer #1 230 kV line | STUDY | LL | 2017-03-01 | [7 empty] | .
G0488 | 2013-05-30 08:51 |  |  | ID | Gem |  | STUDY | GI | 2016-07-01 |  | 13 | 13 | ERIS | Hydro |  | This is a proposed 12.5 MW addition to a 10.2 MW generating capacity of an existing facility, making a combined total of 22.7 MW. | .
G0484 | 2013-05-07 09:20 |  |  | WA | Snohomish | BPA's Snohomish Substation | STUDY | GI | 2014-06-02 |  | 1 | 1 | ERIS | Energy Storage |  |  | .
G0483 | 2013-05-01 15:10 |  |  | WA | Skamania | Trout Creek Field @ Wind River Business Park, Hemlock WA | STUDY COMPLETED | GI | 2014-05-01 |  | 3 | 3 | ERIS | Biomass |  | Generator Nameplate Rating: 2,165 kW; FAS issued 3/12/14 | .
G0482 | 2013-04-30 14:06 |  |  | WA | Lewis | 11814 Hwy 12, Randle, WA 98377 | STUDY COMPLETED | GI | 2013-07-01 |  | 1 | 1 | ERIS | Hydro |  | Generator Nameplate Rating: 500 kW | .
G0481 | 2013-04-25 16:55 |  |  | WA | Snohomish | Snohomish PUD's 12 kV distribution system (Harbour Pointe circuit 12-2277) | STUDY COMPLETED | GI | 2013-08-01 |  | 2 | 2 | ERIS | Energy Storage |  | Generator Nameplate Rating: 1.5 MW | .
G0480 | 2012-12-10 09:55 |  |  | OR | Tillamook | TPUD Distribution System | STUDY COMPLETED | GI | 2013-05-30 |  | 2 | 2 | ERIS | Biomass |  |  | .
L0358 | 2012-11-23 10:36 | L0358 City of Ellensburg Helena Avenue Sub | City of Ellensburg |  |  | A proposed new Helena Avenue substation tap on the existing 115 kV East Ellensburg Tap approx. 2.1 miles before East Ellensburg Sub. | STUDY COMPLETED | LL | 2015-12-31 | [7 empty] | .
L0357 | 2012-11-15 10:00 | UEC McNary 115KV Breaker 3 | Umatilla Electric Cooperative |  |  | BPA McNary Substation | STUDY COMPLETED | LL | 2015-10-01 | [7 empty] | .
G0479 | 2012-10-22 16:30 |  |  | OR | Lake | Tap of 115 kV BPA line between LaPine and Fort Rock. POI approx. 1 mile N of the Fort Rock Substation. | WITHDRAWN | GI | 2014-12-31 |  | 100 | 100 | NRIS & ERIS | Solar |  |  | .
L0356 | 2012-09-25 14:00 | Benton REA Huard Road | Benton Rural Electric Association |  |  | Prosser Tap off Grandview to Snipes 115kV Line | STUDY | LL | 2015-10-01 | [7 empty] | .
L0355 | 2012-09-10 12:00 | Network Load Expansion | Northern Wasco County People's Utility District |  |  | Chenoweth-The Dalles 115 kV Line | STUDY COMPLETED | LL | 2015-10-01 | [7 empty] | .
G0478 | 2012-09-06 14:13 |  |  | OR | Morrow | BPA's proposed Longhorn 500/230 kV Substation. | STUDY | GI | 2016-11-01 |  | 500 | 500 | NRIS & ERIS | Wind |  |  | .
G0477 | 2012-09-05 15:48 |  |  | OR | Deschutes | Pilot Butte to LaPine transmission line | STUDY COMPLETED | GI | 2015-12-31 |  | 38 | 38 | ERIS | Geothermal |  | Draft FAS report issued 5/15/14; final FAS pending | .
L0354 | 2012-08-09 14:01 | Cowlitz John Street | Public Utility District No. 1 of Cowlitz County |  |  | BPA Lexington Substation | WITHDRAWN | LL | 2015-11-06 | [6 empty] | Withdrawn by Customer 2/1/13 | .
L0351 | 2012-08-03 09:00 | PDX-1 and PDX-4 Data Centers - Phase 2 | Umatilla Electric Cooperative |  |  | BPA's Boardman Substation | STUDY COMPLETED | LL | 2015-11-02 | [7 empty] | .
L0352 | 2012-08-03 09:00 | PDX-2 Data Center - Phase 2 | Umatilla Electric Cooperative |  |  | BPA McNary | STUDY COMPLETED | LL | 2015-11-02 | [7 empty] | .
L0353 | 2012-08-03 09:00 | Hat Rock | Umatilla Electric Cooperative |  |  | BPA Hat Rock | WITHDRAWN | LL | 2015-11-02 | [6 empty] | Withdrawn by Customer | .
G0476 | 2012-07-18 09:53 | The Dalles Northshore Fishway Project | Northern Wasco County People's Utility District | OR | Wasco | Existing Interconnection Point at Spearfish Substation | ENERGIZED | GI | 2012-11-12 |  | 7 | 7 | ERIS | Hydro |  | On-line January 2013 | .
L0350 | 2012-07-11 13:25 | Skokomish Substation | Public Utility District No. 1 of Mason County |  |  |  | ENERGIZED | LL | 2013-10-31 | [7 empty] | .
L0349 | 2012-07-05 10:00 | Canby Substation | PacifiCorp |  |  | BPA's Canby Substation | STUDY COMPLETED | LL | 2014-10-31 | [7 empty] | .
L0348 | 2012-06-25 09:00 | McNary 115kV Breaker | Umatilla Electric Cooperative |  |  | McNary Substation | STUDY COMPLETED | LL | 2015-10-01 | [7 empty] | .
G0475 | 2012-06-21 11:42 |  |  | WA | Walla Walla | Walla Walla Substation point of delivery #4048. | STUDY COMPLETED | GI | 2013-01-01 |  | 3 | 3 | ERIS | Hydro |  |  | .
L0347 | 2012-05-29 09:00 | LNG Compressor Load | Columbia River People's Utility District |  |  | St. Johns-Allston 115kV | WITHDRAWN | LL | 2017-10-01 |  | 40 | 40 |  |  |  | Withdrawn by customer. | .
L0346 | 2012-05-18 09:00 | Airport Road | Consumers Power, Inc. |  |  | Albany-Lebanon 115kV #1 | STUDY | LL | 2013-11-01 | [7 empty] | .
L0345 | 2012-05-15 14:00 | Big Eddy-Redmond 230kV Line | Central Electric Cooperative, Inc. |  |  | BPA Big Eddy-Redmond #1 230kV Line | STUDY | LL | 2015-06-01 | [7 empty] | .
G0473 | 2012-05-12 16:41 |  |  | OR | Wasco | Wasco Electric Cooperative's 115 kV Line. | WITHDRAWN | GI | 2013-07-15 |  | 10 | 10 | ERIS | Wind |  | Withdrawn on October 7, 2013. | .
G0474 | 2012-05-12 16:41 |  |  | OR | Wasco | Wasco Electric Cooperative's 115 kV line. | WITHDRAWN | GI | 2013-07-15 |  | 10 | 10 | ERIS | Wind |  | Withdrawn on June 29, 2012. | .
G0471 | 2012-04-11 16:44 |  |  | WA | Klickitat | Harvalum 230 kV Substation | WITHDRAWN | GI | 2016-03-01 |  | 590 | 590 | ERIS | Combined cycle |  | Withdrawn on March 8, 2013. | .
G0470 | 2012-03-21 14:07 | RES Ag Biomass Project | RES - Ag FGO LLC | OR | Yamhill | Breaker 51 out of Booth Bend. | ENERGIZED | GI | 2012-10-15 |  | 1 | 1 | ERIS | Biomass |  |  | .
L0344 | 2012-03-15 09:00 | Slatt Substation | PacifiCorp |  |  | At or near Slatt Substation | WITHDRAWN | LL | 2015-10-01 | [6 empty] | LLIR withdrawn by customer on February 19, 2013. | .
G0469 | 2012-01-27 10:07 | Whitefish In-Line Hydroelectric Project | City of Whitefish, Montana | MT | Flathead | BPA's Flathead Substation | ENERGIZED | GI | 2012-08-07 |  | 1 | 1 | ERIS | Hydro |  | Generator Nameplate: 261 kW | .
L0340 | 2011-12-13 17:00 | DLB2 | Umatilla Electric Cooperative |  |  | Boardman or Longhorn | STUDY COMPLETED | LL | 2015-10-01 |  | 90 | 90 |  |  |  |  | .
L0341 | 2011-12-13 17:00 | Maverick Data Center | Umatilla Electric Cooperative |  |  | Boardman | WITHDRAWN | LL | 2015-10-01 |  | 30 | 30 |  |  |  | Withdrawn by customer 8/3/2012 | .
L0342 | 2011-12-13 17:00 | PDX1&4 Data Centers | Umatilla Electric Cooperative |  |  | Boardman | STUDY COMPLETED | LL | 2015-10-01 |  | 60 | 60 |  |  |  |  | .
L0343 | 2011-12-13 17:00 | PDX2 | Umatilla Electric Cooperative |  |  | McNary | STUDY COMPLETED | LL | 2015-10-01 |  | 30 | 30 |  |  |  |  | .
L0339 | 2011-12-07 09:42 | Bertelsen-Seneca Upgrade | Eugene Water & Electric Board |  |  | BPA Eugene Substation | STUDY COMPLETED | LL | 2014-12-01 | [7 empty] | .
G0468 | 2011-12-06 15:57 | Stoltze Land and Lumber Project | F.H. Stoltze Land and Lumber Co. | MT | Flathead | Flathead 12.5 kV Radial from Trumble Creek Substation. | ENERGIZED | GI | 2013-10-01 |  | 3 | 3 | ERIS | Biomass |  | Generator Nameplate: 2.5 MW | .
L0338 | 2011-10-26 13:39 | Worden Substation | Columbia Rural Electric Association |  |  | BPA's Franklin-Walla Walla 115kV Line 13/6 | STUDY COMPLETED | LL | 2013-01-01 | [7 empty] | .
L0337 | 2011-10-24 09:18 | DLB1 | Umatilla Electric Cooperative |  |  | BPA's future Longhorn Substation | STUDY COMPLETED | LL | 2015-02-11 |  | 30 | 30 |  |  |  |  | .
G0467 | 2011-10-19 14:42 |  |  | OR | Wasco | BPA's Maupin Substation from at or near Wasco's Antelope Substation. | WITHDRAWN | GI | 2015-12-31 |  | 101 | 101 | NRIS & ERIS | Wind |  | Withdrawn by Customer on December 19, 2011. | .
L0336 | 2011-10-05 15:37 | S. Tacoma-Southwest 230kV, Tacoma-Southwest 230kV | Tacoma Power |  |  | BPA Tacoma & BPA South Tacoma Substations | STUDY COMPLETED | LL | 2012-05-31 | [7 empty] | .
G0466 | 2011-10-04 10:36 | Sisters Irrigation Hydro Project | Three Sisters Irrigation District | OR | Deschutes | 68000 Hwy 20 W, Bend, OR 97701 | ENERGIZED | GI | 2013-09-03 |  | 1 | 1 | ERIS | Hydro |  |  | .
G0465 | 2011-09-15 14:46 |  |  | OR | Wasco | Wasco Electric Cooperative's 115 kV line. | WITHDRAWN | GI | 2012-12-31 |  | 10 | 10 | ERIS | Wind |  | Withdrawn on May 11,2012. | .
L0335 | 2011-09-13 09:43 | Project Maverick | Central Electric Cooperative, Inc. |  |  | BPA's Ponderosa Substation | STUDY COMPLETED | LL | 2012-10-01 | [7 empty] | .
G0464 | 2011-09-02 11:23 |  |  | WA | Clark | CPUD feeder connected to CPUD's King Station and closest BPA point of receipt is BPA's Ross Substation. | WITHDRAWN | GI | 2013-09-12 |  | 5 | 5 | ERIS | Biomass |  |  | .
G0463 | 2011-09-01 12:11 |  |  | OR | Lake, Harney | BPA's 230 kV transmission facilities at Ponderosa Substation. | WITHDRAWN | GI | 2014-12-31 |  | 400 | 400 | NRIS & ERIS | Wind |  | Withdrawn on September 6, 2013. | .
G0462 | 2011-09-01 12:10 |  |  | OR | Lake, Harney | BPA's transmission facilities at Summer Lake Substation. | WITHDRAWN | GI | 2014-12-31 |  | 500 | 500 | NRIS & ERIS | Wind |  | Withdrawn by Customer on February 27, 2012. | .
G0461 | 2011-08-12 15:54 |  |  | OR | Wasco | Wasco Electric Cooperative's 115 kV Line. | WITHDRAWN | GI | 2012-12-31 |  | 10 | 10 | ERIS | Wind |  | Withdrawn on May 11,2012 | .
L0334 | 2011-08-12 09:38 | Grand Coulee-Westside | Avista Corporation |  |  | BPA's Grand Coulee-Westside 230kV Transmission Line near mile 76, tower 3 | WITHDRAWN | LL | 2014-10-01 | [6 empty] | Withdrawn by Avista 11/20/12. | .
G0460 | 2011-08-10 15:32 |  |  | OR | Umatilla | BPA's McNary Substation. | WITHDRAWN | GI | 2015-01-01 |  | 220 | 220 | NRIS & ERIS | Gas peaking generation |  | Withdrawn on September 6, 2013 | .
G0459 | 2011-08-07 16:21 |  |  | OR | Linn | At a point on BPA's Albany-Salem 115 kV transmsission line within a mile either side of Conser Road. | WITHDRAWN | GI | 2013-05-01 |  | 65 | 45 | NRIS & ERIS | Gas peaking generation |  | Withdrawn by Customer on December 20,2011. | .
L0333 | 2011-08-05 10:22 | La Grande Substation | Oregon Trail Electric Consumers Cooperative, Inc. |  |  | BPA's La Grande Substation | WITHDRAWN | LL | 2015-01-01 | [6 empty] | Withdrawn by Customer | .
G0458 | 2011-08-04 09:25 |  |  | OR | Union | Oregon Trail Electric Cooperative's Cove Avenue Substation | WITHDRAWN | GI | 2011-12-31 |  | 2 | 2 | ERIS | Solar |  | Withdrawn on May 2, 2012 | .
G0457 | 2011-07-28 16:10 |  |  | OR | Morrow | Slatt substation. | STUDY COMPLETED | GI | 2015-05-01 |  | 36 | 36 | NRIS | Combined cycle |  | Increment to Interconnection Request G0380; Expected Synch date 11/15/15 | .
L0332 | 2011-06-30 09:57 | Baldwin Data Center | Central Electric Cooperative, Inc. |  |  | BPA Ponderosa Substation | STUDY COMPLETED | LL | 2014-10-01 | [7 empty] | .
G0456 | 2011-06-08 15:35 |  |  | WA | Jefferson | At existing interconnection facilities in BPA's Fairmount Substation. | WITHDRAWN | GI | 2013-12-31 |  | 25 | 25 | NRIS & ERIS | Biomass |  |  | .
G0455 | 2011-05-20 11:31 |  |  | OR | Morrow | In the area of Ione Substation/Kinger Tap. | WITHDRAWN | GI | 2014-12-31 |  | 50 | 50 | NRIS & ERIS | Wind |  |  | .
L0331 | 2011-05-12 12:59 | CEC POD at Ponderosa | Central Electric Cooperative, Inc. |  |  | BPA Ponderosa Substation | STUDY COMPLETED | LL | 2014-10-01 | [7 empty] | .
G0454 | 2011-05-11 10:53 |  |  | OR | Morrow | Slatt Substation | WITHDRAWN | GI | 2012-12-01 |  | 20 | 20 | ERIS | Wind |  |  | .
G0452 | 2011-05-09 17:45 |  |  | OR | Umatilla | BPA's McNary Substation at 500 kV. | STUDY COMPLETED | GI | 2015-06-01 |  | 410 | 390 | NRIS & ERIS | Gas peaking generation |  | ISIS Report issued 10/10/2013 | .
G0453 | 2011-05-06 11:53 | University of Oregon CoGeneration | University of Oregon | OR | Lane | EWEB's new U of O Substation | ENERGIZED | GI | 2012-06-01 |  | 11 | 11 | ERIS | Combined cycle |  | on-line September 2012 | .
L0330 | 2011-04-28 09:00 | Addy | tester |  |  | BPA's Addy Substation | WITHDRAWN | LL | 2013-10-31 | [6 empty] | Withdrawn by customer 11/9/11. | .
L0329 | 2011-04-22 09:00 | Red Mountain-Reata 115kV/Dallas Road Substation | City of Richland, Washington |  |  | BPA's Red Mountain-Badger Canyon 115kV Transmission Line | STUDY | LL | 2013-10-31 | [7 empty] | .
L0327 | 2011-04-19 06:58 | Lower Snake Redundant PH Tie Lines | US Department of Army Corps of Engineers |  |  | Lower Monumental Little Goose Lower Granite | WITHDRAWN | LL | 2013-10-01 | [7 empty] | .
L0328 | 2011-04-14 11:20 | Ellensburg-Moxee Tap | Public Utility District No. 1 of Kittitas County |  |  | Columbia-Moxee 115kV Line | WITHDRAWN | LL | 2013-10-01 | [6 empty] | Withdrawn by customer 11/26/12 | .
G0450 | 2011-03-16 16:04 | Farm Power Tillamook | Farm Power Tillamook LLC | OR | Tillamook | Tillamook PUD's Feeder Circuit #63, connected to the Wilson River Substation. | ENERGIZED | GI | 2011-11-01 |  | 1 | 1 | ERIS | Biomass |  |  | .
L0326 | 2011-03-07 14:46 | Ponderosa Substation | PAC |  |  | BPA Ponderosa Substation | ENERGIZED | LL | 2013-10-01 | [7 empty] | .
L0325 | 2011-02-15 10:41 | Alcoa Substation | Clark Public Utilities |  |  | BPA Alcoa Substation | STUDY COMPLETED | LL | 2013-09-01 | [7 empty] | .
G0449 | 2011-02-11 15:01 | Farm Power Misty Meadow | Farm Power Misty Meadow, LLC | OR | Tillamook | Tillamook PUD's Feeder Circuit #63, connected to the Wilson River Substation. | ENERGIZED | GI | 2011-11-01 |  | 1 | 1 | ERIS | Biomass |  |  | .
L0324 | 2011-01-10 11:47 | Knights Bridge Substation | Canby Utility Board |  |  | Knigts Bridge Rd & S. Barlow Rd (adjacent to PGE Canby Sub) | ENERGIZED | LL | 2013-10-01 | [7 empty] | .
G0447 | 2010-12-16 13:58 |  |  | OR | Morrow | A proposed new substation on BPA's McNary-Calpine 500 kV transmission line. | WITHDRAWN | GI | 2013-05-01 |  | 215 | 240 | NRIS & ERIS | Gas peaking generation |  | Withdrawn by Customer on November 19, 2011. | .
G0446 | 2010-12-16 13:57 |  |  | OR | Morrow | A proposed new substation on BPA's McNary-Coyote Springs 500 kV transmission line. | WITHDRAWN | GI | 2013-05-01 |  | 215 | 240 | NRIS & ERIS | Gas peaking generation |  | Withdrawn by customer; letter instructions received November 15, 2013. | .
L0323 | 2010-12-14 15:14 | Aurora Project | City of Richland, Washington |  |  | BPA Ashe Substation and Ashe-Coyote Springs Transmission Line | WITHDRAWN | LL | 2012-07-14 | [6 empty] | Withdrawn by customer 4/21/14 | .
G0448 | 2010-12-13 19:12 |  |  | ID | Cassia | Idahome Substation | WITHDRAWN | GI | 2011-09-01 |  | 20 | 20 | ERIS | Wind |  | Status changed to Withdrawn on 8/27/14. Customer failed to timely execute an agreement. | .
G0445 | 2010-12-07 02:09 |  |  | ID | Cassia | Idahome Substation | WITHDRAWN | GI | 2011-09-01 |  | 20 | 20 | ERIS | Wind |  | Status changed to Withdrawn on 8/27/14. Customer did not timely execute an agreement. | .
G0441 | 2010-11-03 15:44 |  |  | WA | Franklin | Pole 66 G 129 at the Esquatzel Canal and Columbia River Road | STUDY COMPLETED | GI | 2011-02-01 |  | 2 | 2 | ERIS | Hydro |  |  | .
G0440 | 2010-11-02 23:52 |  |  | OR | Umatilla | Umatilla Electric Coop Butter Creek Substation | STUDY COMPLETED | GI | 2011-12-31 |  | 10 | 10 | ERIS | Wind |  |  | .
G0439 | 2010-11-02 10:55 | JC-Biomethane Biogas Plant | JC-Biomethane LLC | OR | Lane | Blachly-Lane Electric Cooperative's Parker Substation | ENERGIZED | GI | 2011-10-31 |  | 2 | 2 | ERIS | Biogas |  | on-line | .
G0443 | 2010-10-22 23:59 |  |  | ID | Cassia | Canal to Minidoka BPA 13.8kV line, 6-8 miles south of Minidoka. | WITHDRAWN | GI | 2011-12-31 |  | 20 | 20 | ERIS | Wind |  | Withdrawn on 10/31/13 | .
G0442 | 2010-10-22 23:57 |  |  | ID | Cassia | Canal to Minidoka BPA 13.8kV line, 6-8 miles South of Minidoka Dam | WITHDRAWN | GI | 2011-12-31 |  | 20 | 20 | ERIS | Wind |  | Withdrawn 10/31/13 | .
G0438 | 2010-10-15 17:38 |  |  | OR | Polk and Lincoln | On BPA's Salem-Grande Ronde-Tillamook 230 kV line near Grande Ronde | WITHDRAWN | GI | 2013-10-01 |  | 125 | 125 | NRIS & ERIS | Wind |  |  | .
G0437 | 2010-09-30 21:13 |  |  | OR | Lake | BPA's Harney 115 kV transmission line | STUDY COMPLETED | GI | 2013-12-31 |  | 30 | 38 | ERIS | Geothermal |  | FAS Draft Report issued 1-31-2014, still in review with customer | .
L0322 | 2010-09-29 14:18 | Klondike/Blalock Reinforcement | Wasco Electric Cooperative, Inc. |  |  | BPA's DeMoss 115kV Substation | STUDY | LL | 2014-07-01 | [7 empty] | .
L0321 | 2010-09-29 13:56 | Fossil-Big Eddy Loop | Wasco Electric Cooperative, Inc. |  |  | 69kV loop from Fossil to Maupin and Maupin to Big Eddy | WITHDRAWN | LL | 2013-07-01 | [6 empty] | Withdrawn effective April 9, 2013 | .
G0436 | 2010-09-27 20:16 |  |  | OR | Morrow and Umatilla | BPA's 500 kV McNary Hermiston line | WITHDRAWN | GI | 2014-12-31 |  | 481 | 481 | NRIS & ERIS | Wind |  |  | .
G0444 | 2010-09-10 16:50 |  |  | WA | Cowlitz | Existing interconnection facilities in Cowlitz PUD service area. | WITHDRAWN | GI | 2011-10-01 |  | 35 | 35 | NRIS & ERIS | Biomass |  | Withdrawn 11/25/13 | .
G0435 | 2010-08-27 21:13 |  |  | OR | Morrow | New substation on 500 kV McNary-HPP Line | STUDY COMPLETED | GI | 2013-11-01 |  | 238 | 238 | NRIS & ERIS | Wind |  | Comprehensive FAS issued 3/7/2014 | .
L0320 | 2010-08-23 15:49 | Woodland Tap | Public Utility District No. 1 of Cowlitz County |  |  | BPA Woodland Tap, Ross-Lexington 230kV Line | WITHDRAWN | LL | 2012-10-01 | [6 empty] | Request withdrawn by customer on 10/24/12. | .
G0434 | 2010-08-19 20:49 |  |  | OR | Linn | At Emerald PUD Facility 12.47 kV bus A-3 | WITHDRAWN | GI | 2012-03-01 |  | 11 | 11 | ERIS | Biomass |  | Withdrawn on January 28, 2011. | .
G0433 | 2010-08-02 10:24 | Outback | Outback Solar, LLC | OR | Lake | Midstate Electric 24.9 kV distribution system | ENERGIZED | GI | 2010-11-15 |  | 1 | 1 | ERIS | Solar |  |  | .
G0432 | 2010-07-08 20:21 |  |  | WA | Kittitas | BPA's Bettas Road 230 kV Substation | STUDY COMPLETED | GI | 2012-12-01 |  | 18 | 18 | ERIS | Wind |  | Incremental to Request No. G105. May 25, 2011: reduced from 31 to 18 MW | .
G0431 | 2010-06-30 14:47 |  |  | OR | Lake | Fort Rock Substation | STUDY COMPLETED | GI | 2012-06-29 |  | 20 | 20 | ERIS | Solar |  | Awaiting Customer permits | .
G0430 | 2010-05-14 12:48 |  |  | WA | Benton | Red Mountain Substation | WITHDRAWN | GI | 2013-12-31 |  | 200 | 200 | NRIS & ERIS | Wind |  | Withdrawn by customer by letter received May 4, 2011. | .
G0429 | 2010-05-06 17:08 |  |  | OR | Wasco | BPA's 230 kV Maupin-Redmond Transmission Line. | WITHDRAWN | GI | 2012-12-31 |  | 135 | 135 | NRIS & ERIS | Wind |  |  | .
G0428 | 2010-05-06 12:23 |  |  | OR | Morrow | New substation on 500 kV McNary-HPP Line | STUDY COMPLETED | GI | 2014-12-01 |  | 201 | 201 | NRIS & ERIS | Wind |  | Comprehensive FAS issued 3/7/2014 | .
G0427 | 2010-04-30 14:26 |  |  | OR | Wheeler | TBD | WITHDRAWN | GI | 2013-04-01 |  | 300 | 300 | NRIS & ERIS | Wind |  | Withdrawn by Customer on June 18, 2010. | .
G0426 | 2010-04-23 12:34 |  |  | WA | Mason | BPA's transmission facilities in or near Shelton substation. | WITHDRAWN | GI | 2013-06-01 |  | 31 | 31 | ERIS | Biomass |  | Withdrawn by Customer on March 17, 2011. | .
G0424 | 2010-04-22 11:34 |  |  | OR | Lake | Summer Lake substation. | WITHDRAWN | GI | 2013-12-31 |  | 103 | 103 | ERIS | Wind |  | Withdrawn on September 27, 2010. | .
G0425 | 2010-04-22 11:34 |  |  | OR | Lake | Summer Lake Subtstation. | WITHDRAWN | GI | 2013-12-31 |  | 103 | 103 | ERIS | Wind |  | Withdrawn on September 27, 2010. | .
G0423 | 2010-04-09 14:37 |  |  | OR | Grant | 115 kV BPA De Moss-Big Eddy line (4.2 miles west of De Moss Substation) | WITHDRAWN | GI | 2011-07-26 |  | 10 | 10 | ERIS | Wind |  |  | .
G0422 | 2010-04-09 13:07 |  |  | OR | Wheeler | Fossil Substation | WITHDRAWN | GI | 2013-04-01 |  | 100 | 100 | NRIS & ERIS | Wind |  | Withdrawn by Customer on June 18, 2010, following Scoping Meeting. | .
G0420 | 2010-04-06 12:58 |  |  | WA | Klickitat | BPA's proposed Wood Creek Substation | STUDY COMPLETED | GI | 2012-12-01 |  | 60 | 60 | Energy | Wind |  | FAS Study Issued 5/16/2013 | .
G0421 | 2010-04-05 07:16 |  |  | OR | Douglas | BPA's Gardiner Substation via Douglas Electric Cooperative's Transmission/Distribution Facility. | STUDY | GI | 2012-06-01 |  | 2 | 2 | ERIS | Wave |  |  | .
G0419 | 2010-04-01 14:22 |  |  | WA | Clallam | At the 69kV bus in BPA's Port Angeles Substation. | STUDY COMPLETED | GI | 2012-04-30 |  | 20 | 20 | NRIS | Biomass |  | Awaiting Customer permits | .
G0418 | 2010-03-29 10:50 |  |  | OR | Morrow | Ione Substation | STUDY COMPLETED | GI | 2011-06-15 |  | 20 | 20 | ERIS | Wind |  |  | .
G0417 | 2010-03-25 10:31 |  |  | UT | Box Elder | Into the Wendover-Minidoka 138 kV transmission line. | WITHDRAWN | GI | 2013-10-01 |  | 50 | 50 | NRIS & ERIS | Wind |  | Request reduced to 50 MW per letter received on January 3, 2011. | .
G0416 | 2010-03-23 18:04 |  |  | OR | Lake | To BPA's Transmission Facilities through the 115 kV facilities of Midstate Electric Cooperative. Midstate Electric Coop 115 kV line | STUDY COMPLETED | GI | 2012-09-30 |  | 20 | 20 | NRIS & ERIS | Solar |  | effective July 30, 2010, G0416 seeks interconnection of a reduced nameplate generating capacity of 20 MW (in lieu of 75 MW). | .
G0415 | 2010-03-22 11:21 |  |  | OR | Clatsop | BPA's 115 kV Transmission Facilities at or near Fern Hill Substation. | WITHDRAWN | GI | 2012-04-01 |  | 20 | 20 | ERIS | Biomass |  | Withdrawn on January 28, 2011 | .
G0413 | 2010-03-19 09:28 |  |  | OR | Lake | BPA's Summer Lake Substation at 230 kV | WITHDRAWN | GI | 2012-12-31 |  | 103 | 103 | NRIS & ERIS | Wind |  | Withdrawn by Customer on September 1, 2011. | .
G0414 | 2010-03-19 09:28 |  |  | OR | Lake | BPA's Summer Lake Substation at 230 kV | WITHDRAWN | GI | 2012-12-31 |  | 103 | 103 | NRIS & ERIS | Wind |  | Withdrawn by Customer on September 1, 2011. | .
G0412 | 2010-03-12 14:37 |  |  | ID | Cassia | Minidoka-Unity 138 kV line | WITHDRAWN | GI | 2011-12-01 |  | 20 | 20 | ERIS | Wind |  | Withdrawn on April 13, 2010 | .
G0411 | 2010-03-12 14:35 |  |  | ID | Cassia | Minidoka-Unity 138 kV line | WITHDRAWN | GI | 2011-12-01 |  | 20 | 20 | ERIS | Wind |  | Withdrawn on April 13, 2010 | .
G0409 | 2010-02-26 09:20 |  |  | OR | Lake | TO THE MIDSTATE ELECTRIC 24.9 KV DISTRIBUTION SYSTEM ON THE EAST BORDER OF THE PROPERTY, ALONG OIL DRI ROAD. | STUDY COMPLETED | GI | 2010-12-07 |  | 5 | 5 | ERIS | Solar |  | Awaiting Customer permits | .
G0410 | 2010-02-26 09:20 |  |  | OR | Lake | TO THE MIDSTATE ELECTRIC 24.9 KV DISTRIBUTION SYSTEM ON THE WEST BORDER OF THE PROPERTY, ALONG FOSSIL LAKE ROAD. | STUDY COMPLETED | GI | 2010-12-07 |  | 5 | 5 | ERIS | Solar |  | Awaiting Customer permits. | .
G0408 | 2010-02-09 09:43 |  |  | OR | Umatilla | New substation on 500 kV McNary-HPP Line | STUDY COMPLETED | GI | 2012-12-01 |  | 400 | 400 | NRIS & ERIS | Wind |  | Comprehensive FAS issued 3-7-2014 | .
G0407 | 2010-02-04 09:41 | Coastal Energy Project | Coastal Energy Project, LLC | WA | Grays Harbor | Grays Harbor PUD 15 kV Distribution Pole Number P1/64 | ENERGIZED | GI | 2010-05-17 |  | 6 | 6 | ERIS | Wind |  | on-line June 2010 | .
G0406 | 2010-02-01 15:08 |  |  | WA | Klickitat | BPA’s Big Eddy-McNary 230 kV Transmission Line in Klickitat County, Wash. | WITHDRAWN | GI | 2012-12-31 |  | 99 | 99 | ERIS | Wind |  | Withdrawn by Customer on September 14, 2010. | .
G0405 | 2010-01-29 12:45 |  |  | ID | Madison | BPA’s Goshen-Drummond No. 1 161 kV Transmission Line in Madison Co. Idaho | WITHDRAWN | GI | 2010-11-30 |  | 240 | 240 | NRIS | Wind |  | Withdrawn by Customer on November 1, 2010. | .
G0403 | 2010-01-27 16:51 |  |  | OR | Morrow | New substation on 500 kV McNary-HPP Line | STUDY | GI | 2014-11-01 |  | 302 | 302 | NRIS | Wind |  | Comprehensive FAS issued 3/7/2014 | .
G0404 | 2010-01-27 16:51 |  |  | OR | Morrow | New substation on 500 kV McNary-HPP Line | STUDY | GI | 2014-11-01 |  | 302 | 302 | NRIS | Wind |  | Comprehensive FAS issued 3/7/2014 | .
G0402 | 2010-01-12 09:19 |  |  | OR | Sherman | BPA’s Transmission Facilities at or close to John Day Substation. | WITHDRAWN | GI | 2013-10-01 |  | 110 | 110 | ERIS | Wind |  | Withdrawn on July 1, 2013 | .
G0401 | 2010-01-12 03:44 |  |  | OR | Wasco | 230 kV Big Eddy - Maupin or Buckley 500 kV | STUDY COMPLETED | GI | 2013-12-31 |  | 299 | 299 | NRIS & ERIS | Wind |  | FAS Study Issued 9/16/2011 Optional Study issued 6/25/2012 | Awaiting Customer Permits To Complete NEPA Review
G0400 | 2010-01-06 09:23 |  |  | OR | Lake | 115 kV Fort Rock Line(between LaPine Substation and Midstate’s Fort Rock Substation) | WITHDRAWN | GI | 2011-12-31 |  | 20 | 20 | ERIS | Solar |  | Withdrawn on January 5, 2011 | .
G0399 | 2009-12-16 15:00 |  |  | OR | Morrow | The 69 kV transmission system of Columbia Basin Electric Cooperative, approximately 15 line miles from BPA’s Ione Substation | WITHDRAWN | GI | 2010-08-01 |  | 10 | 10 | Energy | Biomass |  | Withdrawn on July 21, 2010 | .
G0397 | 2009-12-15 09:31 |  |  | WA | Klickitat | BPA’s Goldendale-Chenoweth Transmission Line at 115 kV | WITHDRAWN | GI | 2011-12-31 |  | 202 | 202 | Energy | Wind |  | Withdrawn by Customer on September 14, 2010. | .
G0398 | 2009-12-15 09:31 |  |  | WA | Klickitat | BPA’s Transmission Facilities at or near Centerville, Wash. at 230 kV | WITHDRAWN | GI | 2011-12-31 |  | 101 | 101 | Energy | Wind |  | Withdrawn by Customer on April 29, 2010. | .
L0318 | 2009-12-14 13:39 | McNary Substation | Umatilla Electric Cooperative |  |  |  | WITHDRAWN | LL | 2012-09-01 | [6 empty] | Request withdrawn by customer 9/19/11 | .
L0317 | 2009-12-14 13:30 | Decatur Island Tap | Orcas Power & Light Cooperative |  |  |  | STUDY COMPLETED | LL | 2013-09-01 | [7 empty] | .
G0396 | 2009-11-30 16:07 |  |  | WA | Klickitat | BPA’s transmission facilities in/near Goldendale, Wash. | WITHDRAWN | GI | 2013-01-01 |  | 56 | 56 | NRIS | Wind |  | Withdrawn on November 19, 2012 | .
G0394 | 2009-11-24 12:49 |  |  | OR | Deschutes | BPA’s Lapine Substation | STUDY COMPLETED | GI | 2012-03-01 |  | 28 | 28 | NRIS | Biomass |  | FAS Study Issued 11/21/2011 | .
G0395 | 2009-11-23 14:37 |  |  | ID | Cassia | Minidoka-Unity 138 kV line | STUDY | GI | 2010-10-15 |  | 20 | 20 | ERIS | Wind |  |  | .
G0393 | 2009-11-17 09:30 |  |  | WA | Kittitas | 345 kV Rocky Reach - Maple Valley transmission line | WITHDRAWN | GI | 2010-12-15 |  | 75 | 75 | NRIS | Solar |  | Withdrawn on 4/8/2014 | .
G0392 | 2009-11-09 08:49 |  |  | OR | Gilliam | 345 kV Rocky Reach - Maple Valley transmission line | WITHDRAWN | GI | 2013-12-01 |  | 300 | 300 | NRIS | Wind |  | Withdrawn on October 24, 2012 | .
G0391 | 2009-11-03 16:44 |  |  | OR | Gilliam | BPA’s Transmission Facilities on the Slatt-Buckley or Ashe-Marion transmission lines approx. 9 miles SW of Slatt | WITHDRAWN | GI | 2013-03-01 |  | 425 | 425 | NRIS | Wind |  | Withdrawn by Customer on February 25, 2014. | .
G0388 | 2009-11-02 18:45 |  |  | ID | Cassia | BPA’s Idahome Substation | WITHDRAWN | GI | 2010-10-15 |  | 20 | 20 | ERIS | Wind |  | Deemed Withdrawn May 27, 2014 | .
G0389 | 2009-11-02 12:02 |  |  | OR | Morrow | New Substation near McNary 500 kV | STUDY | GI | 2013-11-01 |  | 207 | 207 | NRIS | Wind |  | Comprehensive FAS issued 3/7/2014 | .
G0390 | 2009-11-02 12:02 |  |  | OR | Morrow | New Substation near McNary 500 kV | STUDY | GI | 2013-11-01 |  | 207 | 207 | NRIS | Wind |  | Comprehensive FAS issued 3/7/2014 | .
G0386 | 2009-10-28 08:47 |  |  | WA | Garfield | BPA’s Pomeroy Substation | WITHDRAWN | GI | 2011-12-01 |  | 20 | 20 | ERIS | Wind |  | Withdrawn by Customer on June 1, 2011. | .
G0387 | 2009-10-26 15:49 |  |  | OR | Lake | Midstate Electric 24.9kV distribution system at Christmas Valley Substation | STUDY COMPLETED | GI | 2009-12-31 |  | 10 | 10 | ERIS | Solar |  |  | .
G0385 | 2009-10-08 18:07 |  |  | OR | Lake | Midstate Electric’s Fort Rock Substation at 115 kV bus | STUDY COMPLETED | GI | 2011-12-01 |  | 15 | 15 | ERIS | Solar |  | Integration; Studies completed | .
G0383 | 2009-10-06 23:06 |  |  | WA | Pacific | Raymond 115 kV Substation | WITHDRAWN | GI | 2012-12-31 |  | 100 | 100 | NRIS | Wind |  | Withdrawn on 7/30/2014 | .
G0384 | 2009-10-06 09:06 |  |  | OR | Coos | Bandon 115 kV Substation | WITHDRAWN | GI | 2011-06-01 |  | 101 | 101 | NRIS | Wind |  | Withdrawn by Customer on July 12, 2010. | .
G0381 | 2009-09-21 16:19 |  |  | OR | Harney | On Harney Electric Cooperative’s 115 kV line ~ 30 miles south of Burns, Ore. | WITHDRAWN | GI | 2012-12-31 |  | 103 | 103 | ERIS | Wind |  | Withdrawn by Customer on September 1, 2011. | .
G0382 | 2009-09-21 14:51 |  |  | WA | Yakima & Benton | At BPA’s Midway 230 kV substation | WITHDRAWN | GI | 2012-10-30 |  | 100 | 100 | NRIS | Wind |  | Withdrawn by Customer on March 31, 2011. | .
G0380 | 2009-09-15 16:40 | Carty CCCT | Portland General Electric Company | OR | Morrow | 500 kV Slatt Substation | ENERGIZED | GI | 2014-05-01 |  | 413 | 464 | NRIS | Combined cycle |  | Expected Synch date is 11/15/15 | .
G0379 | 2009-09-02 15:30 |  |  | OR | lake | Midstate Electric 24.9 kV distribution system | STUDY COMPLETED | GI | 2010-07-30 |  | 4 | 4 | ERIS | Solar |  | Integration, Study issued 5/12/2010 | .
L0316 | 2009-08-28 14:25 | McNary Substation | PacifiCorp |  |  | BPA's McNary Substation | STUDY COMPLETED | LL | 2011-10-01 | [7 empty] | .
L0314 | 2009-08-27 09:25 | Merchant Txm Line-Townsend | Tonbridge Power Inc |  |  | BPA Colstrip line at or near Townsend, MT | STUDY | LL | 2013-10-01 | [7 empty] | .
L0315 | 2009-08-27 09:25 | Merchant Txm Line-Garrison | Tonbridge Power Inc |  |  | BPA Colstrip 500kV Line at Garrison Substation | STUDY | LL | 2013-10-01 | [7 empty] | .
G0378 | 2009-08-27 09:22 |  |  | WA | Mason | BPA’s Substation at Shelton, Wash. | WITHDRAWN | GI | 2012-12-31 |  | 65 | 65 | ERIS | Biomass |  | Withdrawn by Customer on March 18, 2011 | .
L0313 | 2009-08-20 11:34 | Bridge Substation | Raft River Rural Electric Cooperative, Inc. |  |  | BPA's Bridge Substation | WITHDRAWN | LL | 2010-11-01 | [7 empty] | .
L0311 | 2009-08-10 16:53 | Lancaster Substation | Avista Corporation |  |  | Lancaster 230 | ENERGIZED | LL | 2012-09-01 | [7 empty] | .
L0312 | 2009-08-10 10:48 | Bell-Boundary #1 230 kV | Inland Power & Light Company |  |  | Bell-Boundary #1 transmission line. | ENERGIZED | LL | 2011-10-01 | [7 empty] | .
G0376 | 2009-08-06 10:09 |  |  | OR | Lake | Midstate Electric 24.9 kV distribution system | STUDY COMPLETED | GI | 2010-07-30 |  | 4 | 4 | ERIS | Solar |  | Integration, Study Issued 3/12/10 | .
G0377 | 2009-08-06 10:09 | Outback | Outback Solar, LLC | OR | Lake | Midstate Electric 24.9 kV distribution system | ENERGIZED | GI | 2010-07-30 |  | 4 | 4 | ERIS | Solar |  | Integration; on-line November 2012 | .
L0310 | 2009-07-30 14:52 | Mount Adams Substation | Yakama Power |  |  | Feeder #2 out of BPA's Alfalfa Substation | ENERGIZED | LL | 2009-12-01 | [7 empty] | .
G0375 | 2009-07-14 13:18 |  |  | WA | Klickitat | BPA’s proposed Wood Creek 230 kV Substation | WITHDRAWN | GI | 2011-10-01 |  | 50 | 50 | ERIS | Wind |  | Withdrawn on September 17, 2012 | .
G0374 | 2009-06-30 09:53 | Horse Butte Wind | Horse Butte Wind I LLC | ID | Bonneville | 115 kV Goshen-Palisades transmission line | ENERGIZED | GI | 2010-12-31 |  | 100 | 100 | NRIS | Wind |  | on-line August 2012 | .
G0373 | 2009-06-29 10:27 |  |  | MT | Flathead & Lincoln | 230 kV Libby-Haskill line | WITHDRAWN | GI | 2012-04-30 |  | 200 | 200 | NRIS | Wind |  | Withdrawn on June 5, 2013 | .
G0371 | 2009-06-03 14:15 |  |  | WA | Grays Harbor | TBA | WITHDRAWN | GI | 2012-12-31 |  | 65 | 65 | ERIS | Biomass |  | Withdrawn on May 4, 2010 | .
G0372 | 2009-06-03 14:15 |  |  | ID | Latah | TBA | WITHDRAWN | GI | 2012-12-31 |  | 65 | 65 | ERIS | Biomass |  | Withdrawn by Customer on June 14, 2010. | .
G0369 | 2009-06-02 12:55 |  |  | WA | Benton | BPA's Red Mountain Substation. | WITHDRAWN | GI | 2012-12-31 |  | 65 | 65 | ERIS | Wind |  | Withdrawn by Customer on September 8, 2011. | .
G0368 | 2009-06-01 12:04 |  |  | OR | Wasco | Maupin 230 kV substation | STUDY COMPLETED | GI | 2013-08-01 |  | 101 | 101 | NRIS | Wind |  | FAS Issued 4/27/2011 | .
G0367 | 2009-06-01 12:03 |  |  | OR | Wasco | Maupin 230 kV substation | STUDY COMPLETED | GI | 2012-12-01 |  | 202 | 202 | NRIS | Wind |  | FAS Study Issued 4/27/2011 | .
G0370 | 2009-06-01 10:39 | Young’s Creek Hydro Project | Public Utility District No. 1 of Snohomish County | WA | Snohomish | Sultan Substation | ENERGIZED | GI | 2010-12-31 |  | 8 | 8 | ERIS | Hydro |  | on-line December 2010 | .
G0366 | 2009-05-18 21:41 |  |  | OR | Morrow | New Substation near McNary 500 kV. | STUDY COMPLETED | GI | 2014-11-01 |  | 302 | 302 | NRIS | Wind |  | FAS Study Issued 7/6/2011 | .
G0365 | 2009-05-18 21:40 |  |  | OR | Morrow | New Substation near McNary 500 kV. | STUDY COMPLETED | GI | 2013-11-01 |  | 302 | 302 | NRIS | Wind |  | FAS Study Issued 11/1/2012 | .
L0309 | 2009-05-18 14:01 | Benton City Substation | Benton Rural Electric Association |  |  | Grandview-Red Mountain #1 115kV | ENERGIZED | LL | 2012-11-01 | [7 empty] | .
L0308 | 2009-05-18 10:43 | Transmission Reinforcement | Peninsula Light Company |  |  | Shelton-Kitsap 115kV Line | STUDY COMPLETED | LL | 2012-11-01 | [7 empty] | .
G0364 | 2009-04-24 13:41 |  |  | WA | Kittitas | TBD | WITHDRAWN | GI | 2011-12-31 |  | 50 | 50 | NRIS | Biomass |  | Withdrawn by Customer on August 7, 2009. | .
G0363 | 2009-04-03 15:40 |  |  | OR | Gilliam | New Substation near McNary 500 kV. | STUDY COMPLETED | GI | 2012-11-01 |  | 204 | 204 | NRIS | Wind |  | Study Issued 11/1/2012 | .
G0362 | 2009-04-03 15:39 |  |  | OR | Gilliam | New Substation near McNary 500 kV | STUDY COMPLETED | GI | 2012-11-01 |  | 204 | 204 | NRIS | Wind |  | FAS Study Issued 7/6/2011 | .
G0361 | 2009-04-02 15:29 |  |  | OR | Umatilla | New substation on 500 kV McNary-HPP Line | STUDY COMPLETED | GI | 2011-10-01 |  | 201 | 201 | NRIS | Wind |  | FAS Study Issued 12/22/2010 | .
G0360 | 2009-03-25 11:26 |  |  | WA | Grays Harbor | Grays Harbor PUD’s 15 kV Distribution line | WITHDRAWN | GI | 2009-07-01 |  | 6 | 6 | ERIS | Wind |  | Withdrawn on December 16, 2009. | .
G0359 | 2009-03-25 09:53 |  |  | OR | Umatilla | Sacajawea 115 kV Substation | WITHDRAWN | GI | 2012-10-01 |  | 101 | 101 | NRIS | Wind |  | Withdrawn by Customer on February 27, 2012. | .
G0358 | 2009-03-24 09:13 | Flathead LFGTE Project | Flathead Electric Cooperative, Inc. | OR | Flathead | Flathead’s LaSalle Substation | ENERGIZED | GI | 2009-05-01 |  | 2 | 2 | ERIS | Biogas |  | on-line June 2009 | .
G0357 | 2009-03-18 20:10 |  |  | OR | Harney | Diamond Junction near the Harney-Catlow line | WITHDRAWN | GI | 2010-12-31 |  | 104 | 104 | NRIS | Wind |  | Withdrawn by Customer on October 4, 2010. | .
L0307 | 2009-03-16 11:02 | Flathead Substation 230kV Bay | Flathead Electric Cooperative, Inc. |  |  | BPA's Flathead Substaion 230kV | ENERGIZED | LL | 2010-11-01 | [7 empty] | .
G0356 | 2009-03-09 15:49 |  |  | MT | Wheatland | 500kV Broadview-Townsend transmission line | WITHDRAWN | GI | 2015-12-31 |  | 200 | 200 | NRIS | Wind |  | Withdrawn by Customer on June 26, 2012. | .
G0355 | 2009-03-09 15:47 |  |  | MT | Meagher | 500kV Broadview-Townsend transmission line | WITHDRAWN | GI | 2014-12-31 |  | 200 | 200 | NRIS | Wind |  | Withdrawn by Customer on June 26, 2012. | .
G0354 | 2009-03-09 15:45 |  |  | MT | Meagher | 500kV Broadview-Townsend transmission line | WITHDRAWN | GI | 2014-12-31 |  | 200 | 200 | NRIS | Wind |  | Withdrawn by Customer on June 26, 2012. | .
G0353 | 2009-03-09 15:42 |  |  | MT | Meagher | 500kV Broadview-Townsend transmission line. | WITHDRAWN | GI | 2013-12-31 |  | 200 | 200 | NRIS | Wind |  | Withdrawn by Customer on June 26, 2012. | .
L0306 | 2009-02-17 12:38 | Dayton Substation | Columbia Rural Electric Association |  |  | Walla Walla-Tucannon 115kV Line | ENERGIZED | LL | 2011-10-01 | [7 empty] | .
L0305 | 2009-02-06 09:32 | Westside Phase II | City of Idaho Falls |  |  | BPA's Westside Substation | WITHDRAWN | LL | 2011-10-01 | [7 empty] | .
G0352 | 2009-01-26 16:09 |  |  | OR | Coos | Reedsport-Fairview 115 kV transmission line | WITHDRAWN | GI | 2013-12-31 |  | 120 | 120 | ERIS | Combined cycle |  | Withdrawn by Customer on April 12, 2010. 8/12/09: FES review meeting held; FES report available on request. ISIS completed. April 12, 2010: Following review of the ISIS report, customer withdrew the Request by letter. | .
G0350 | 2008-12-02 09:34 |  |  | WA | Klickitat | BPA's Harvalum 230 kV substation | WITHDRAWN | GI | 2099-01-01 |  | 1200 | 1200 | NRIS | Energy Storage |  | Withdrawn by Customer on January 12, 2009. | .
G0351 | 2008-12-02 09:34 |  |  |  |  | BPA's Rock Creek substation | WITHDRAWN | GI | 2099-01-01 |  | 1200 | 1200 | NRIS | Energy Storage |  | Withdrawn November 28, 2012 | .
G0349 | 2008-11-18 09:23 | Senaca Sawmill | Blachly-Lane Electric Cooperative | OR | Blachly Lane | Blachly Lane Substation | ENERGIZED | GI | 2010-10-01 |  | 20 | 20 | N/A | Biomass |  | on-line | .
G0348 | 2008-10-23 15:52 |  |  | OR | Umatilla | Umatilla Electric Coop’s 12.47kV Line, Pole #3N 27E 138000 | WITHDRAWN | GI | 2008-12-31 |  | 2 | 2 | Energy | Wind |  | Withdrawn on October 29, 2010 | .
G0347 | 2008-09-24 19:43 |  |  | OR | Harney | Harney Electric Coop Harney-Fields 115 kV line. Withdrawn by Customer on February 20, 2009. | WITHDRAWN | GI | 2013-12-31 |  | 76 | 76 | NRIS | Wind |  | Withdrawn on Febuary 20, 2009 | .
G0346 | 2008-09-24 19:42 |  |  | OR | Harney | Harney Electric Coop Harney-Fields 115 kV line. Withdrawn by Customer on February 20, 2009. | WITHDRAWN | GI | 2013-12-31 |  | 76 | 76 | NRIS | Wind |  | Withdrawn on February 20, 2009 | .
L0304 | 2008-09-24 11:14 | Saddleback Mountain Interconnection | Public Utility District No. 1 of Klickitat County |  |  | BPA's Midway-North Bonneville 230kV Line | WITHDRAWN | LL | 2010-10-01 | [7 empty] | .
G0345 | 2008-09-16 16:50 |  |  | OR | Wasco | Big Eddy-Redmond 230 kV line | STUDY COMPLETED | GI | 2010-08-30 |  | 201 | 201 | ERIS | Wind |  | FAS Study Issued 8/8/2010 | .
G0344 | 2008-09-04 16:35 |  |  | OR | Gilliam | New Substation near Slatt 500 kV | STUDY | GI | 2011-09-01 |  | 488 | 488 | NRIS | Wind |  | Re-study underway | .
L0302 | 2008-09-03 12:15 | Tower Road Substation | Umatilla Electric Cooperative |  |  | BPA's Boardman-Alkali 115kV Line | WITHDRAWN | LL | 2010-09-01 | [7 empty] | .
L0303 | 2008-09-03 12:15 | Port of Morrow Substation | Umatilla Electric Cooperative |  |  | BPA's Boardman-Tower Rd 115kV Line | WITHDRAWN | LL | 2010-09-01 | [6 empty] | Request withdrawn by customer 9/19/11 | .
G0343 | 2008-09-02 09:33 |  |  | OR | Wasco | BPA's Big Eddy-Maupin 230 kV transmission line | WITHDRAWN | GI | 2010-12-01 |  | 107 | 107 | NRIS | Wind |  | Withdrawn by Customer on June 9, 2009. | .
G0341 | 2008-08-27 16:17 |  |  | OR | Morrow | Boardman - Ione 69 kV line | WITHDRAWN | GI | 2012-10-01 |  | 200 | 200 | NRIS | Wind |  | Deemed Withdrawn on April 5, 2011. Customer did not meet terms of LGIP, Section 3.3.5. | .
G0342 | 2008-08-27 09:17 |  |  | OR | Gilliam | New Substation near Slatt 500 kV. | STUDY | GI | 2011-10-01 |  | 200 | 200 | NRIS | Wind |  | Re-study underway | .
G0340 | 2008-08-07 19:42 |  |  | WA | Grant | Midway-Rocky Ford 230 kV Transmission line | WITHDRAWN | GI | 2011-12-31 |  | 185 | 185 | NRIS | Wind |  | Withdrawn on July 30, 2013 | .
G0338 | 2008-07-28 16:05 |  |  | OR | Umatilla | Walla Walla-Pendleton 69 kV line | WITHDRAWN | GI | 2013-12-31 |  | 100 | 100 | NRIS | Wind |  | Withdrawn on January 24, 2013 | .
G0339 | 2008-07-28 16:05 |  |  | OR | Umatilla | Walla Walla-Pendleton 69 kV line | WITHDRAWN | GI | 2013-12-31 |  | 152 | 152 | NRIS | Wind |  | Withdrawn by Customer on August 31, 2009. | .
G0337 | 2008-07-11 14:49 |  |  | WA | Klickitat & Yakima | New substation on BPA's 500 kV McNary-John Day 500 kV line | WITHDRAWN | GI | 2011-10-01 |  | 200 | 200 | NRIS | Wind |  | Withdrawn by Customer on June 10, 2009. | .
G0336 | 2008-07-11 14:48 |  |  | WA | Klickitat & Yakima | New substation on BPA's 500 kV McNary-John Day 500 kV line | WITHDRAWN | GI | 2011-10-01 |  | 200 | 200 | NRIS | Wind |  | Withdrawn by Customer on June 10, 2009. | .
L0301 | 2008-07-03 09:31 | Spearfish Substation Expansion | Public Utility District No. 1 of Klickitat County |  |  | BPA's Chenoweth-Goldendale 115kV Line | WITHDRAWN | LL | 2010-10-01 | [7 empty] | .
L0300 | 2008-06-20 11:28 | Pinecreek Substation | Okanogan County Public Utility District No. 1 |  |  | Omak-Tonasket #1 & #2 Txm Line, Twr 11/1 | ENERGIZED | LL | 2009-09-01 | [7 empty] | .
L0299 | 2008-06-18 11:00 | Skamania PUD Transmission Reinforcement | Public Utility District #1 of Skamania County |  |  | BPA's Midway-N.Bonneville 230kV line in the vicinity of Underwood Substation. | WITHDRAWN | LL | 2010-10-01 | [7 empty] | .
G0334 | 2008-05-30 16:18 |  |  | OR | Gilliam | New Substation near Slatt 500 kV. | STUDY | GI | 2010-10-01 |  | 300 | 300 | NRIS | Wind |  | Re-study underway | .
G0333 | 2008-05-20 16:08 |  |  | OR | Wasco | Big Eddy-Maupin 230 kV line | WITHDRAWN | GI | 2010-12-01 |  | 200 | 200 | NRIS | Wind |  | Withdrawn by Customer on March 19, 2009. | .
G0332 | 2008-05-19 15:41 | King Estate Solar Generator Project | Lane Electric Cooperative, Inc. | OR | Lane | Integrating in Lane Electric Coop's system (Fox Hollow Substation) | ENERGIZED | GI | 2008-12-01 |  | 1 | 1 | NRIS | Solar |  | on-line November 2009 | .
L0298 | 2008-05-14 12:50 | NorthernLights Transmission Project | NorthernLights Transmission, Inc. |  |  | BPA's Buckley Substation | WITHDRAWN | LL | 2014-05-01 | [7 empty] | .
G0328 | 2008-05-12 23:28 |  |  | WA | Garfield | Central Ferry Substation | WITHDRAWN | GI | 2012-07-01 |  | 252 | 252 | ERIS | Wind |  | Withdrawn on July 12, 2013 | .
G0329 | 2008-05-12 23:28 |  |  | WA | Garfield | Central Ferry Substation | WITHDRAWN | GI | 2013-08-01 |  | 252 | 252 | ERIS | Wind |  | Withdrawn on July 12, 2013 | .
G0330 | 2008-05-12 23:28 |  |  | WA | Garfield | Central Ferry Substation | WITHDRAWN | GI | 2014-10-01 |  | 116 | 116 | ERIS | Wind |  | Withdrawn by Customer on August 1, 2011. | .
G0327 | 2008-05-09 13:30 | Columbia Ridge Landfill | WM Renewable Energy, LLC | OR | Gilliam | At or near Alkali Substation | ENERGIZED | GI | 2009-01-01 |  | 7 | 7 | Energy | Biomass |  | on-line December 2009 | .
G0326 | 2008-05-05 16:29 |  |  | UT | Box Elder | At BPA's 138 kV Bridge Substation | STUDY COMPLETED | GI | 2010-06-30 |  | 42 | 42 | NRIS | Wind |  | FAS Study Issued 8/17/2010 | .
G0325 | 2008-04-29 12:25 |  |  | WA | Grant | A point on BPA’s Midway-Rocky Ford 230kV line | WITHDRAWN | GI | 2011-12-31 |  | 130 | 130 | NRIS | Wind |  | Withdrawn by Customer on March 5, 2009. | .
L0297 | 2008-04-24 10:00 | Data Center | Umatilla Electric Cooperative |  |  | BPA's McNary, Hatrock or Boardman Substation | WITHDRAWN | LL | 2010-09-01 | [7 empty] | .
L0296 | 2008-04-18 11:00 | Sunriver | Midstate Electric Cooperative, Inc. |  |  | BPA LaPine-Pilot Butte 230kV Line | STUDY COMPLETED | LL | 2012-09-01 | [7 empty] | .
L0295 | 2008-04-17 15:57 | St.Johns-Allston Interconnection | Columbia River People's Utility District |  |  | St.Johns-Allston 115kV Line | STUDY COMPLETED | LL | 2012-10-01 | [7 empty] | .
L0294 | 2008-04-14 09:34 | New Commercial/Industrial Substation | Blachly-Lane Electric Cooperative |  |  | Between BPA Parker and Junction City Substations | STUDY COMPLETED | LL | 2010-09-01 | [6 empty] | All studies for this request are complete (3/30/10). | .
G0324 | 2008-04-08 13:55 |  |  | WA | Garfield | BPA's Tucannon River-North Lewiston No. 1 115 kV transmission line | WITHDRAWN | GI | 2010-12-01 |  | 300 | 300 | NRIS | Wind |  | Withdrawn on February 26, 2010 | .
G0323 | 2008-04-08 13:53 |  |  | OR | Sherman | New Substation near John Day 500 kV Substation | STUDY COMPLETED | GI | 2011-12-01 |  | 300 | 300 | NRIS | Wind |  | FAS Study Issued 9/20/2009 | .
L0293 | 2008-04-08 08:19 | Vantage Substation | PacifiCorp |  |  | BPA Vantage Substation | STUDY | LL | 2009-09-01 | [7 empty] | .
G0322 | 2008-04-07 08:55 |  |  | WA | Klickitat | At a point in BPA's Harvalum Substation, at 230 kV | WITHDRAWN | GI | 2009-12-31 |  | 51 | 51 | ERIS | Wind |  | Withdrawn on June 3, 2008 | .
L0292 | 2008-04-01 09:10 | Bakers Corner Tap | Public Utility District No. 1 of Cowlitz County |  |  | Lexington-Longview 115 kV Line | ENERGIZED | LL | 2009-09-01 | [6 empty] | Studies complete | .
G0321 | 2008-03-27 15:19 |  |  | WA | Grays Harbor | Satsop 230 kV | WITHDRAWN | GI | 2010-06-01 |  | 290 | 295 | NRIS | Combined cycle |  | Withdrawn by Customer on March 5, 2010. On February 20, 2009, Customer was notified that the FES Report would be delayed until March 27, 2009, to allow more detailed study of line routings and constraints for a preferred plan of service. | .
L0291 | 2008-03-27 14:59 | Chenowith Tap | Northern Wasco County People's Utility District |  |  | Big Eddy - Chenowith 115 kV | WITHDRAWN | LL | 2009-09-01 | [7 empty] | .
G0318 | 2008-03-27 14:38 |  |  | WA | Klickitat | Goldendale 115 kV | WITHDRAWN | GI | 2010-07-01 |  | 20 | 20 | Energy | Wind |  | Withdrawn by Customer on March 8, 2012. | .
G0319 | 2008-03-27 14:38 |  |  | WA | Klickitat | Goldendale 115 kV | WITHDRAWN | GI | 2010-07-01 |  | 20 | 20 | Energy | Wind |  | Withdrawn by Customer on March 8, 2012. | .
G0320 | 2008-03-27 14:38 |  |  | WA | Klickitat | Goldendale 115 kV | WITHDRAWN | GI | 2010-07-01 |  | 20 | 20 | Energy | Wind |  | Withdrawn by Customer on March 8, 2012. | .
L0290 | 2008-03-27 12:58 | Ethanol Facility | Public Utility District No. 1 of Franklin County |  |  | Franklin Substation | WITHDRAWN | LL | 2009-09-01 | [7 empty] | .
G0335 | 2008-03-20 09:20 | W Hill Landfill Gas Plant | Public Utility District No. 1 of Klickitat County | WA | Klickitat | Roosevelt 115 kV | ENERGIZED | GI | 2010-09-01 |  | 17 | 17 | Energy | Biogas |  | on-line October 2011 | .
G0317 | 2008-03-17 12:05 | Libby 6th Unit | BPA Power Services | MT | Lincoln | Existing T-3 at the Libby Project | WITHDRAWN | GI | 2010-09-07 |  | 120 | 120 | NRIS | Hydro |  | Withdrawn by Customer on April 9, 2010. | .
L0289 | 2008-03-17 09:41 | Gardiner-Reedsport | Central Lincoln People's Utility District |  |  | Gardiner Substation | STUDY COMPLETED | LL | 2009-09-01 | [6 empty] | Studies complete | .
L0288 | 2008-03-14 13:00 | Industrial Park | Columbia Rural Electric Association |  |  | Franklin-Walla Walla 115 kV/Sacajawea Sub | WITHDRAWN | LL | 2009-09-01 | [7 empty] | .
G0316 | 2008-03-12 10:11 |  |  | OR | Yamhill | 230 kV Tillamook-Carlton line | WITHDRAWN | GI | 2011-07-01 |  | 100 | 100 | ERIS | Wind |  | Withdrawn February 9, 2009 | .
G0315 | 2008-03-03 11:25 |  |  | WA | Lewis | 115 kV line at Pe Ell Substation | WITHDRAWN | GI | 2012-12-01 |  | 150 | 150 | NRIS | Wind |  | Withdrawn February 9, 2009 | .
G0314 | 2008-02-29 16:21 |  |  |  |  | Noxon-Hot Springs 230 kV line near Thompson Falls, MT | STUDY COMPLETED | GI | 2010-07-01 |  | 95 | 95 | NRIS | Hydro |  | FAS Study Issued 12/8/2009 | .
G0313 | 2008-02-07 14:57 |  |  | WA | Lewis | Lewis County PUD facilities near BPA's 115 kV Pe Ell Substation | STUDY COMPLETED | GI | 2011-12-01 |  | 128 | 128 | NRIS | Wind |  | FAS Study Issued 11/1/2010 Integration project. | .
L0286 | 2008-02-05 11:00 | Mt. Si | Puget Sound Energy, Inc. |  |  | Tanner 115 kV Tap | WITHDRAWN | LL | 2009-01-01 | [6 empty] | Project name formerly Tanner Tap | .
L0287 | 2008-02-05 11:00 | Novelty Substation | Puget Sound Energy, Inc. |  |  | Monroe-Sammamish 230 kV Line | WITHDRAWN | LL | 2009-09-01 | [7 empty] | .
G0309 | 2008-01-29 18:33 |  |  | WA | Klickitat & Yakima | New substation on BPA's 500 kV McNary-John Day line | WITHDRAWN | GI | 2011-10-01 |  | 200 | 200 | NRIS | Wind |  | Withdrawn on July 30, 2013 | .
G0310 | 2008-01-29 18:33 |  |  | WA | Klickitat & Yakima | New substation on BPA's 500 kV McNary-John Day line near Alderdale, Washington | WITHDRAWN | GI | 2011-10-01 |  | 200 | 200 | NRIS | Wind |  | Withdrawn on July 30, 2013 | .
G0311 | 2008-01-29 10:33 |  |  | OR | Klickitat & Yakima | New substation on BPA's 500 kV McNary-John Day line near Roosevelt and Alderdale, Washington | WITHDRAWN | GI | 2011-10-01 |  | 200 | 200 | NRIS | Wind |  | Withdrawn on July 30, 2013 | .
G0312 | 2008-01-29 10:33 |  |  | WA | Klickitat & Yakima` | New substation on BPA's 500 kV McNary-John Day line near Alderdale, Washington | WITHDRAWN | GI | 2011-10-01 |  | 200 | 200 | NRIS | Wind |  | Withdrawn on July 30, 2013 | .
G0308 | 2008-01-28 18:52 |  |  | OR | Gilliam | A 500 kV interconnection in Gilliam County, Oregon | WITHDRAWN | GI | 2012-10-01 |  | 250 | 250 | NRIS | Wind |  |  | .
G0307 | 2008-01-28 10:52 |  |  | OR | Gilliam | A 500 kV interconnection in Gilliam County, Oregon | WITHDRAWN | GI | 2011-10-01 |  | 250 | 250 | NRIS | Wind |  |  | .
G0306 | 2008-01-24 16:39 |  |  | OR | Harney Lake Crook Deschutes | BPA's Harney/Redmond transmission line near Harney. | WITHDRAWN | GI | 2009-12-01 |  | 600 | 600 | NRIS | Wind |  | Withdrawn by Customer on October 6, 2008. | .
G0305 | 2008-01-18 09:58 |  |  | OR | Union | BPA's 230 kV LaGrande Substation | WITHDRAWN | GI | 2010-01-15 |  | 200 | 200 | ERIS | Wind |  | Withdrawn on September 2, 2010 | .
L0285 | 2008-01-15 11:12 | McNary Substation | PacifiCorp |  |  | McNary Substation | WITHDRAWN | LL | 2010-12-01 | [7 empty] | .
G0304 | 2008-01-09 12:09 |  |  | OR | Harney | BPA's Harney/Redmond transmission line near Harney | WITHDRAWN | GI | 2009-12-01 |  | 416 | 416 | NRIS | Wind |  | Withdrawn by Customer on December 15, 2009. | .
L0284 | 2008-01-09 09:07 | Merchant Transmission Line | Green Pacific Highway, LLC |  |  | Merchant Transmission Line | WITHDRAWN | LL | 2009-07-01 |  | 0 | 0 |  |  |  |  | .
G0301 | 2008-01-08 16:00 |  |  | OR | Harney | BPA's Harney/Redmond transmission line near Harney | WITHDRAWN | GI | 2009-12-01 |  | 104 | 104 | NRIS | Wind |  | Withdrawn by Customer on December 13, 2012. | .
G0302 | 2008-01-08 16:00 |  |  | OR | Harney | BPA's Harney/Redmond transmission line near Harney | WITHDRAWN | GI | 2010-12-01 |  | 104 | 104 | NRIS | Wind |  | Withdrawn by Customer on October 4, 2010. | .
G0303 | 2008-01-08 16:00 |  |  | OR | Harney | BPA's Harney/Redmond transmission line near Harney | WITHDRAWN | GI | 2011-12-01 |  | 104 | 104 | NRIS | Wind |  | Withdrawn by Customer on October 4, 2010. | .
G0300 | 2007-12-18 08:47 |  |  | OR | Crook | At a point on BPA's Brasada-Harney 115 kV transmission line | STUDY COMPLETED | GI | 2010-10-30 |  | 104 | 104 | ERIS | Wind |  | FAS Study Issued 7/1/2009 | .
L0283 | 2007-12-17 10:50 | Kalispell Substation | Flathead Electric Cooperative, Inc. |  |  | BPA Kalispell Substation 115kV Bay #9 | WITHDRAWN | LL | 2009-06-01 | [7 empty] | .
G0331 | 2007-12-17 09:30 |  |  | OR | Harney | Harney-Brasada 115 kV line near Hampton Substation | STUDY COMPLETED | GI | 2009-07-01 |  | 8 | 8 | ERIS | Wind |  | FAS Study Issued March 29, 2008 | .
G0299 | 2007-11-19 17:10 |  |  | WA | Columbia | BPA’s Lower Granite/Little Goose 500 kV line | WITHDRAWN | GI | 2010-12-15 |  | 300 | 300 | ERIS | Wind |  | Withdrawn by Customer on March 11, 2008 | .
G0298 | 2007-11-19 17:03 |  |  | WA | Columbia | Little Goose 500 kV Substation | WITHDRAWN | GI | 2009-12-15 |  | 300 | 300 | ERIS | Wind |  | Withdrawn by Customer on March 11, 2008 | .
G0297 | 2007-11-01 11:46 | Biglow Canyon Wind Farm Addition | Portland General Electric Company | OR | Sherman |  | ENERGIZED | GI | 2009-10-01 |  | 50 | 50 | ERIS | Wind |  | on-line May 2010 (combined with Phase 3 of G099 for 125 MW) | .
G0296 | 2007-10-29 08:45 |  |  | OR | Morrow | BPA's McNary-Roundup 230 kV line | WITHDRAWN | GI | 2012-10-01 |  | 300 | 300 | NRIS | Wind |  | Withdrawn on November 17, 2008 | .
G0295 | 2007-10-25 23:06 |  |  | WA | Columbia & Garfield | Central Ferry Substation | STUDY COMPLETED | GI | 2011-12-31 |  | 250 | 250 | NRIS | Wind |  | LGIA in Progress | .
G0294 | 2007-10-25 16:06 |  |  | WA | Columbia & Garfield | Central Ferry Substation | STUDY COMPLETED | GI | 2011-12-31 |  | 250 | 250 | NRIS | Wind |  | LGIA in progress | .
G0293 | 2007-10-24 13:50 |  |  |  |  | BPA's LaGrande 230 kV Substation | WITHDRAWN | GI | 2015-10-01 |  | 200 | 200 | NRIS | Wind |  | Withdrawn on July 31, 2013 | .
G0292 | 2007-10-17 09:30 |  |  | WA | Benton | Prosser 115 kV Substation | WITHDRAWN | GI | 2011-07-01 |  | 180 | 180 | ERIS | Wind |  | Withdrawn on November 23, 2009 | .
G0291 | 2007-10-15 09:48 | Shepherds Flat Wind Farm addition | Caithness Shepherds Flat, LLC | OR | Gilliam | Slatt 500 kV Substation | ENERGIZED | GI | 2009-07-01 |  | 96 | 96 | NRIS | Wind |  | on-line June 2012 | .
L0282 | 2007-09-26 11:29 | Cowlitz Substation | Tacoma Power |  |  | Reterminate BPA's South Tacoma-Cowlitz 230kV Line | WITHDRAWN | LL | 2010-01-01 | [6 empty] | BPA's S.Tacoma 230kV line to be disconnected from Cowlitz and connect directly to Tacoma's Southwest #4 line. | .
L0281 | 2007-09-14 16:04 | Grant Rocky Ford | Public Utility District No. 2 of Grant County, Washington |  |  | Columbia 115/230kV Substation | ENERGIZED | LL | 2010-01-01 | [7 empty] | .
G0290 | 2007-09-06 09:19 |  |  | OR | Wasco | Wasco Co., Oregon | WITHDRAWN | GI | 2011-10-01 |  | 75 | 75 | NRIS | Wind |  | Withdrawn by Customer on November 17, 2008 | .
G0289 | 2007-08-29 02:08 |  |  | WA | Grays Harbor | Satsop 23 kV Substation | STUDY COMPLETED | GI | 2010-12-31 |  | 628 | 659 | NRIS | Combined cycle |  | FAS Study Issued 7/2/2010 | .
G0288 | 2007-08-24 09:09 |  |  | WA | Pacific | One mile from Naselle 115 kV Substation | WITHDRAWN | GI | 2011-07-01 |  | 82 | 82 | ERIS | Wind |  | Withdrawn on December 12, 2011 | .
L0279 | 2007-08-23 09:24 | Victor Transformer | Fall River Rural Electric Cooperative, Inc. |  |  | Victor Substation | ENERGIZED | LL | 2010-01-01 | [7 empty] | .
L0278 | 2007-08-22 10:05 | North Loop | City of Idaho Falls |  |  | Westside Substation | ENERGIZED | LL | 2010-01-01 | [7 empty] | .
G0287 | 2007-08-17 08:59 |  |  | WA | Klickitat | Midway-N. Bonneville 230 kV line north of Goldendale, Wa. | WITHDRAWN | GI | 2010-09-01 |  | 200 | 200 | ERIS | Wind |  | Withdrawn by Customer on July 8, 2008. | .
G0284 | 2007-08-13 10:51 | Lower Snake Phase 1 | Puget Sound Energy, Inc. | WA | Columbia | Central Ferry Substation | ENERGIZED | GI | 2011-12-31 |  | 250 | 250 | NRIS | Wind |  | Phase I for 250 MW; on-line January 2010 | .
G0285 | 2007-08-13 10:51 | Lower Snake Phase 1 | Puget Sound Energy, Inc. | WA | Columbia & Garfield | Central Ferry Substation | ENERGIZED | GI | 2011-12-31 |  | 250 | 250 | NRIS | Wind |  | Phase I for 93 MW; on-line January 2012 | .
G0286 | 2007-08-13 10:51 | Tucannon River Wind Farm | Portland General Electric Company | WA | Columbia & Garfield | Central Ferry Substation | ENERGIZED | GI | 2011-12-31 |  | 250 | 250 | NRIS | Wind |  | Phase 2 for 267 MW acquired by PGE; on-line scheduled for December 2014. | .
G0283 | 2007-08-10 10:25 |  |  |  |  | DeMoss Springs | WITHDRAWN | GI | 2009-04-01 |  | 40 | 40 | ERIS | Wind |  | Withdrawn by Customer on June 24, 2011. | .
G0282 | 2007-08-10 09:11 |  |  |  |  | Chandler 115 kV line | WITHDRAWN | GI | 2011-10-01 |  | 100 | 100 | NRIS | Wind |  | Withdrawn on November 29, 2012 | .
L0277 | 2007-08-03 10:05 | Oceanside | Tillamook People's Utility District |  |  | Tillamook Substation | ENERGIZED | LL | 2010-01-01 | [7 empty] | .
L0276 | 2007-07-25 09:28 | Network Connection, 230 kV loop line | Puget Sound Energy, Inc. |  |  | St Clair or Spurgeon Creek Substation | ENERGIZED | LL | 2008-08-01 | [6 empty] | Energized 6/11/14 | .
G0279 | 2007-07-17 14:15 |  |  | OR | Sherman | To be determined | WITHDRAWN | GI | 2010-08-01 |  | 105 | 105 | NRIS | Wind |  |  | .
G0280 | 2007-07-17 14:15 |  |  |  |  | To be determined | WITHDRAWN | GI | 2011-07-01 |  | 242 | 242 | NRIS | Wind |  |  | .
G0281 | 2007-07-17 09:00 |  |  | WA | Walla Walla | Lower Monumental-McNary 500kV line in vicinity of Wallula, WA. | WITHDRAWN | GI | 2013-06-01 |  | 760 | 760 | NRIS | Combined cycle |  | Withdrawn by Customer on February 12, 2008. | .
G0278 | 2007-07-12 08:56 |  |  | WA | Klickitat | Midway-North Bonneville 230kV Line | WITHDRAWN | GI | 2009-12-01 |  | 75 | 75 | ERIS | Wind |  | Withdrawn by Customer on March 5, 2009. | .
G0277 | 2007-07-10 16:25 |  |  |  |  | to be determined | WITHDRAWN | GI | 2010-12-31 |  | 250 | 250 | ERIS | Wind |  | Withdrawn on July 30, 2013 | .
G0276 | 2007-07-06 09:55 |  |  | WA | Douglas | Grand Coulee-Columbia 230kV Line | WITHDRAWN | GI | 2010-12-01 |  | 300 | 300 | NRIS | Wind |  | Withdrawn on January 27, 2009 | .
L0275 | 2007-07-06 07:05 | Merchant Transmission Line | Green Pacific Highway, LLC |  |  | Allston Substation | WITHDRAWN | LL | 2009-07-01 | [7 empty] | .
G0275 | 2007-07-03 16:44 |  |  |  |  | 20Miles West of Milton-Freewater | WITHDRAWN | GI | 2009-11-01 |  | 100 | 100 | NRIS | Wind |  | Withdrawn on January 7, 2013 | .
G0274 | 2007-06-29 10:00 | Hopkins Ridge Addition | Puget Sound Energy, Inc. | WA | Columbia | Tucannon River Switching Station | ENERGIZED | GI | 2008-08-01 |  | 7 | 7 | NRIS | Wind |  | on-line August 2008 | .
G0273 | 2007-06-14 09:36 |  |  | WA | Kittitas | Vantage Substation | WITHDRAWN | GI | 2008-09-01 |  | 104 | 104 | ERIS | Wind |  | Witrhdrawn by Customer on July 18, 2008. | .
L0273 | 2007-05-25 09:16 | Beverly Park Expansion | Public Utility District No. 1 of Snohomish County |  |  | Snohomish Substation | WITHDRAWN | LL | 2008-10-01 |  | 178 | 178 |  |  |  |  | .
L0272 | 2007-05-17 09:20 | Columbia Substation | Public Utility District No. 1 of Douglas County |  |  | BPA's Columbia Substation | WITHDRAWN | LL | 2008-06-01 |  | 5 | 5 |  |  |  |  | .
G0271 | 2007-05-04 10:00 |  |  | WA | Yakima | BPA's Wautoma 230 kV Line | WITHDRAWN | GI | 2009-09-01 |  | 300 | 300 | ERIS | Wind |  | Withdrawn on May 30, 2008 | .
G0272 | 2007-05-04 10:00 |  |  | WA | Yakima | BPA's Wautoma 230kV Line | WITHDRAWN | GI | 2008-08-01 |  | 300 | 300 | ERIS | Wind |  | Withdrawn on May 30, 2008. | .
L0271 | 2007-03-29 11:26 | Brothers Tap Upgrade | Midstate Electric Cooperative, Inc. |  |  | Christmas Valley 115 kV | WITHDRAWN | LL | 2008-05-01 |  | 14 | 14 |  |  |  |  | .
G0263 | 2007-03-08 17:03 |  |  | OR | Sherman | N/A | WITHDRAWN | GI | 2009-11-01 |  | 200 | 200 | NRIS | Wind |  | Withdrawn August 28, 2007 | .
G0262 | 2007-03-07 10:21 |  |  | OR | Wasco | Big Eddy-DeMoss 115 kV Line | WITHDRAWN | GI | 2007-12-01 |  | 3 | 3 | Energy | Wind |  | Withdrawn September 10, 2007 | .
G0261 | 2007-02-22 17:06 |  |  | WA | Klickitat | Ashe-Marion 500 kV | WITHDRAWN | GI | 2010-09-01 |  | 1200 | 1200 | ERIS | Wind |  | Withdrawn November 8, 2007 | .
L0259 | 2007-02-06 09:19 | Wahkiakum PUD 115kV Tap | Public Utility District No. 1 of Wahkiakum County |  |  | Naselle Tap to Allston-Astoria #1 115kV | ENERGIZED | LL | 2009-02-01 |  | 0 | 0 |  |  |  | Studies complete | .
G0258 | 2007-02-02 09:56 |  |  | WA | Cowlitz | Longview Substation | WITHDRAWN | GI | 2012-01-01 |  | 320 | 375 | ERIS | Combined cycle |  | Withdrawn on September 6, 2013. | .
G0255 | 2007-01-25 12:26 | Willow Creek and Horn Butte | Invenergy Wind Development, LLC | OR | Gilliam | Boardman-Alkali 115 kV Line | ENERGIZED | GI | 2008-05-01 |  | 72 | 72 | ERIS | Wind |  | LGIA executed for Phase 1, 72 MW; on-line November 2008. | .
L0260 | 2007-01-18 16:49 | Midstate LaPine Addition | Midstate Electric Cooperative, Inc. |  |  | LaPine Substation | ENERGIZED | LL | 2008-12-01 |  | 163 | 163 |  |  |  |  | .
L0257 | 2007-01-18 08:28 | West Wendover | Wells Rural Electric Company |  |  | West Wendover POD | ENERGIZED | LL | 2008-01-01 |  | 0 | 0 |  |  |  |  | .
L0256 | 2007-01-12 13:33 | Targhee Substation | Fall River Rural Electric Cooperative, Inc. |  |  | Targhee Substation | ENERGIZED | LL | 2008-01-01 |  | 0 | 0 |  |  |  |  | .
G0252 | 2006-12-19 08:54 |  |  | WA | Yakima | Wautoma 500 kV Substation | WITHDRAWN | GI | 2008-09-01 |  | 350 | 350 | ERIS | Wind |  | Withdrawn by Customer on February 29, 2008. | .
G0253 | 2006-12-19 08:54 |  |  | WA | Klickitat | Horse Heaven Substation 115 kV | WITHDRAWN | GI | 2008-09-01 |  | 100 | 100 | ERIS | Wind |  | Withdrawn on July 18, 2007 | .
G0251 | 2006-12-14 09:15 |  |  | WA |  | New substation on BPA's 500 kV McNary-John Day line | STUDY COMPLETED | GI | 2010-09-01 |  | 700 | 700 | ERIS | Wind |  | FAS Study Issued 5/27/2009 | .
L0250 | 2006-12-13 09:25 | Pacific Ethnanol Tap | United Electric Co-op, Inc. |  |  | Unity-West Burley 138 kV | ENERGIZED | LL | 2008-12-01 |  | 0 | 0 |  |  |  |  | .
G0249 | 2006-12-07 05:54 |  |  | WA | Klickitat | Midway-Big Eddy 230 kV | WITHDRAWN | GI | 2008-12-01 |  | 75 | 75 | Energy | Wind |  | Withdrawn on July 11, 2008 | .
L0244 | 2006-11-01 08:11 | PSE Alderton Substation | Puget Sound Energy, Inc. |  |  | Olympia-White River 230 kV | WITHDRAWN | LL | 2008-11-01 |  | 0 | 0 |  |  |  | Generation Facility Location Pierce County, WA | .
G0248 | 2006-11-01 04:00 |  |  | ID | Cassia | Idahome Substation | WITHDRAWN | GI | 2007-12-31 |  | 20 | 20 | Energy | Wind |  | Withdrawn on March 31, 2009 | .
G0247 | 2006-11-01 03:58 |  |  | ID | Cassia | Idahome Substation | WITHDRAWN | GI | 2007-12-31 |  | 20 | 20 | Energy | Wind |  | Withdrawn on March 31, 2009 | .
G0246 | 2006-11-01 03:52 |  |  | ID | Cassia | Idahome Substation | WITHDRAWN | GI | 2007-12-31 |  | 20 | 20 | Energy | Wind |  |  | .
G0245 | 2006-11-01 03:49 |  |  | ID | Cassia | Idahome Substation | WITHDRAWN | GI | 2007-12-31 |  | 20 | 20 | Energy | Wind |  | Withdrawn on March 31, 2009 | .
L0243 | 2006-10-26 09:12 | Canyon Substation | Tacoma Power |  |  | South Tacoma Substation | ENERGIZED | LL | 2008-10-01 |  | 0 | 0 |  |  |  |  | .
G0237 | 2006-10-10 16:33 |  |  | OR | Sherman | New Substation near John Day 500kV Substation | STUDY COMPLETED | GI | 2009-11-01 |  | 100 | 100 | NRIS | Wind |  | FAS Study Issued 7/2/2008 | .
G0238 | 2006-10-10 16:01 |  |  | OR | Gilliam County | Slatt Substation | STUDY COMPLETED | GI | 2010-09-01 |  | 202 | 202 | ERIS | Wind |  | FAS Study Issued 7/20/2008 | .
G0239 | 2006-10-10 16:01 |  |  | OR | Gilliam County | Slatt Substation | STUDY COMPLETED | GI | 2010-07-01 |  | 202 | 202 | ERIS | Wind |  | FAS Study Issued 7/20/2008 | .
G0240 | 2006-10-10 16:01 |  |  | OR | Morrow | Boardman Substation | WITHDRAWN | GI | 2010-07-01 |  | 202 | 202 | NRIS | Wind |  | Withdrawn on August 31, 2007 | .
G0241 | 2006-10-10 16:01 |  |  | OR | Morrow | Boardman Substation | WITHDRAWN | GI | 2010-09-01 |  | 202 | 202 | NRIS | Wind |  | Withdrawn on August 31, 2007 | .
G0242 | 2006-10-10 16:01 |  |  | WA | Klickitat County | Horse Heaven-Harvalum 230 kV line | STUDY COMPLETED | GI | 2009-07-01 |  | 101 | 101 | NRIS | Wind |  | FAS Study Issued 4/22/2009 | .
L0236 | 2006-10-06 02:38 | Clatskanie Tap | Clatskanie People's Utility District |  |  | Clatskanie Tap | ENERGIZED | LL | 2007-11-01 |  | 0 | 0 |  |  |  | Clatskanie PUD | .
G0235 | 2006-09-25 09:08 |  |  | OR | Sherman | New Substation near John Day 500kV Substation | STUDY COMPLETED | GI | 2009-11-01 |  | 200 | 200 | NRIS | Wind |  | FAS Study Issued 7/2/2008 | .
G0234 | 2006-09-05 12:39 |  |  | WA |  | Station Z 230kV | WITHDRAWN | GI | 2007-12-01 |  | 300 | 300 | Energy | Wind |  | Withdrawn by Customer on July 8, 2008 | .
G0233 | 2006-09-05 12:38 |  |  | WA |  | Rock Creek Substation | STUDY COMPLETED | GI | 2007-12-01 |  | 150 | 150 | Energy | Wind |  | FAS Study Issued 9/27/2008; NEPA complete 10/1/2008 | .
G0232 | 2006-08-25 15:41 |  |  | OR | Wasco | Big Eddy-DeMoss 115 kV Line | WITHDRAWN | GI | 2007-10-01 |  | 10 | 10 | Energy | Wind |  | Withdrawn September 3, 2008 | .
L0231 | 2006-08-23 09:37 | Albany Lebanon | Consumers Power, Inc. |  |  | Tap on Albany-Lebanon 115 kV line | WITHDRAWN | LL | 2007-09-01 |  | 10 | 10 |  |  |  |  | .
L0274 | 2006-07-20 11:23 | Lauderdale Project | Public Utility District No. 1 of Kittitas County |  |  | Columbia-Ellensburg 115kV Line | ENERGIZED | LL | 2009-06-01 | [7 empty] | .
G0230 | 2006-07-19 15:58 |  |  | OR | Gilliam | Jones Canyon 230 kV Substation | WITHDRAWN | GI | 2008-06-01 |  | 200 | 200 | ERIS | Wind |  | Withdrawn July 17, 2007 | .
L0229 | 2006-06-28 09:00 | Bradwood Tap | PacifiCorp |  |  | Allston -Astoria #1 115 kV Line near Cathlamet Tap | WITHDRAWN | LL | 2008-01-01 |  | 40 | 40 |  |  |  |  | .
G0228 | 2006-06-27 09:33 |  |  | OR | Wasco County | Hood River-The Dalles 115 KV Transmission Line | WITHDRAWN | GI | 2008-06-30 |  | 80 | 80 | NRIS | Wind |  |  | .
L0227 | 2006-06-08 14:58 | Zephyr Heights | Public Utility District No. 1 of Benton County |  |  | Franklin-Badger Canyon 115 kV | ENERGIZED | LL | 2006-12-01 |  | 0 | 0 |  |  |  |  | .
G0226 | 2006-05-24 09:30 | Leaning Juniper II | Iberdrola Renewables, LLC | OR | Gilliam County | Jones Canyon Substation | ENERGIZED | GI | 2009-06-01 | 2011-03-31 17:00 | 200 | 200 | ERIS | Wind |  | on-line April 2011 | .
G0225 | 2006-05-18 12:00 |  |  | WA | Douglas | to be determind | WITHDRAWN | GI | 2008-06-01 |  | 127 | 127 | NRIS | Wind |  | Withdrawn January 11, 2006 | .
G0224 | 2006-05-09 09:57 | Big Horn 2 | Iberdrola Renewables, LLC | WA |  | Spring Creek Substation | ENERGIZED | GI | 2007-06-01 |  | 50 | 50 | NRIS | Wind |  | on-line September 2010 | .
G0223 | 2006-04-19 15:56 | Hay Canyon/Star Point | Iberdrola Renewables, LLC | OR | Sherman | John Day Substation | ENERGIZED | GI | 2008-12-01 | 2008-11-30 16:00 | 201 | 201 | NRIS | Wind |  | Hay Canyon on-line December 2008 for 101 MW; Star Point on-line January 2010. Two LGIAs provided. | .
G0222 | 2006-03-24 10:17 | Windy Flats -Dooley Wind | Windy Point Partners, LLC | WA | Klickitat | Rock Creek Substation | ENERGIZED | GI | 2008-12-31 | 2009-10-31 17:00 | 250 | 250 | NRIS | Wind |  | on-line November 2009, combined with G0122, in part | .
L0254 | 2006-03-13 10:39 | Joyce Substation | Public Utility District No. 1 of Clallam County |  |  | Port Angeles-Sappho 115 kV Line | ENERGIZED | LL | 2008-09-30 |  | 9 | 9 |  |  |  | Studies complete | .
G0214 | 2006-01-05 11:59 |  |  | OR | Deschutes County | Lapine Substation 230kV | STUDY COMPLETED | GI | 2009-09-01 |  | 140 | 140 | ERIS | Geothermal |  | FAS Study Issued 9/11/2007 | .
G0213 | 2005-12-21 10:12 |  |  | WA | Cowlitz | Longview Substation 230kV | WITHDRAWN | GI | 2012-01-01 |  | 600 | 600 | NRIS | Combined cycle |  |  | .
L0219 | 2005-11-17 | Sunset Substation | Portland General Electric Company |  |  | Keeler Substation | ENERGIZED | LL | 2007-01-01 |  | 0 | 0 |  |  |  | Studies complete | .
G0212 | 2005-11-15 14:25 |  |  | WA | Kittitas | To Be determined | WITHDRAWN | GI | 2008-01-01 |  | 100 | 100 | NRIS & ERIS | Wind |  | Withdrawn by Customer on January 23, 2006. | .
G0211 | 2005-11-14 15:38 |  |  | WA | Douglas | to be determined | WITHDRAWN | GI | 2007-10-01 |  | 127 | 127 | NRIS | Wind |  |  | .
L0221 | 2005-11-01 | Pacific West Coast Cable | Sea Breeze Pacific West Coast Cable LP |  |  | Allston 500 kV | WITHDRAWN | LL | 2007-01-01 |  | 1600 | 1600 |  |  |  | Sea Breeze Pacific West Coast Cable, LP - failed to execute Facility Study | .
L0216 | 2005-09-22 | Vintage Valley | PacifiCorp |  |  | Midway-Mabton 230 | ENERGIZED | LL | 2007-04-01 |  | 0 | 0 |  |  |  | Pacificorps | .
L0217 | 2005-09-22 | Yew Ave. Sub | PacifiCorp |  |  | Redmond-Harney 115 | ENERGIZED | LL | 2006-12-01 |  | 0 | 0 |  |  |  | Pacificorps | .
L0218 | 2005-09-22 | Bradwood Tap | PacifiCorp |  |  | Cathlamet Tap-Cathlamet 115 | WITHDRAWN | LL | 2007-01-01 |  | 25 | 25 |  |  |  | Pacificorps | .
G0210 | 2005-09-15 09:50 |  |  | WA | Lincoln | Grand Coulee-Bell 115 kV line, north of Reardan, WA. | WITHDRAWN | GI | 2006-10-31 |  | 75 | 75 | ERIS | Wind |  | Withdrawn by Customer on May 1, 2008. | .
L0215 | 2005-08-23 | Montanore Mine | Flathead Electric Cooperative, Inc. |  |  | Libby-Noxon 230 | WITHDRAWN | LL | 2007-06-01 |  | 26 | 26 |  |  |  | Withdrawn by FEC on 4/2/2013. | .
G0209 | 2005-08-22 12:28 |  |  | WA | Grant | Grand Coulee-Rocky Ford 230 kV line | WITHDRAWN | GI | 2008-02-01 |  | 124 | 0 | ERIS | Hydro |  | Withdrawn May 21, 2008 | .
G0208 | 2005-07-18 13:12 | Tuolumne Wind (Windy Point 1) | Windy Point Partners, LLC | WA | Klickitat | Rock Creek Substation 230 kV | ENERGIZED | GI | 2007-03-01 | 2008-11-30 16:00 | 125 | 125 | NRIS | Wind |  | on-line December 2008(sold to Turlock Irrigation District, operated as Tuolumne Wind) | .
G0207 | 2005-06-29 09:46 |  |  | OR | Gilliam | John Day Substation 230 kV | WITHDRAWN | GI | 2006-07-15 |  | 200 | 200 | NRIS | Wind |  |  | .
G0206 | 2005-06-24 |  |  | OR | Union County | Lagrande Substation 230 kV | WITHDRAWN | GI | 2008-10-01 |  | 110 | 110 | ERIS | Wind |  |  | .
G0205 | 2005-06-16 09:37 | Grays Harbor 1 | Grays Harbor Energy, LLC | WA | Grays Harbor | Satsop Substation | ENERGIZED | GI | 2006-12-31 |  | 628 | 659 | NRIS | Combined cycle |  |  | .
G0203 | 2005-05-26 09:56 | Juniper Canyon 1 | Iberdrola Renewables, LLC | WA | Klickitat | Rock Creek | ENERGIZED | GI | 2007-12-01 | 2011-01-31 16:00 | 50 | 50 | NRIS | Wind |  | on-line February 2011 | .
G0204 | 2005-05-26 09:56 | Juniper Canyon 1 | Iberdrola Renewables, LLC | WA | Klickitat | Rock Creek Substation 230 kV. | ENERGIZED | GI | 2007-12-01 | 2011-01-31 16:00 | 100 | 100 | ERIS | Wind |  | on-line February 2012 | .
L0201 | 2005-04-04 09:38 | Juan de Fuca HVDC (Port Angeles) | Olympic Converter, LP - Don'T Use |  |  | Port Angeles 230 kV | STUDY COMPLETED | LL | 2007-05-01 |  | 550 | 550 |  |  |  | FAS complete. NEPA complete. | .
L0202 | 2005-04-04 09:38 | Juan de Fuca HVDC (Fairmount) | Olympic Converter, LP - Don'T Use |  |  | Fairmount 230 kV | STUDY COMPLETED | LL | 2008-05-01 |  | 550 | 550 |  |  |  | Sea Breeze Olympic Converter, LP | .
G135 | 2004-06-23 13:00 | White Creek Wind I | White Creek Wind I, LLC | WA | Klickitat | Rock Creek | ENERGIZED | GI | 2006-08-01 |  | 200 | 200 | Energy | Wind |  | on-line August 2007 | .
G132 | 2004-06-07 11:16 | Sea Breeze Olympic Ph 1 | Olympic Converter, LP - Don'T Use | WA | Clallam | Port Angeles 230 kV | WITHDRAWN | GI | 2007-05-01 |  | 330 | 330 | Energy |  |  |  | .
G133 | 2004-06-07 11:16 | Sea Breeze Olympic Ph 2 | Olympic Converter, LP - Don'T Use | WA | Clallam | Port Angeles 230 kV or Fairmount 230 kV | WITHDRAWN | GI | 2008-05-01 |  | 330 | 330 | Energy |  |  |  | .
G134 | 2004-06-07 11:16 | Sea Breeze Olympic Ph 3 | Olympic Converter, LP - Don'T Use | WA | Clallam | Port Angeles 230 kV or Fairmount 230 kV | WITHDRAWN | GI | 2010-05-01 |  | 330 | 330 | Energy |  |  |  | .
L0220 | 2004-05-17 | Monmouth Tap | City of Monmouth |  |  | Salem-Albeni 115 | ENERGIZED | LL | 2006-12-01 |  | 0 | 0 |  |  |  | Ciy of Monmouth | .
G131 | 2004-04-27 03:54 | Windtricity Ventures LLC | Windtricity Ventures | WA | Klickitat | Rock Creek 230kV | ENERGIZED | GI | 2007-09-15 |  | 150 | 150 | ERIS | Wind |  |  | .
G130 | 2004-04-02 10:28 | N/A | BPA Power Services | OR | Umatilla | McNary 230 kV | WITHDRAWN | GI | 2005-10-01 |  | 200 | 200 | Energy | Hydro |  | Withdrawn by Customer on December 1, 2008. | .
G129 | 2004-03-15 11:38 | River Road Generating Plant | Clark Public Utilities | WA | Clark | Interconnect between River Road Gen and BPA's Alcoa Sub | ENERGIZED | GI | 2005-07-01 |  | 240 | 240 | Energy | Gas peaking generation |  | Plant constructed and operational | .
G128 | 2004-03-08 09:53 | Summit/Westward | Summit Power Northwest Project, LLC | OR | Clatsop | BPA’s Driscoll 230kV switchyard | WITHDRAWN | GI | 2009-03-10 |  | 536 | 536 | Energy | Combined cycle |  | March 11, 2010: This is provisionally posted as 'Withdrawn' pending confirmation that OR EFSC has terminated the site certificate. | .
G127 | 2004-03-04 16:47 | Orion Energy LLC | Orion Energy, LLC | OR | Wasco | DeMoss Substation | WITHDRAWN | GI | 2006-12-01 |  | 450 | 450 | Energy | Wind |  |  | .
G126 | 2004-03-04 09:53 | Iberdrola Renewables Inc | Iberdrola Renewables, LLC | OR | Wasco | Big Eddy-Midway 230 kV line | ENERGIZED | GI | 2005-12-01 |  | 200 | 200 | Energy | Wind |  |  | .
G125 | 2004-03-01 19:17 | USGeothermal | US Geothermal, Inc. | ID | Cassia | At Bridge Substation, 34.5 kV ·or·138 kV bus | WITHDRAWN | GI | 2006-01-01 |  | 30 | 30 | Energy | Geothermal |  | on-line June 2006 | .
G123 | 2004-02-13 17:28 | NextEra Energy Resources | NextEra Energy Resources LLC | OR | Umatilla | At Stateline Wind Project 115 kV substation | WITHDRAWN | GI | 2005-01-01 |  | 17 | 17 | Energy | Wind |  |  | .
G124 | 2004-02-12 11:53 | Klondike 3 Wind | Klondike Wind Power III, LLC | OR | Wasco | Klondike Schoolhouse 230kV | ENERGIZED | GI | 2007-10-15 |  | 300 | 300 | ERIS | Wind |  | on-line October 2007, April 2008. | .
G122 | 2004-01-16 09:55 | Windy Point 1 Wind | Cannon Power Corporation | WA | Klickitat | Rock Creek 230kV | ENERGIZED | GI | 2009-07-01 |  | 125 | 125 | ERIS | Wind |  | on-line December 2008, as Tuolumue Wind. | .
G121 | 2003-12-05 11:06 | Willow Creek | Invenergy Wind Development, LLC | OR | Gilliam | McNary – Santiam 230 kV transmission line | WITHDRAWN | GI | 2005-12-01 |  | 180 | 180 | ERIS | Wind |  |  | .
G120 | 2003-11-24 11:06 | Invenergy Wind Development | Invenergy Wind Development, LLC | OR | Morrow | McNary – Santiam 230 kV transmission line | WITHDRAWN | GI | 2005-12-01 |  | 180 | 180 | Energy | Wind |  |  | .
G119 | 2003-09-17 17:00 | LifeLine Renewable Energy | Lifeline Renewable Energy, Inc. | OR | Morrow | BPA's McNary - Santiam 230kV Line | WITHDRAWN | GI | 2004-10-01 |  | 200 | 200 | ERIS | Wind |  |  | .
G118 | 2003-09-17 10:00 | Shepherds Flat | Caithness Shepherds Flat, LLC | OR | Gilliam | BPA's Slatt 500kV Substation | ENERGIZED | GI | 2009-10-01 |  | 750 | 750 | ERIS | Wind |  | on-line August 2011; June 2012 (Phase 2 & 3) | .
G117 | 2003-07-31 18:45 | NextEra Energy Resources | NextEra Energy Resources LLC | OR | wasco | Big Eddy Substation at 230kV. | WITHDRAWN | GI | 2004-12-31 |  | 100 | 100 | Energy | Wind |  | Withdrawn by Customer on January 30, 2004. | .
G116 | 2003-05-19 18:06 | Oregon Wind | Oregon Wind, LLC | OR | Wasco | Hood River-The Dalles 115 KV Line. | WITHDRAWN | GI | 2008-06-01 |  | 50 | 50 | ERIS | Wind |  | Withdrawn by Customer on January 8, 2009. | .
G115 | 2003-05-01 17:58 | Windland Inc | Windland, Inc. | ID | Cassia | Minidoka-Wendover 138 kV Line and/or East Hills 138 kV line | WITHDRAWN | GI | 2005-07-01 |  | 200 | 200 | Energy | Wind |  | Withdrawn by Customer on July 13, 2005. | .
G114 | 2003-01-22 19:44 | Horizon Wind Energy-WRidge | Wind Ridge Power Partners, LLC | WA | Kittitas | 230 kV Columbia - Covington line near Kittitas | WITHDRAWN | GI | 2004-09-15 |  | 252 | 252 | Energy | Wind |  |  | .
G113 | 2002-11-20 17:28 | RES North America LLC | RES North America | OR | Sherman | John Day Substation | WITHDRAWN | GI | 2004-06-01 |  | 250 | 250 | Energy | Wind |  |  | .
G111 | 2002-11-04 21:29 | Iberdrola Renewables Inc | Iberdrola Renewables, LLC | WA | klickitat | On Midway – Big Eddy 230 kV Line, 8 mi SW of Bickleton | WITHDRAWN | GI | 2004-03-01 |  | 200 | 200 | Energy | Wind |  | Withdrawn on December 17, 2003. | .
G112 | 2002-11-01 21:29 | Iberdrola Renewables Inc | Iberdrola Renewables, LLC | OR | Klickitat | On Hanford-JohnDay 500 kV Line, ~8 miles SW of Bickleton | WITHDRAWN | GI | 2004-03-01 |  | 200 | 200 | Energy | Wind |  |  | .
G110 | 2002-09-18 11:12 | Shepherds Flat Wind | Caithness Shepherds Flat, LLC | OR | Morrow | BPA Slatt 500 kV Substation | WITHDRAWN | GI | 2003-10-01 |  | 250 | 250 | ERIS | Wind |  |  | .
G109-01 | 2002-09-16 21:03 | Iberdrola Renewables Inc | Iberdrola Renewables, LLC | OR | Gilliam | Near Slatt 500kV Substation | WITHDRAWN | GI | 2003-12-30 |  | 100 | 100 | Energy | Wind |  | Withdrawn on December 19, 2003 by Customer. | .
G109 | 2002-07-24 09:52 | Combine Hills II | Eurus Combine Hills II LLC | OR | Umatilla | Walla Walla-Pendleton 69kV line | ENERGIZED | GI | 2009-12-10 |  | 63 | 63 | ERIS | Wind |  | on-line January 2010 | .
G106 | 2002-06-24 17:25 | Pebble Springs Wind Project | Iberdrola Renewables, LLC | OR | Gilliam | Jones Canyon substation on McNary Santiam line | ENERGIZED | GI | 2004-01-01 |  | 200 | 200 | Energy | Wind |  | on-line November 2008 | .
G107 | 2002-06-24 17:25 | Ib | Iberdrola Renewables, LLC |  | Gilliam | Near Slatt 500kV Substation | WITHDRAWN | GI | 2004-01-01 |  | 200 | 200 | Energy | Wind |  | Withdrawn per 12/16/2003 letter from Customer. | .
G108 | 2002-06-24 17:22 | Whistling Ridge | Whistling Ridge Energy, LLC | OR | Skamania | Midway-North Bonneville 230kV Transmission line | STUDY COMPLETED | GI | 2009-12-31 |  | 70 | 70 | ERIS | Wind |  | Restudy of plan-of-service, site permit approved; FAS issued 9/12/07 | .
G105 | 2002-06-20 23:16 | Desert Claim | enXco Northwest | WA | Kittitas | Covington-Columbia 230kV transmission line | STUDY COMPLETED | GI | 2009-10-01 |  | 159 | 159 | ERIS | Wind |  | New plan-of-serivce per customer request, site permits approved; FAS issued 2/4/13 | Awaiting Customer Permits To Complete NEPA Review
G102 | 2002-06-10 17:00 | Energy Northwest Inc | Energy Northwest Inc | WA | Benton | Mabton-Big Eddy 230kV line. | WITHDRAWN | GI | 2004-05-01 |  | 75 | 75 | Energy | Wind |  |  | .
G103 | 2002-06-07 08:30 | Telephone Flat | Calpine Energy Services, L.P. | OR | Klamath | BPA's 230kV Malin-Hilltop line | WITHDRAWN | GI | 2004-10-01 |  | 60 | 60 | Energy | Geothermal |  |  | .
G104 | 2002-06-07 08:30 | Fourmile Hill | Calpine Energy Services, L.P. | OR | Klamath | The BPA's 230kV Malin-Hilltop line | WITHDRAWN | GI | 2004-10-01 |  | 60 | 60 | Energy | Geothermal |  |  | .
G101 | 2002-06-03 21:10 | NextEra Energy Resources | NextEra Energy Resources LLC | WA | Garfield | 500 kV McNary-Lower Monumental line | WITHDRAWN | GI | 2003-09-01 |  | 300 | 300 | Energy | Wind |  |  | .
G100 | 2002-05-07 06:45 | Hopkins Ridge Wind | Puget Sound Energy, Inc. | WA | Columbia | At BPA Tucannon River 115 kV Substation on N. Lewiston - Walla Walla line | ENERGIZED | GI | 2003-12-01 |  | 150 | 150 | Energy | Wind |  | on-line December 2005 | .
G99 | 2002-04-05 14:12 | Biglow Canyon Wind | Portland General Electric Company | OR | Sherman County | Biglow Canyon | ENERGIZED | GI | 2008-12-01 |  | 400 | 400 | ERIS | Wind |  | on-line Phase 1 October 2007 for 126 MW, Phase 2 June 2009 for 149 MW, Phase 3 May 2010 for 125 MW | .
G98-01 | 2002-04-05 09:20 | Summit Ridge Project | Seawest Windpower, Inc. | OR | Wasco | Big Eddy–DeMoss 115 kV line 8-9 miles east of Big Eddy | WITHDRAWN | GI | 2003-10-31 |  | 75 | 75 | Energy | Wind |  | Withdrawn by Customer | .
G98-02 | 2002-04-05 09:20 | White Creek | Harvest Wind Project | OR | Klickitat | Rock Creek 230kV | ENERGIZED | GI | 2009-10-01 |  | 100 | 100 | ERIS | Wind |  | on line January 2010 | .
G97 | 2002-03-19 13:50 | Anderson Ranch Wind Farm | NextEra Energy Resources LLC | OR | Gilliam | Slatt - John Day 500 kV | WITHDRAWN | GI | 2002-09-01 |  | 100 | 100 | Energy | Wind |  | Withdrawn by Customer | .
G98 | 2002-03-19 13:50 | The Dalles Wind Farm | NextEra Energy Resources LLC | OR | Wasco | Big Eddy-Redmond 230 kV line | WITHDRAWN | GI | 2003-09-01 |  | 350 | 350 | Energy | Wind |  | Withdrawn by Customer | .
G96 | 2002-03-08 16:57 | Klondike 2 Wind | Klondike Wind Power II, LLC | OR | Wasco | BPA's DeMoss 115kV Substation | ENERGIZED | GI | 2003-09-01 |  | 50 | 50 | Energy | Wind |  | on-line June 2005 for 76 MW (combined with G82) | .
G95 | 2002-02-15 13:18 | Arlington Wind_Wheatfield Wind | EDP Renewables North America LLC | OR | Gilliam | Jones Canyon Substation | ENERGIZED | GI | 2008-10-01 |  | 200 | 200 | ERIS | Wind |  | on-line November 2008 for 103 MW and February 2009 for 93 MW (LGIA split) | .
G94 | 2002-02-08 13:00 | Peoples Energy Resources | Peoples Energy Resources Corporation | OR | Klamath | BPA’s 500 kV Grizzly – Malin transmission line approximately 30 miles north of Malin Substation | WITHDRAWN | GI | 2005-02-01 |  | 600 | 600 | Energy | Geothermal |  |  | .
G93 | 2002-01-09 13:15 | Duke Energy NA | Duke Energy North America, LLC | OR | Linn | Between Santiam and Wren Tap at 230kV Line. | WITHDRAWN | GI | 2005-01-01 |  | 600 | 600 | Energy | Combined cycle |  |  | .
G92 | 2002-01-04 10:45 | Plymouth Energy | Plymouth Energy, LLC | WA | Benton | BPA’s McNary - John Day 500kV Line in the vicinity of Plymouth, WA. | WITHDRAWN | GI | 2004-04-27 |  | 306 | 306 | Energy | Combined cycle |  |  | .
G91 | 2001-12-20 11:01 | Duke Energy NA | Duke Energy North America, LLC | OR | Deschutes | BPA's 230 kV transmission line between Redmond and Pilot Butte substations in Deschutes Co., OR | WITHDRAWN | GI | 2005-06-01 |  | 640 | 640 | Energy | Combined cycle |  |  | .
G90 | 2001-11-29 10:39 | Cal Geo | Cal Geo Company | CA | modoc | Cedarville Junction Substation | WITHDRAWN | GI | 2003-07-01 |  | 30 | 30 | Energy | Geothermal |  |  | .
G89 | 2001-11-23 14:32 | Enron Power Marketing | Enron Power Marketing, Inc. | WA | king | Maple Valley 230 kV Substation | WITHDRAWN | GI | 2004-01-01 |  | 300 | 300 | Energy | Combined cycle |  | Withdrawn by Customer | .
G88 | 2001-11-21 10:00 | NextEra Energy Resources | NextEra Energy Resources LLC | WA | Walla Walla | Sacajawea Substation | WITHDRAWN | GI | 2002-09-01 |  | 150 | 150 | Energy | Wind |  | Withdrawn by Customer | .
G87 | 2001-10-31 10:26 | Peoples Energy Resources | Peoples Energy Resources Corporation | OR | Klamath | 500 kV Grizzly – Malin line near Malin Substation | WITHDRAWN | GI | 2005-03-01 |  | 1200 | 1200 | Energy | Combined cycle |  | Withdrawn by Customer | .
G84 | 2001-10-29 10:43 | Touchet Wind Farm | Winds Over Washington Energy Group | WA | Walla Walla | 500 kV Lower Monumental - McNary line near Wallula, WA | WITHDRAWN | GI | 2004-01-01 |  | 150 | 150 | Energy | Wind |  | Withdrawn by Customer | .
G85 | 2001-10-29 10:43 | Windy Ridge Wind Farm | Winds Over Washington Energy Group | WA | Garfield | BPA's Lower Monumental Substation | WITHDRAWN | GI | 2004-01-01 |  | 150 | 150 | Energy | Wind |  | Withdrawn by Customer | .
G86 | 2001-10-29 10:43 | Eureka Flats Wind Farm | Winds Over Washington Energy Group | WA | Whatcom | 500 kV Lower Monumental McNary line | WITHDRAWN | GI | 2004-01-01 |  | 150 | 150 | Energy | Wind |  | Withdrawn by Customer | .
G83 | 2001-10-24 08:05 | Sempra Generation | Sempra Generation, LLC | OR | Marion | BPA's Pearl - Marion 500 kV line in the vicinity of Aurora, OR | WITHDRAWN | GI | 2005-06-01 |  | 612 | 612 | Energy | Combined cycle |  | Withdrawn by Customer | .
G82 | 2001-10-18 13:33 | Klondike 1 Wind | Northwestern Wind Power, LLC | OR | Wasco | Interconnection is BPA's De Moss 115 kV Substation | ENERGIZED | GI | 2002-09-01 |  | 26 | 26 | Energy | Wind |  | combined with G96 | .
G81 | 2001-10-10 18:39 | Clipper WindPower | Clipper Windpower Development, Inc. | OR | Curry | BPA's 115kV transmission line near Langlois Substation | WITHDRAWN | GI | 2002-06-01 |  | 53 | 53 | Energy | Wind |  | Withdrawn by Customer | .
G80 | 2001-09-28 11:54 | Kittitas Valley Wind | Sagebrush Power Partners, LLC | WA | Kittitas County | Columbia Covington 230kV line (Bettas Road Substation) | ENERGIZED | GI | 2009-12-31 |  | 108 | 108 | ERIS | Wind |  | on-line 12/20/2010. Request reduced to 101 MW | .
G79 | 2001-09-27 16:34 | Horizon Wind Energy-WRidge | Wind Ridge Power Partners, LLC | WA | Asotin | 115 kV North Lewiston-Walla Walla line near Clarkston WA | WITHDRAWN | GI | 2003-06-15 |  | 200 | 200 | Energy | Wind |  | Withdrawn by Customer | .
G78 | 2001-09-27 16:32 | Horizon Wind Energy-Wheat | Wheat Field Power Partners, LLC | OR | Wasco | BPA's Big Eddy - Maupin 230kV transmission line in the vicinity of Dufur, Oregon | WITHDRAWN | GI | 2005-10-01 |  | 195 | 195 | Energy | Wind |  | Withdrawn on July 11, 2003 | .
G77 | 2001-09-21 17:49 | 300MW Lower Monumental-Starbuck | RES North America | WA | Columbia | Lower Monumental-Starbuck 500 kV line. | WITHDRAWN | GI | 2004-06-01 |  | 300 | 300 | Energy | Wind |  | Withdrawn by Customer | .
G76 | 2001-09-19 17:49 | 200MW North Lewiston-Walla Walla 2 | RES North America | WA | Walla Walla | 115 kV North Lewiston-Walla Walla line | WITHDRAWN | GI | 2002-12-01 |  | 200 | 200 | Energy | Wind |  | Withdrawn by Customer | .
G75 | 2001-09-19 14:02 | 200MW North Lewiston-Walla Walla 1 | RES North America | WA | Walla Walla | 115 kV North Lewiston-Walla Walla line | WITHDRAWN | GI | 2002-12-01 |  | 200 | 200 | Energy | Wind |  | Withdrawn by Customer | .
G74 | 2001-09-19 09:20 | Cielo Wind Power | Cielo Wind Power | WA | Klickitat | Big Eddy 230 kV line South of Goldendale. | WITHDRAWN | GI | 2003-08-01 |  | 80 | 80 | Energy | Wind |  | Withdrawn by Customer | .
G73-01 | 2001-09-18 11:06 | Nine Canyon 2 | Energy Northwest | WA | Benton | 115 kV McNary-Badger Canyon line (Nine Canyon Substation) | ENERGIZED | GI | 2007-11-01 |  | 32 | 32 | ERIS | Wind |  | on-line January 2008; reduced request from 100 MW | .
G73 | 2001-09-12 10:03 | OR-CAL Power | Or-Cal Power, Inc. | OR | Deschutes | LaPine Substation | WITHDRAWN | GI | 2003-03-01 |  | 97 | 97 | Energy | Geothermal |  | Withdrawn by Customer | .
G72 | 2001-08-20 17:19 | AES Pacific Inc | AES Pacific Inc | WA | Walla Walla | BPA's Proposed Wallula 500 kV Substation | WITHDRAWN | GI | 2002-06-01 |  | 300 | 300 | Energy | Combined cycle |  | Withdrawn by Customer | .
G71-01 | 2001-08-20 09:30 | GNA Energy | GNA Energy, LLC | WA | Klickitat | BPA's Harvalum 230 kV Substation in Goldendal WA. | WITHDRAWN | GI | 2003-01-15 |  | 100 | 100 | Energy | Combined cycle |  | Withdrawn on December 3, 2010 | .
G71 | 2001-08-17 15:50 | AES Pacific Inc | AES Pacific Inc | CA | Modoc | BPA's Canby 230 kV Substation in Modoc County, CA. | WITHDRAWN | GI | 2002-06-01 |  | 300 | 300 | Energy | Biomass |  | Withdrawn by Customer | .
G70-01 | 2001-08-14 13:47 | 01 37MW Connell | Effective Energy Corporation | WA | Franklin | BPA's Connell Substation | WITHDRAWN | GI | 2002-06-01 |  | 37 | 37 | Energy | Combined cycle |  | Withdrawn on December 3, 2010 | .
G70-02 | 2001-08-14 13:47 | 02 37MW Franklin PUD,Franklin Riverview | Effective Energy Corporation | WA | Franklin | Franklin PUD's Oregon Street Substation | WITHDRAWN | GI | 2002-06-01 |  | 37 | 37 | Energy | Combined cycle |  | Request submitted as 36.1 MW | .
G70 | 2001-07-24 10:32 | Frederickson Power LP | Frederickson Power, LP | WA | Pierce | South Tacoma Substation. | WITHDRAWN | GI | 2002-10-01 |  | 300 | 300 | Energy | Combined cycle |  | Withdrawn by Customer | .
G69 | 2001-07-12 15:37 | National Energy and Gas Tx | National Energy & Gas Transmission, Inc. | OR | Morrow | Coyote Springs loop on the McNary/Slatt 500 kV line | WITHDRAWN | GI | 2005-02-01 |  | 620 | 620 | Energy | Combined cycle |  | Withdrawn by Customer | .
G68 | 2001-07-05 09:56 | Clatskanie | Clatskanie People's Utility District | OR | Clatsop | The Wauna Substation | WITHDRAWN | GI | 2001-11-15 |  | 65 | 65 | Energy |  |  | Withdrawn by Customer | .
G66 | 2001-06-29 12:07 | 100MW Harvalum | ABB Equity Ventures Inc | WA | Klickitat | Harvalum Substation | WITHDRAWN | GI | 2003-09-01 |  | 100 | 100 | Energy | Wind |  | Withdrawn by Customer | .
G67 | 2001-06-29 12:07 | 100MW Midway-Bonneville | ABB Equity Ventures Inc | OR | Klickitat | Midway-Bonneville 230 kV line near Goldendale WA | WITHDRAWN | GI | 2003-09-01 |  | 100 | 100 | Energy | Wind |  | Withdrawn by Customer | .
G65 | 2001-06-22 07:12 | 310MW Cardwell | Cogentrix Energy, Inc. | WA | Cowlitz | Cardwell Substation | WITHDRAWN | GI | 2003-06-01 |  | 310 | 310 | Energy | Combined cycle |  | Withdrawn by Customer | .
G64 | 2001-06-21 08:15 | US Elect Power Corp | US Electric Power Corporation | WA | Whatcom | Interconnection at 230 kV Customer Substation | WITHDRAWN | GI | 2004-03-01 |  | 349 | 349 | Energy | Combined cycle |  | Withdrawn by Customer | .
G62 | 2001-06-07 09:45 | 30MW Walla Walla-Pendleton | FPL Energy Power Marketing Inc | OR | Umatilla | Walla Walla-Pendleton 69 kV line near Duroc | WITHDRAWN | GI | 2002-09-01 |  | 30 | 30 | Energy | Wind |  | Withdrawn by Customer | .
G63 | 2001-06-07 09:45 | 70MW Walla Walla-Franklin | FPL Energy Power Marketing Inc | OR | Umatilla | Nine Mile Tap on the Walla Walla-Franklin 115 kV line | WITHDRAWN | GI | 2002-09-01 |  | 70 | 70 | Energy | Wind |  | Withdrawn by Customer | .
G61 | 2001-06-05 14:25 | Black Hills Energy | Black Hills Energy Capital Inc | ID | Minidoka | Hay Mill 138 kV Substation | WITHDRAWN | GI | 2002-07-01 |  | 55 | 55 | Energy | Combined cycle |  | Withdrawn by Customer | .
G59 | 2001-05-31 14:33 | 700MW Sickler-Schultz | Calpine Energy Services, L.P. | WA | Benton | Sickler-Schultz 500 kV | WITHDRAWN | GI | 2005-06-01 |  | 700 | 700 | Energy | Combined cycle |  | Withdrawn by Customer | .
G60 | 2001-05-31 14:33 | 1300MW Sickler-Schultz | Calpine Energy Services, L.P. | WA | Benton | Sickler-Schultz 500 kV | WITHDRAWN | GI | 2005-06-01 |  | 1300 | 1300 | Energy | Combined cycle |  | Withdrawn by Customer | .
G58 | 2001-05-23 10:02 | 105MW McNary-Roundup | Seawest Windpower, Inc. | OR | Umatilla | McNary-Roundup 230 kV line | WITHDRAWN | GI | 2003-09-01 |  | 105 | 105 | Energy | Wind |  | Withdrawn by Customer | .
G57 | 2001-05-22 15:15 | GNA Energy | Seawest Windpower, Inc. | OR | Sherman | Big Eddy-DeMoss 115 kV line | WITHDRAWN | GI | 2003-09-01 |  | 105 | 105 | Energy | Wind |  | Withdrawn by Customer | .
G56 | 2001-05-11 17:54 | GNA Energy | GNA Energy, LLC | WA | Klickitat | Harvalum 230 kV Substation | WITHDRAWN | GI | 2002-02-01 |  | 45 | 45 | Energy | Combined cycle |  | Withdrawn by Customer | .
G55 | 2001-05-11 16:34 | Cedar Hills Energy LLC | Cedar Hills Energy LLC | WA | king | Maple Valley 230 kV Substation | WITHDRAWN | GI | 2004-01-01 |  | 300 | 300 | Energy | Combined cycle |  | Withdrawn by Customer | .
G54 | 2001-05-09 11:19 | Klondike Wind Power | Klondike Wind Power, LLC | OR | Sherman | De Moss 69 kV Substation, relocated to 230 kV KSHS | ENERGIZED | GI | 2001-10-31 |  | 24 | 24 | Energy | Wind |  | on-line December 2000; later sold to Iberdrola and operated as Klondike 1 | .
G53 | 2001-05-04 11:37 | Tacoma Power TC-PSE | Tacoma Power | WA | Skagit | 230 kV Sedro Wooley-Bellingham line | WITHDRAWN | GI | 2002-01-01 |  | 83 | 83 | Energy | Combined cycle |  | Withdrawn by Customer | .
G51 | 2001-05-03 15:17 | Pierce County Project No 1 | Duke Energy North America, LLC | WA | Pierce | South Tacoma 230 kV Substation | WITHDRAWN | GI | 2003-01-01 |  | 170 | 170 | Energy | Combined cycle |  | Withdrawn by Customer | .
G52 | 2001-05-03 15:17 | Pierce County Project No 2 | Duke Energy North America, LLC | WA | Pierce | South Tacoma 230 kV Substation | WITHDRAWN | GI | 2003-01-01 |  | 170 | 170 | Energy | Combined cycle |  | Pierce County Project No. 2 | .
G48-01 | 2001-04-23 18:47 |  | Washington Winds, Inc. | WA | BentoN | 230 kV Big Eddy-Midway/ 500 kV Hanford-John Day line | WITHDRAWN | GI | 2002-11-15 |  | 249 | 249 | Energy | Wind |  | Withdrawn by Customer | .
G48 | 2001-04-23 18:47 |  | Washington Winds, Inc. | WA | Benton | 230 kV Big Eddy-Midway/ 500 kV Hanford-John Day line | WITHDRAWN | GI | 2002-11-15 |  | 150 | 150 | Energy | Wind |  | Withdrawn on January 28, 2004 | .
G49 | 2001-04-23 09:46 |  | Washington Winds, Inc. | WA | Benton | 230 kV Big Eddy-Midway/ 500 kV Hanford-John Day line | WITHDRAWN | GI | 2002-11-30 |  | 249 | 249 | Energy | Wind |  |  | .
G50 | 2001-04-23 09:46 | Pacific Winds Inc | Pacific Winds, Inc. | WA | Klickitat | 230/kV McNary - Horse Heaven/ 345 kV McNary - Ross line | WITHDRAWN | GI | 2003-03-31 |  | 249 | 249 | Energy | Wind |  | Withdrawn by Customer | .
G47 | 2001-04-19 09:52 | Nordic Energy Barge No 2 | Nordic Energy Barge #2, LLC | OR | Columbia | Trojan Switching Station | WITHDRAWN | GI | 2001-12-01 |  | 170 | 170 | Energy |  |  | Withdrawn by Customer | .
G46-03 | 2001-04-18 09:00 | 100MW Cowlitz-Cardwell | Avista Power, LLC | WA | Cowlitz | Cowlitz-Cardwell 115 kV line | WITHDRAWN | GI | 2001-12-01 |  | 100 | 100 | Energy | Combined cycle |  | Withdrawn by Customer | .
G46-01 | 2001-04-17 16:21 | Clark Public Utilities | Clark Public Utilities | WA | Clark | 115 kV bus at BPA Alcoa Substation | WITHDRAWN | GI | 2002-07-01 |  | 250 | 250 | Energy | Combined cycle |  |  | .
G46 | 2001-04-16 16:31 | Coburg Power | Coberg Power LLC | OR | Lane | Marion-Lane No. 1 500 kV line near Colburg | WITHDRAWN | GI | 2004-08-01 |  | 570 | 570 | Energy | Combined cycle |  | Withdrawn on October 16, 2004 | .
G44 | 2001-04-11 17:50 | 100MW Longview 1 | Avista Power, LLC | WA | Cowlitz | BPA's Longview Substation | WITHDRAWN | GI | 2001-12-01 |  | 100 | 100 | Energy | Combined cycle |  | Withdrawn by Customer | .
G45 | 2001-04-11 17:50 | 100MW Longview 2 | Avista Power, LLC | WA | Cowlitz | BPA's Longview Substation | WITHDRAWN | GI | 2001-12-01 |  | 100 | 100 | Energy | Combined cycle |  | Withdrawn by Customer | .
G43 | 2001-04-06 17:03 | Clatskanie | Clatskanie People's Utility District | OR | Columbia | Alcoa Substation 115 kV | WITHDRAWN | GI | 2002-05-15 |  | 88 | 88 | Energy | Combined cycle |  | Withdrawn by Customer | .
G41 | 2001-04-06 12:25 | 100MW McNary | Calpine Energy Services, L.P. | OR | Umatilla | McNary Substation | WITHDRAWN | GI | 2001-12-01 |  | 100 | 100 | Energy | Combined cycle |  | Withdrawn by Customer | .
G42 | 2001-04-06 12:25 | 50MW Alcoa | Calpine Energy Services, L.P. | WA | Clark | Alcoa Substation 230 kV in the vicinity of Vancouver, WA | WITHDRAWN | GI | 2001-10-31 |  | 50 | 50 | Energy | Combined cycle |  | Withdrawn by Customer | .
G40 | 2001-04-06 12:24 | 250MW Covington-Chehalis,Tacoma-Olympia | Calpine Energy Services, L.P. | WA | Pierce | 230 kV Covington-Chehalis and/or Tacoma-Olympia lines | WITHDRAWN | GI | 2001-05-01 |  | 250 | 250 | Energy | Combined cycle |  | Withdrawn by Customer | .
G39 | 2001-04-04 12:04 | Grant Generation | Grant Generation, LLC | WA | Grant | Vantage-Hanford 500 kV line | WITHDRAWN | GI | 2005-02-01 |  | 1300 | 1300 | Energy | Combined cycle |  | Withdrawn by Customer | .
G46-02 | 2001-04-01 09:00 | 100MW Cowlitz PUD BHP at Kalama | Avista Power, LLC | WA | Cowlitz | Cowlitz PUD BHP at Kalama 115 kV line | WITHDRAWN | GI | 2001-12-01 |  | 100 | 100 | Energy | Combined cycle |  | Withdrawn by Customer | .
G38 | 2001-03-22 17:21 | 600 MW Monroe-Custer | Calpine Energy Services, L.P. | WA | Skagit | Monroe-Custer 500 kV line near Sedro Wooley | WITHDRAWN | GI | 2005-06-01 |  | 600 | 600 | Energy | Combined cycle |  | Withdrawn by Customer | .
G37 | 2001-03-20 08:12 | Nordic Energy Barge 1 | Nordic Energy Barge #1, LLC | WA | Cowlitz | Cowlitz Substation | WITHDRAWN | GI | 2001-08-01 |  | 100 | 100 | Energy | Combined cycle |  | Withdrawn by Customer | .
G36 | 2001-03-16 14:23 | Frontier Technology | Frontier Technology, Inc | OR | Lane | Marion-Lane No. 1 500 kV transmission line near Colburg | WITHDRAWN | GI | 2003-08-01 |  | 265 | 265 | Energy | Combined cycle |  | Withdrawn on October 11, 2002 | .
G35 | 2001-03-06 18:36 | Grant Generation | Grant Generation, LLC | WA | Grant | Grand Coulee-Schultz 500 kV line | WITHDRAWN | GI | 2005-06-01 |  | 1300 | 1300 | Energy | Combined cycle |  | Withdrawn on October 11, 2002 | .
G34 | 2001-03-06 16:08 | Competitive Power Venture | Newport Northwest, LLC | WA | Whatcom | Intalco 500 kV Substation | WITHDRAWN | GI | 2005-06-01 |  | 1300 | 1300 | Energy | Combined cycle |  |  | .
G33 | 2001-03-06 10:57 | Tenaska Inc | Tenaska, Inc. | OR | Klamath | Captain Jack 500 kV Substation | WITHDRAWN | GI | 2004-06-01 |  | 450 | 450 | Energy | Combined cycle |  | Withdrawn on July 15, 2002 | .
G32 | 2001-03-05 08:28 | Kootenai Generation | Kootenai Electric Cooperative, Inc. | WA | Kootenai | BPA's Taft-Bell 500 kV line | WITHDRAWN | GI | 2005-06-01 |  | 1300 | 1300 | Energy | Combined cycle |  | Withdrawn on October 11, 2002 | .
G30 | 2001-03-01 13:57 | Pacific Winds Inc | Pacific Winds, Inc. | WA | Benton | 230 kV Hanford-Mabton transmission line near Rattlesnake Hills | WITHDRAWN | GI | 2002-11-15 |  | 100 | 100 | Energy | Wind |  | Withdrawn by Customer | .
G31 | 2001-03-01 13:57 | Pacific Winds Inc | Pacific Winds, Inc. | WA | Benton | 230 kV Franklin-McNary line near Horse Heaven Hills | WITHDRAWN | GI | 2002-11-15 |  | 100 | 100 | Energy | Wind |  | Withdrawn by Customer | .
G29 | 2001-02-23 14:46 | BP Energy Company | BP Energy Company | OR | Grant | John Day | WITHDRAWN | GI | 2004-01-01 |  | 200 | 200 | Energy | Wind |  | Withdrawn on October 11, 2002 | .
G28 | 2001-02-22 14:59 | N/A | Clark Public Utilities | WA | Clark | Alcoa Substation | WITHDRAWN | GI | 2001-01-01 |  | 100 | 100 | Energy | Combined cycle |  | Withdrawn on October 30, 2002 | .
G27-01 | 2001-02-20 17:05 | Cherry Point Refinery | BP Energy Company | WA | Whatcom | Custer Substation | WITHDRAWN | GI | 2004-01-01 |  | 1000 | 1000 | Energy | Combined cycle |  | LGIA terminated on February 1, 2011. | .
G22 | 2001-02-16 06:13 | 50MW Alcoa-St Johns | Calpine Energy Services, L.P. | WA | Clark | Tap of Alcoa-St. Johns 115 kV line | WITHDRAWN | GI | 2001-11-01 |  | 50 | 50 | Energy | Combined cycle |  |  | .
G27 | 2001-02-15 16:26 | Benton PUD | Public Utility District No. 1 of Benton County | WA | Benton | Unocal Finley Substation | WITHDRAWN | GI | 2001-08-01 |  | 25 | 25 | Energy | Combined cycle |  |  | .
G26 | 2001-02-15 15:51 | Wanapa Energy Center | Confederated Tribes Umatilla Indian Resvation | OR | Umatilla | McNary 500 kV bus | STUDY | GI | 2003-07-01 |  | 1000 | 1000 | Energy | Combined cycle |  | Study suspended by customer due to ownership issues | .
G24 | 2001-02-15 14:14 | 500MW Custer-[Intalco,Portal Way] 1 | Calpine Energy Services, L.P. | WA | Whatcon | Custer-Intalco/Portal Way 230 kV transmission line | WITHDRAWN | GI | 2005-06-01 |  | 500 | 500 | Energy | Combined cycle |  |  | .
G25 | 2001-02-15 14:14 | 500MW Custer-[Intalco,Portal Way] 2 | Calpine Energy Services, L.P. | WA | Whatcom | Custer-Inalco/Portal Way 230 kV transmission line | WITHDRAWN | GI | 2004-06-01 |  | 500 | 500 | Energy | Combined cycle |  |  | .
G23 | 2001-02-15 14:13 | 500MW St Johns-Ross | Calpine Energy Services, L.P. | WA | Clark | St. Johns-Ross 230 kV line | WITHDRAWN | GI | 2005-06-01 |  | 500 | 500 | Energy | Combined cycle |  |  | .
G20 | 2001-02-05 14:48 | Centralia Generation Addition | TransAlta Utilities Cooperative | WA | Lewis | Tap of the Centralia-Paul 500 kV line | ENERGIZED | GI | 2002-01-01 |  | 248 | 248 | Energy | Combined cycle |  | on-line | .
G21 | 2001-02-05 14:48 | Condon Wind Farm | Seawest Windpower, Inc. | OR | Gilliam | At the Demoss-Fossil 69 kV line near Condon, OR | ENERGIZED | GI | 2002-01-01 |  | 25 | 25 | Energy | Wind |  | on-line 2000 | .
G19-01 | 2001-01-25 16:06 | Summit PNW | Summit Power Northwest Project, LLC | OR | Clatsop | Allston 230 KV | WITHDRAWN | GI | 2003-10-31 |  | 520 | 520 | Energy | Combined cycle |  | Withdrawn on March 11, 2010. | .
G19 | 2001-01-18 18:18 | 500MW Snohomish | FPL Energy Power Marketing Inc | WA | Snohomish | At 115 kV and 230 kV Snohomish Substation | WITHDRAWN | GI | 2002-09-01 |  | 500 | 500 | Energy | Combined cycle |  |  | .
G18 | 2001-01-10 12:42 | 250MW Snohomish | FPL Energy Power Marketing Inc | WA | Snohomish | Snohomish 115 kV Substation | WITHDRAWN | GI | 2002-09-01 |  | 250 | 250 | Energy | Combined cycle |  |  | .
G17 | 2000-12-24 14:40 | JP Saylor and Associates | J P Saylor & Associates | OR | Curry | BPA's Fairview-Rogue 230 kV line in the vicinity of Curry County, OR | WITHDRAWN | GI | 2001-10-31 |  | 25 | 25 | Energy | Wind |  |  | .
G16 | 2000-12-22 13:31 | 500MW Taft-Bell | Cogentrix Energy, Inc. | ID | Kootenai | BPA's Taft-Bell 500 kV line in the vicinity of Kootenaid County, ID | WITHDRAWN | GI | 2004-12-01 |  | 500 | 500 | Energy | Combined cycle |  |  | .
G15 | 2000-12-18 14:51 | Oregon Energy Company | Oregon Energy Company LLC | OR | Columbia | on BPA's 115 kV Allston-St. Helens line in the vicinity of St. Helens, OR | WITHDRAWN | GI | 2002-08-01 |  | 170 | 170 | Energy | Combined cycle |  |  | .
G14 | 2000-11-30 15:38 | Stateline Wind Farm | FPL Energy Vansycle L.L.C. | OR | Umatilla | on BPA's Franklin-Walla Walla line in the vicinity of Touchet, WA | ENERGIZED | GI | 2001-09-01 |  | 90 | 90 | Energy | Wind |  | on-line October 2008 | .
G13 | 2000-10-31 14:50 | Centralia Generation | TransAlta Utilities Cooperative | WA | Lewis | C.W. Paul 500 kV Substation | ENERGIZED | GI | 2001-06-01 |  | 50 | 50 | ERIS | Combined cycle |  |  | .
G11 | 2000-09-13 16:25 | Pacific Winds Inc | Pacific Winds, Inc. | WA | Benton | a new POR in the vicinity of the Franklin-McNary 230 kV line | WITHDRAWN | GI | 2002-07-01 |  | 76 | 76 | Energy | Wind |  |  | .
G12 | 2000-09-09 00:06 | Oregon Energy Company | Oregon Energy Company LLC | OR | Linn | Albany-Eugene 115 kV line near Halsey, OR | WITHDRAWN | GI | 2001-10-01 |  | 120 | 120 | Energy | Combined cycle |  | Withdrawn on July 8, 2002. | .
G10 | 2000-08-28 14:52 | 1100MW Grizzly | Cogentrix Energy, Inc. | OR | Jefferson | Grizzly 500 kV Substation | WITHDRAWN | GI | 2004-07-01 |  | 1100 | 1100 | Energy | Combined cycle |  |  | .
G9 | 2000-08-28 14:51 | 1100MW Paul | Cogentrix Energy, Inc. | WA | Lewis | Paul 500 kV Substation | WITHDRAWN | GI | 2004-07-01 |  | 1100 | 1100 | Energy | Combined cycle |  |  | .
G8 | 2000-08-28 14:50 | 1100MW Troutdale | Cogentrix Energy, Inc. | OR | Multnomah | Troutdale kV Substation | WITHDRAWN | GI | 2004-07-01 |  | 1100 | 1100 | Energy | Combined cycle |  | Withdrawn by Customer | .
G7 | 2000-08-25 14:19 | Pacific Winds Inc | Pacific Winds, Inc. | WA | Benton | Hanford-Mabton 230 kV line | WITHDRAWN | GI | 2002-10-31 |  | 76 | 76 | Energy | Wind |  | Withdrawn by Customer | .
G6 | 2000-08-22 14:30 | Continental Energy Svcs | Continental Energy Services, Inc. | MT | Silver Bow | Silver Bow 230 kV Substation | WITHDRAWN | GI | 2002-03-31 |  | 400 | 400 | Energy | Combined cycle |  | Withdrawn by Customer | .
G5 | 2000-08-02 07:56 | Nine Canyon Wind Project | Energy Northwest Inc | WA | Benton | 115 kV McNary-Badger Canyon line (Nine Canyon Substation) | ENERGIZED | GI | 2001-09-01 |  | 63 | 63 | Energy | Wind |  |  | .
G4 | 2000-07-28 16:17 | Mint Farm Energy Center | Puget Sound Energy, Inc. | WA | Cowlitz | Longview 230 kV Substation | ENERGIZED | GI | 2007-11-28 |  | 320 | 320 | Energy | Combined cycle |  | on-line | .
G3 | 2000-07-28 15:55 | Enron Power Marketing | Enron Power Marketing, Inc. | WA | Cowlitz | Longview 230 kV Substation | WITHDRAWN | GI | 2003-06-01 |  | 600 | 600 | Energy | Combined cycle |  | Withdrawn by Customer | .
G2 | 2000-06-23 | Goldendale Energy Center | Goldendale Energy Center, LLC | OR | klickitat | Harvalum 230 kV Substation | ENERGIZED | GI | 2002-01-01 |  | 247 | 247 | Energy | Combined cycle |  | on-line | .
G1 | 2000-06-09 16:12 | PG and E Generation | PG&E Energy Services | OR | Umatilla | McNary 230 kv Substation | WITHDRAWN | GI | 2000-06-09 |  | 581 | 581 | Energy | Combined cycle |  |  | .