## Timeline
Project: Systems Portfolio/e-Folio
Last Update: June 4, 2010
Month
Key Milestones | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Responsible Party
Met with Academic Deans on Systems Portfolio duties | July: 29 | OIE
Met with Learner Services AVP, and Deans on Systems Portfolio duties | Aug: 14 | OIE
Train Academic Division Secretaries to input into e-Folio web shell | Aug: 17, 18, 19 | OIE
Met with HR regarding Systems Portfolio | Aug: 31 | OIE
Met with Business Services and Finance regarding input for Systems Portfolio | [11 empty] | OIE | bar: Sept
Met with Faculty Senate regarding the Systems Portfolio | Sept: 18 | OIE
Met with External Affairs Div. regarding the Systems Portfolio | Oct: 9 | OIE
Met with WCC and ECE staff regarding the Systems Portfolio | Oct: 21 | OIE
Teams collect information and data from NWACC community | [11 empty] | NWACC
Teams have completed draft #1 | Month Dec: Rough draft Dec 18th | All Division Reps
Draft #1 returned with comments to teams | Month Jan: Jan 11th | Cabinet
Institutional overview in near final draft form (draft Shared with President and CAO for comments) | Month Jan: Jan 18th | TBD
Accomplishing other distinct objectives/planning CI in draft form | Month Feb: 1st of month | Cabinet
Draft #2 due | Month Feb: Feb 12th | All Division Reps
Begin data entry into eFolio | Month Mar: mid month | OIE
Draft #2 returned with comments to teams | Month Mar: TBD | Cabinet
Draft #3 due from teams | Month Mar: Mar 12th | All Division Reps
Cabinet (with subordinates) reviews final drafts | Month Apr: 1st of month | Cabinet
Multiple Focus Groups to review drafts | Month Mar: Mid March; Month May: Mid May | College Employees
Draft #4 due from teams | Month Apr: April 8th | All Division Reps
Submit to President and CAO for review | Month Apr: Mid- month | Cabinet
Comments from President and CAO | Month May: 1st week of May | Cabinet
Final drafts submitted to "One Voice" editor | Month May: 1st week of May | OIE
Final formating for pdf document and loading of eFolio | Month May: May 24th | Advancement
eFolio Live | Month May: May 28th | Claudia Tonihka
Submission of PDF of Systems Portfolio to the HLC | Month May: June 1st | OIE