## Notes
Notes
1. Site ID The initials of the city (SF, RC, PA, MV, or SJ) followed by a three digit number starting over with 001 for each city.
2. Priority Rank based on a scale of 1-3. 1 being the highest priority and 3 being the lowest. Please be sure to factor readiness of the site (i.e will it be ready for equipment to arrive in March) into the priority ranking. A site that is very important to the city, but not going to be ready in time for the pilot rollout, should be ranked as a 2 not a 1.
3. Readiness based on a scale of 1-3. 1 being the most ready and 3 being the least. Please be sure to take all permiting and physical site preparation into account when ranking a site's readiness.

## SFMTA
Site ID | SFMTA ID | Priority Ranking | Readiness | Street Name | Side of Street | Nearest Cross-street | Closest Property | Station Length | Sidewalk | Parking Lane | Private Property | Historical Site | Environmental Issues | Construction Needed | Comments (If applicable, explain construction/ environmental issues)
SF001 | Embr-E | 1 | 2 | Embarcadero | W | Sansome | 1500 Sansome - The Roundhouse (Pier 27) | 23 | Y |  | Y |  |  |  | Port Jurisdiction - Separate approval process
SF002 | Embr-F | 1 | 2 | Embarcadero | E | Green | Pier 15/17 The Exploratorium | 23 | Y |  | Y |  |  |  | Port Jurisdiction - Separate approval process
SF003 | Embr-G | 1 | 2 | Embarcadero | E | Market | Ferry Building- The Lagoon | 55 | Y |  | Y |  |  |  | Port Jurisdiction - Separate approval process
SF004 | Embr-H4 | 1 | 2 | Embarcadero | E | Harrison | Pier 24 | 29 | Y |  | Y |  |  |  | Port Jurisdiction - Separate approval process
SF005 | Embr-J | 1 | 2 | Embarcadero | E | Townsend | Pier 40 | 31 | Y |  | Y |  |  |  | Port Jurisdiction - Separate approval process
SF006 | Market-0 | 1 | 2 | South Van Ness | E | Market | 1 South Van Ness | 27 | Y
SF007 | Market-01A | 1 | 2 | Market | S | Grant/O'Farrell | 773 Market | 19 | Y
SF008 | Market-02 | 1 | 2 | Market | N | Battery | 444 Market | 27 | Y
SF009 | Market-03A | 1 | 2 | Market | N | 7th | 10 UN Plaza | 23 | Y |  |  | Y
SF010 | Market-04 | 1 | 2 | Market | N | Taylor | 988 Market Street | 21 | Y
SF011 | Market-07A | 1 | 2 | Market | N | Cyril Magnin | 1 Halladie Plaza | 15 | Y
SF012 | Market-10A | 1 | 2 | Steuart | W | Market | 1 Market | 23 |  | Y
SF013 | Market-09A | 1 | 2 | 2nd | E | Market | 29 2nd Street/109 Stevenson St | 15 |  | Y
SF014 | NOMA-01A | 1 | 2 | Battery | E | Filbert | 1155 Battery | 23 |  | Y
SF015 | NOMA-02D | 1 | 2 | Broadway | S | Battery | 750 Battery | 23 |  | Y
SF016 | NOMA-03C | 1 | 2 | Davis St | W | Jackson | Davis at Jackson | 15 |  | Y
SF017 | NOMA-04 | 1 | 2 | Drumm | E | Washington | Drumm at Washington | 23 |  | Y
SF018 | NOMA-05A | 1 | 2 | Clay | S | Battery | 1 Embarcadero Center (Battery and Clay) | 15 |  | Y
SF019 | NOMA-07 | 1 | 2 | Leidesdorff | W | California | 464 California | 23 |  | Y
SF020 | NOMA-09A | 1 | 2 | Grant | E | Post | 185 Post | 15 |  | Y
SF021 | NOMA-10A | 1 | 2 | Columbus | E | Kearny | 170 Columbus | 25 |  | Y
SF022 | NOMA-11 | 1 | 2 | Battery | E | Jackson | 570 Battery | 25 |  | Y
SF023 | NOMA-13C | 1 | 2 | Columbus | E | Broadway | 270 Columbus | 25 |  | Y
SF024 | NOMA-14 | 1 | 2 | Grove | N | Larkin | 30 Grove | 21 |  | Y |  | Y
SF025 | NOMA-18A | 1 | 2 | Leidesdorff | S | Leidesdorff | 217 Leidesdorff | 23 |  | Y
SF026 | NOMA-21A | 1 | 2 | California | E | Kearny | 555 California | 21 | Y |  | Y |  |  |  | Additional outreach to private property owner
SF027 | NOMA-22B | 1 | 2 | Polk | E | Golden Gate | 450 Golden Gate | 27 | Y
SF028 | NOMA-23A | 1 | 2 | McAllister | N | Breen Pl | 200 McAllister | 17 | Y |  | Y |  |  |  | Private property owner in support
SF029 | NOMA-24A | 1 | 2 | Grove | N | Dr. Carlton B Goodlet Pl | Civic Center Plaza | 23 | Y |  | Y | Y |  |  | SF Rec and Park approval process
SF030 | NOMA-25A | 1 | 2 | Powell | W | Post | 400 Post | 21 |  | Y
SF031 | NOMA-26 | 1 | 2 | Walter U Lum | E | Washington | Portsmouth Square | 23 | Y
SF032 | NOMA-27 | 1 | 3 | Bush | S | Kearny | 381 Bush | 23 |  | Y
SF033 | NOMA-30 | 1 | 3 | California | N | Battery | 300 California | 23 |  | Y
SF034 | NOMA-31A | 1 | 2 | Washington | S | Sansome | 501 Washington, 505 Washington | 21 |  | Y
SF035 | NOMA-32 | 1 | 2 | Post | N | Kearny | 1 Montgomery Street | 23 |  | Y
SF036 | NOMA-33 | 1 | 2 | Davis St | E | Sacramento | 3 Emabrcadero Center (Davis and Sacramento) | 21 |  | Y
SF037 | SOMA-01A | 1 | 2 | Jesse | E | Mint Plaza | 66 Mint Plaza | 15 |  | Y
SF038 | SOMA-02A | 1 | 2 | Berry | S | 4th Street | 185 Berry Street | 15 |  | Y
SF039 | SOMA-03 | 1 | 2 | Howard | N | 7th St. | 1098 Howard Street (7th and Howard ) | 21 |  | Y
SF040 | SOMA-06 | 1 | 2 | Howard | N | Main | Temporary Transbay Terminal | 46 | Y |  | Y |  |  | Y | TJPA seeks assistance relocating a fence
SF041 | SOMA-07B | 1 | 2 | Mission | W | 7th St. | 90 7th Street | 25 | Y |  | Y |  |  |  | GSA approval process
SF042 | SOMA-08 | 1 | 2 | 5th St. | E | Howard | 165 5th Street | 23 |  | Y
SF043 | SOMA-09A | 1 | 2 | 4th Street | E | Clara Street | 399 4th Street | 15 |  | Y
SF044 | SOMA-10C | 1 | 2 | Townsend St | N | 7th St. | 650 Townsend | 23 |  | Y
SF045 | SOMA-11A | 1 | 2 | Townsend St | N | 4th St | 310 Townsend Street | 23 |  | Y
SF046 | SOMA-11B | 1 | 2 | Townsend St | S | 5th | 310 Townsend St | 44 | Y |  | Y |  |  |  | Caltrain approval process
SF047 | SOMA-11C | 1 | 2 | Townsend St | S | 4th | 700 4th St | 44 | Y |  | Y |  |  |  | Caltrain approval process
SF048 | SOMA-12C | 1 | 2 | 2nd | E | Folsom | 303 2nd St | 23 |  | Y
SF049 | SOMA-13A | 1 | 2 | 2nd | W | South Park | 1 South Park | 15 |  | Y |  | Y
SF050 | SOMA-15C | 1 | 2 | Spear | E | Folsom | 345 Spear Street | 23 |  | Y
SF051 | SOMA-16 | 1 | 2 | Howard | N | 8th St | 1200 Howard Street | 15 |  | Y
SF052 | SOMA-17 | 1 | 2 | Howard | N | 3rd | Yerba Buena Gardens Center for the Arts | 21 | Y |  | Y
SF053 | SOMA-18C | 1 | 2 | Howard | N | 1st | 500 Howard St | 15 |  | Y
SF054 | SOMA-19 | 1 | 2 | Folsom | S | 4th | 855 Folsom Street | 21 |  | Y
SF055 | SOMA-20 | 1 | 2 | 2nd Street | E | Mission Street | 101 Second Street | 19 |  | Y
SF056 | SOMA-22 | 1 | 2 | Beale | E | Folsom | 300 Beale Street | 21 |  | Y
SF057 | SOMA-25 | 1 | 2 | 2nd | E | Townsend | 2nd and Townsend | 15 |  | Y
SF058 | SOMA-27A | 1 | 2 | Gene Friend Way | S | 4th St. | UCSF Mission Bay Campus 1 Plaza | 23 | Y |  | Y |  |  |  | UCSF approval process
SF059 | SOMA-29 | 1 | 2 | Mission | S | Main | Temporary Transbay Terminal Spillover | 46 | Y |  | Y |  |  | Y | TJPA seeks assistance relocating a fence
SF060 | SOMA-30 | 1 | 2 | 4th Street | W | King | 700 4th Street | 8 | Y

## SF Caltrain
Site ID | Priority Ranking1 | Readiness | Street Name | Side of Street | Nearest Cross-street | Closest Property | Station Length2 | Sidewalk | Parking Lane | Private Property | Historical Site | Environmental Issues | Construction Needed | Comments (If applicable, explain construction/ environmental issues)
CSF001 | 1 | 1 | King Street | N | 4th (near landscaped area) | Caltrain Station | 16 docks | N | N | N | N | N | N | newly installed bollards may make location suboptimal by time of pilot launch
CSF002 | 1 | 1 | King Street | N | 4th (at station plaza, along station bldg) | Caltrain Station | 12 docks | N | N | N | N | N | N
CSF003 | 1 | 1 | Townsend | S | 4th (in front of Warm Planet) | Caltrain Station | 16 docks | N | N | N | N | N | N | possible pedestrian flow and circualtion impacts
CSF004 | 1 | 2 | Townsend | S | 4th (behind Warm Planet) | Caltrain Station | 25 docks | N | N | N | N | N | Y | removal of fencing
1. Only priority ranking 1 sites are being considered for the pilot program.
2. Assumes a kiosk at the station

## Redwood City
Site ID | Priority Ranking | Readiness | Street Name | Side of Street | Nearest Cross-street | Closest Property | Station Length | Sidewalk | Parking Lane | Private Property | Historical Site | Environmental Issues | Construction Needed | Comments (If applicable, explain construction/ environmental issues)
RC001 | 1 | 1 | Middlefield Rd | W | Main St | Library | 18 | Y | N | N | TBD | N | N
RC002 | 1 | 1 | Roosevelt Ave | N | Sanchez Way | Red Morton CAB | 18 | Y | N | N | N | N | N
RC003 | 1 | 1 | Maple St | S | Veterans Ave | Kaiser Hospital | 14 | Y | N | N | N | N | N
RC004 | 1 | 1 | Howland St | S | Allerton St | Mezes park | 8 | Y | N | N | N | N | N
RC005 | 1 | 1 | Broadway Rd | N | Perry St | N/A | 12 | N | Y | N | N | N | N
RC006 | 1 | 1 | Hopkins Ave | N | King St | Stafford Park | 12 | Y | N | N | N | N | N
RC007 | 1 | 1 | Roosevelt Ave | N | Upton St | N/A | 8 | Y | N | N | N | N | N
RC008 | 1 | 2 | Marshall St | S | Jefferson Ave | Marshall Parking Garage | 12 | Y | N | N | N | N | Y | will need minor relocation of some bollards and restriping of garage
RC009 | 1 | 2 | Hopkins Ave | Mid | Broadway Rd | neighborhood park | 10 | Y | N | N | N | N | Y
RC010 | 2 | 2 | Chestnut St | N | Middlefield Rd | Jardin de Ninos | 8 | Y | N | N | N | N | Y | Park renovation in design process and station will need to be incorporated into design
RC011 | 2 | 1 | Broadway Rd | SW | Brewster Ave | Sequoia HS | 8 | Y | N | N | N | N | N
RC012 | 2 | 1 | Broadway Rd | E | Walnut St | Wells Fargo Bank | 8 | Y | N | N | N | N | N
RC013 | 2 | 2 | El Camino Real | E | Maple St | N/A | 8 | Y | N | N | N | N | Y
RC014 | 2 | 2 | Valota Rd | E | Vera Ave | Red Morton Park | 8 | Y | N | N | N | N | Y
RC015 | 3 | 1 | Brewster Ave | E | Perry St | CalTrain Parking Lot | 8 | Y | N | N | N | N | N
RC016 | 3 | 1 | Broadway Rd | E | Chestnut St | PWS Corp Yard | 8 | Y | N | N | N | N | N

## San Mateo County
Site ID | Priority Ranking | Readiness | Street Name | Side of Street | Nearest Cross-street | Closest Property | Station Length | Sidewalk | Parking Lane | Private Property | Historical Site | Environmental Issues | Construction Needed | Comments (If applicable, explain construction/ environmental issues)
SM001 | 1 | 2 | Marshall St | S | County Center | SMC Museum | 6 docks | Y | N | N | N | N | N | Shared lot with History Museum
SM002 | 1 | 2 | Middlefield | S | Douglas | Fair Oaks Library | 9 docks | Y | N | N | N | N | N | Placed over existing parking
SM003 | 1 | 2 | Industrial Way | N | Circle Star Way | Circle Star | 9 docks | Y | N | N | N | N | N | Placed over existing parking

## RWC Caltrain
Site ID | Priority Ranking1 | Readiness | Street Name | Side of Street | Nearest Cross-street | Closest Property | Station Length2 | Sidewalk | Parking Lane | Private Property | Historical Site | Environmental Issues | Construction Needed | Comments (If applicable, explain construction/ environmental issues)
CRC001 | 1 | 1 | Southbound Platform | N | near Transit Center | Caltrain Station | 9 docks | N | N | N | N | N | N | no upgrades required (if solar utilized)
CRC002 | 1 | 2 | Southbound Platform | N | North end near Broadway | Caltrain Station | 9 docks | N | N | N | N | N | Y | May need to add concrete footing for securing a bicycle station. No other upgrades required if solar utilized.
1. Only priority ranking 1 sites are being considered for the pilot program.
2. Assumes a kiosk at the station
CITY OF REDWOOD CITY OWNERSHIP
CRC003 | 1 | 1 | Winslow Street | W | Plaza next to City Parking Lot and Northbound Platform | Caltrain Station | 5 docks | N | N | N | N | N | N | As of 2/12 location will likely be under construction and not available during project launch. no upgrades required (if solar utilized)
CRC004 | 1 | 1 | Winslow Street | W | near Northbound Platform Entrance | Caltrain Station | 13 docks | N | N | N | N | N | N | no upgrades required (if solar utilized)

## PA Caltrain
Site ID | Priority Ranking1 | Readiness | Street Name | Side of Street | Nearest Cross-street | Closest Property | Station Length2 | Sidewalk | Parking Lane | Private Property | Historical Site | Environmental Issues | Construction Needed | Comments (If applicable, explain construction/ environmental issues)
CPA001 | 1 | 1 | Alma Street | W | Lytton Ave | Caltrain Station | 17 docks | N | N | N | Y | Y | Y | No upgrades required (with solar); pavement cut and repair (if electrical) Need to remove and relocate bike racks On historical site (environmental issues)
CPA002 | 1 | 1 | Alma Street | W | Lytton Ave (just south of PA001 location) | Caltrain Station | 13 docks | N | N | N | Y | Y | Y | No upgrades required (with solar); pavement cut and repair (if electrical) Need to remove and relocate bike racks On historical site (environmental issues)
CPA003 | 2 | 2 | VTA Transit Center | S | west of Southbound Platform | Caltrain Station | 5 docks | Y | N | N | Y | Y | Y | Paving cut and repair (for electrical) On historical site (environmental issues)
CPA004 | 2 | 2 | VTA Transit Center | S | west of Southbound Platform (just south of PA003 location) | Caltrain Station | 5 docks | Y | N | N | Y | Y | Y | Paving cut and repair (for electrical) On historical site (environmental issues)
CPA005 | 2 | 1 | Southbound Platform | S | south of University Ave | Caltrain Station | 7 docks | N | N | N | Y | Y | N | On historical site (environmental issues)
CPA006 | 2 | 2 | Southbound Platform | N | Between building and platform | Caltrain Station | 5 docks | N | N | N | Y | Y | Y | Paving cut and repair (for electrical - does not meet solar minimum) On historical site (environmental issues)
1. Only priority ranking 1 sites are being considered for the pilot program.
2. Assumes a kiosk at the station

## MV Caltrain
Site ID | Priority Ranking1 | Readiness | Street Name | Side of Street | Nearest Cross-street | Closest Property | Station Length2 | Sidewalk | Parking Lane | Private Property | Historical Site | Environmental Issues | Construction Needed | Comments (If applicable, explain construction/ environmental issues)
CMV001 | 1 | 1 | Transit Center | N | east of W Evelyn Ave | Caltrain Station | 18 docks | N | N | N | N | N | Y | no upgrades required (if solar utilized); pavement cut and repair ( for electrical)
CMV002 | 2 | 1 | Transit Center | N | east of W Evelyn Ave(just east of MV001 location) | Caltrain Station | 9 docks | N | N | N | N | N | Y | no upgrades required (if solar utilized); pavement cut and repair ( for electrical)
CMV003 | 2 | 1 | Transit Center | N | east of W Evelyn Ave(just south of MV002 location) | Caltrain Station | 14 docks | N | N | N | N | N | Y | no upgrades required (if solar utilized); pavement cut and repair ( for electrical)
CMV004 | 3 | 1 | Transit Center | S | east of W Evelyn Ave | Caltrain Station | 15 docks | N | N | N | N | N | Y | no upgrades required (if solar utilized); pavement cut and repair ( for electrical)
CMV005 | 3 | 1 | Transit Center | S | east of W Evelyn Ave(just east of MV004 location) | Caltrain Station | 7 docks | N | N | N | N | N | Y | no upgrades required (if solar utilized); pavement cut and repair ( for electrical) Need to relocate bike racks
1. Only priority ranking 1 sites are being considered for the pilot program.
2. Assumes a kiosk at the station

## SJ Caltrain
Site ID | Priority Ranking1 | Readiness | Street Name | Side of Street | Nearest Cross-street | Closest Property | Station Length2 | Sidewalk | Parking Lane | Private Property | Historical Site | Environmental Issues | Construction Needed | Comments (If applicable, explain construction/ environmental issues)
CSJ001 | 1 | 1 | Crandall St | S | Cahill St (at southwest parking lot) | Caltrain Station | 30 docks | Y | N | N | Y | Y | N | On historical site (environmental issues)
CSJ002 | 2 | 2 | Cahill St | E | Crandall St (across from transit loading) | Caltrain Station | 30 docks | Y | N | N | Y | Y | Y | May need electrical connection On historical site (environmental issues)
CSJ003 | 2 | 2 | Caltrain Station | SE | Cahill St (adjacent to special parking) | Caltrain Station | 10 docks | Y | N | N | Y | Y | Y | Remove lawn, paving On historical site (environmental issues)
CSJ004 | 2 | 2 | Caltrain Station | SE | Cahill St (adjacent to special parking, just south of SJ003) | Caltrain Station | 10 docks | Y | N | N | Y | Y | Y | Remove lawn, paving On historical site (environmental issues)
CSJ005 | 3 | 2 | Cahill St | W | Crandall St | Caltrain Station | 12 docks | Y | N | N | Y | Y | Y | Remove lawn, paving On historical site (environmental issues)
1. Only priority ranking 1 sites are being considered for the pilot program.
2. Assumes a kiosk at the station

## Santa Clara VTA
Site ID | Priority Ranking | Readiness | Street Name | Side of Street | Nearest Cross-street | Closest Property | Station Length | Sidewalk | Parking Lane | Private Property | Historical Site | Environmental Issues | Construction Needed | Tentatively Approved (staff)? | Comments (If applicable, explain construction/ environmental issues) | Status
SJ001 | 1 | 1 | Crandall St | S | Cahill St (at southwest parking lot) | Caltrain Station | 40 docks | Y | N | N | Y | Y | N | Y | On historical site | R'cvd categorical exemption
SJ002 | 1 | 1 | Santa Clara St | SE | S. Almaden Ave | Citibank | 10-15 docks | Y | N | N | N | N | N | Y | Move bike rack, keep clear of utility box access | DOT Staff level approval
SJ003 | 1 | 1 | Almaden Blvd | W | W San Fernando St | Adobe HQ | 10 docks | Y | N | N | N | N | N | Y | Some tree shade; one bike space may need to remain vacant to clear a tree well | DOT Staff level approval; need to conduct courtesy outreach to Adobe
SJ004 | 1 | 1 | San Pedro St | E | St. John St. | San Pedro Public Market Square | 10 docks | Y | N | N | N | N | Y/N | Y | City will install concrete pad adjacent to sidewalk, and remove fence at sidewalk edge | DOT staff level approval
SJ005 | 1 | 1 | W San Carlos St | N | Market St. | Civic Center | 7-10 docks | Y | N | N | N | N | N | Y | Leave clear where sidewalk narrows | DOT staff level approval
SJ006 | 1 | 1 | Park Avenue | N | S. Market St | Bankof America | 10 docks | Y | N | N | N | N | N | Y | None | DOT staff level approval; need to conduct courtesy outreach to BofA
SJ007 | 1 | 1 | Fountain Alley |  | B/t 1st & 2nd St | Tangerine Hookah Bar | 15 docks | Y | N | N | N | N | N | Y | Alleyway location; move 1 or 2 planters | DOT staff level approval; planters belong to Dtwn. Association - requires outreach
SJ008 | 1 | 1 | Paseo de San Antonio | SW | 2nd Street | San Jose Repertory Theater/Rosies & Posies Flower Shop | 10 docks | N | N | N | N | N | N | Y | Plaza location; confirm ROW | DOT staff level approval
SJ009 | 1 | 1 | Paseo de San Antonio | SE | 3rd Street | San Jose Repertory Theater/Circle A Skate Shop | 10 docks | N | N | N | N | N | N | Y | Plaza location; confirm ROW | DOT staff level approval
SJ010 | 1 | 1 | SOFA (South of First Street Area) | W | San Carlos St | American Institute of Architects/Original Joe's | 10 docks | N | Y | N | N | N | N | Y | remove 2 on-street parking | DOT staff level approval; Coordinate with Downtown Association to remove 2 parking spaces
SJ011 | 1 | 1 | Fifth Street | W | Jackson St | Roy's Coffee Shop | 10 docks | N | Y | N | N | N | N | Y | remove 1 or 2 on-street parking | DOT staff level approval; need courtesy outreach to business owner
SJ012 | 1 | 1 | S 4th Street | E | E Santa Clara St | City Hall | 10-15 docks | Y | N | N | N | N | N | Y | None | DOT staff level approval & Senior Staff support; need to work with Facilities to get full support
SJ013 | 1 | 1 | E San Fernando | SE | 4th Street | MLK Library | 10-15 docks | Y | N | N | N | N | N | Y | Magazine rack relocation; keep clear width of utility boxes, manholes and sign posts | DOT staff level approval
SJ014 | 1 | 1 | 4th Streeet | E | San Carlos | Uchida Hall (SJSU) | 10 docks | Y | N | N | N | N | N | Y | None | DOT staff level approval
SJ015a | 1 | 1 | E San Fernando | N | 9th Street | SJSU North Parking Garage | 7-10 docks | Y | N | N | N | N | N | Y | DOT confirming ROW | DOT staff level approval
SJ015b | 1 | 1 | 9th Street | E | E San Fernando St | SJSU North Parking Garage | 10 docks | Y | N | N | N | N | N | Y | DOT confirming ROW | DOT staff level approval
MV001 | 1 | 1 | Transit Center | N | East of W Evelyn Ave | Caltrain Station | 18 docks | N | N | N | N | N | Y | Y | no upgrades required (if solar utilized); pavement cut and repair ( for electrical)
MV002 | 1 | 1 | Castro Street | N | Mercy Street | City Hall | 10 docks | N | N | N | N | N | N | Y | Plaza location; some shade; must curve around existing planters | Park & Rec want to be involved in final design
MV003 | 1 | 2 | Castro Street | SW | El Camino Real | Cognition Cyclery | 5-7 docks | Y | N | N | N | N | N | N | Optional location; City concerns w/ final design and aesthetics | Work w/ Economic & Planning Directors
MV004 | 1 | 1 | E Evelyn Ave | S | Pioneer Way | VTA Park n Ride Lot | 10 docks | Y | N | N | N | N | N | Y | Confirm w/ VTA staff
MV005 | 1 | 1 | Showers Drive | N | Latham Street | San Antonio Shopping Center (Walmart) | 10 docks | Y | N | N | N | N | N | Y | plaza parcels owned by several developers; install on sidewalk (City ROW)
MV006 | 1 | 2 | Showers Drive | N | Pacchetti Way | San Antonio Caltrain Station | 10 docks | N | N | N | N | N | N | N | install on level dirt; consider for 2nd phase | Work w/ JPB-Caltrain
MV007 | 1 | 1 | N Rengstorff Ave | W | W Middlefield Rd | Valero gas station | 5-7 docks | Y | N | N | N | N | N | Y | limited sidewalk width available
MV008 | 1 | 1 | Amphitheater Pkwy | N | Rengstorff /Charleston | Google Park Transit Stop | 5-7 docks | Y | N | N | N | N | N | Y | Google dedicated 25’ sidewalk easement to the City of Mtn. View
MV009 | 1 | 2 | Charleston Rd | N |  | Charleston Park | 5-7 docks | N | N | N | N | Y | N | Y | Park walkway or grass installation; can't remove bike racks | Coordinate w/ Parks on irrigation and exact placement
MV010 | 1 | 1 | La Avenida Ave | E | end of cul-de-sac | Stevens Creek Trail | 5-7 docks | N | N | N | N | N | N | Y | Street installation near entrance of trail
MV011 | 1 | 1 | E Middlefield Rd | N | Ellis Street | Middlefield Light Rail Station | 10 docks | Y | N | N | N | N | N | Y | Keep clear of plaza
PA001 | 1 | 1 | Alma Street | W | Lytton Ave | Caltrain Station | 17 docks | N | N | N | Y | Y | Y | Y | No upgrades required (with solar); pavement cut and repair (if electrical). Need to remove and relocate bike racks. On historical site (r'cvd categorical exemption)
PA002 | 1 | 1 | Alma Street | W | Lytton Ave (just south of PA001 location) | Caltrain Station | 13 docks | N | N | N | Y | Y | Y | Y | No upgrades required (with solar); pavement cut and repair (if electrical). Need to remove and relocate bike racks. On historical site (r'cvd categorical exemption)
PA003 | 1 | 1 | Ramona St | N | Hamilton Ave | City Hall | 15 docks | N | N | N | N | N | N | Y | Plaza location; ramp located around the corner; requires signage
PA004 | 1 | 1 | Emerson St | N | University Ave | Lytton Plaza | 5-7 docks | N | N | N | N | N | N | Y | Plaza location; remove u-racks; outreach to Friends of Lytton Plaza group; 3 alternate locationd are 2 on-street parking spaces or across the street at existing bike rack | requires approval from Park & Rec and Architectural Review Board
PA005 | 1 | 1 | University Ave | E | Emerson St | Palo Alto Bicycles | 5-7 docks | N | Y | N | N | N | N | Y | remove 1 on-street parking space; coordination with PA Bicycles
PA006 | 1 | 1 | University Ave | W | Cowper St | Bridge Bank | 5-7 docks | N | N | N | N | N | N | Y | remove bike racks; relocate trash can; courtesy outreach to Bridge Bank
PA007 | 1 | 2 | S California Ave | N | Park Blvd | Cal Ave Caltrain Station | 5-7 docks | N | Y | N | N | N | N | Y | remove one parking space and use the hatched area in parking lot | requires coordination w/ JPB-Caltrain
PA008 | 1 | 1 | Campus Drive |  | at Serra Mall on N/S Axis | Gates Computer Science Bldg (Stanford) | 5-7 docks | Y | N | Y | N | N | N | Y | Location near existing bike racks | Pending approval from Campus Administration
PA009 | 1 | 1 | Lagunita Dr |  | Tresidder Memorial Union at the Transit Circle | Tresidder Memorial Union in front of Braun Music Center-(Stanford) | 10 docks | Y | N | Y | N | N | N | Y | Coordinate with Zone Manager; near Marguerite shuttle drop-off | Pending approval from Campus Administration
PA010 | 1 | 1 | Galvez St |  | at Campus Drive | Stanford Visitor Center | 5-7 docks | Y | N | Y | N | N | N | Y | Requires coordination and approval from Athletic Dept | Pending approval from Campus Administration and Athletics

## Santa Clara VTA Additional Info
City | # Sites | Approval Process | Contacts | Fees | Identifying add'l sites
San Jose | 15 | City will facilitate process for acquiring encroachment permits through the Public Works Dept. Typically requires vendor to submit certificate insurance and completed encroachment permit application. Encroachment permits take 2 weeks to be issued. Traffic control plan will also be required for each location that will block traffic or close traffic lanes for installation. Staff can help turn around application/permit in 1 week, if necessary. Strategy is to bundle all locations under 1 encroachment permit. | John Brazil (Bike/Ped Program)
408-975-3206
John.Brazil@sanjoseca.gov
Zahir Gulzadah
|  |  | zahir.gulzadah@sanjoseca.gov | Waived
Mountain View | 8 | Take list of site locations to April 18th Transportation Committee Meeting then May City Council meeting for approval. Public ROW installation requires encroachment permits - staff level process. Environmental review will occur at the same time as the Council decision. Bundle all locations under 1 permit. | Helen Kim, Project Manager
650-903-6311
helen.kim@mountainview.gov
|  |  | Robert Kagiyama (DPW - Land Development) | waived
(650) 903-6311
Robert.kagiyama@mountainview.gov
Palo Alto | 9 | Encroachment permits needed. Need to go to BPAC and City Council for approval | Rafael Rius (Transportation Project Engineer)
|  |  | (650) 329-2305 | waived
Rafael.Rius@CityofPaloAlto.org
Stanford | 3 | Need: approval from administration for 3 site selections; MOU; special accommodations for pods due to university restrictions on corporate advertising; PCI compliant equipment; architectural review of final site plan/appearance. | Ariadne Delon Scott (Bicycle Program Coordinator) (650) 725-2453, adscott@stanford.edu | TBD