## Sheet1
Bill Strickland - Communications Schedule
Date | Task | Responsible Party | Task Executed Date
Week of Oct. 12 | Oct (Oct. 16) - Press release in IUP Reporter | Communications Staff - Michelle Fryling | 2009-10-15
Week of Oct. 19 | Oct. 16 - News post to Common Freshman Reader Website (re: general event announcement) | Communications Staff - Regan Houser | 2009-10-16
| Oct. 19 - IUP Daily (re: general event announcement) | Communications Staff - Web Team | 2009-10-16
| Oct. 21 - General announcement of event in Alumni Connections | Alumni Staff - Mary Morgan; information provided to M. Morgan by Elaine Smith | 2009-10-17
| Oct. 23 - General announcement of event (will go to all western PA media, including Pitts and Pitts TV) | Communications Staff - Michelle Fryling | 2009-10-23
| Oct. 23 - General announcement of event distributed via Social Media channels | Communications Staff - Web Team | 2009-10-23
Week of Nov. 2 | Email to Indiana Arts Council with PDF (provided by Dr. Luckey) | Communications Staff - Michelle Fryling | 2009-11-04
| Email to Downtown Indiana mailing list with PDF (provided by Dr. Luckey) | Communications Staff - Michelle Fryling | 2009-11-04
| Email to Chamber mailing list with PDF (provided by Dr. Luckey) | Communications Staff - Michelle Fryling | 2009-11-04
| Nov. 2 - Announcement of essay winners tied into Strickland appearance (will go to all western PA media, including Pitts and Pitts TV) | Communications Staff - Michelle Fryling | 2009-11-05
| Nov. 2 - News post to Common Freshman Reader website (re: essay winners tied to Strickland appearance) | Communications Staff - Regan Houser | 2009-11-03
| Nov. 3 - Announcement of event in IUP Daily (re: essay winners tied to Strickland appearance) | Communications Staff - Web Team | 2009-11-03
| Nov. 3 - Announcement of essay winners tied to Strickland appearance distributed via Social Media channels | Communications Staff - Web Team | 2009-11-03
| Renda "Indiana in the Morning" | Communications Staff - Michelle Fryling | 2009-11-03
Week of Nov. 9 | Nov. 12 - Press release in IUP Reporter | Communications Staff - Michelle Fryling | 2009-11-12
| Nov. 10 - Email inviting to University faculty and staff to attend strickland lecture | Communications Staff - Regan Houser | 2009-11-10
| Nov. 10 - Email inviting to University faculty and staff to attend strickland lecture | Communications Staff - Regan Houser | 2009-11-10
| Nov. 10 - News post to Common Freshman Reader website (inviting university community to lecture) | Communications Staff - Regan Houser | 2009-11-10
| Nov. 10 - Announcement of event in IUP Daily (inviting university community to lecture) | Communications Staff - Regan Houser | 2009-11-10
| Nov.12 - Announcement of Strickland's Phi Kappa Phi award tied to Nov. 17 event (will go to all western PA media, including Pitts and Pitts TV) | Communications Staff - Michelle Fryling | 2009-11-12
| Nov. 12 - News post to Common Freshman Reader website (re: Strickland's Phi Kappa Phi award tied to Nov. 17 event) | Communications Staff - Regan Houser | 2009-11-13
| Newspost - Fryling to promote Strickland visit on Renda | Communications Staff - Web team
| Nov. 13 - Announcement of event in IUP Daily (re: Strickland's Phi Kappa Phi award tied to Nov. 17 event) | Communications Staff - Web Team | 2009-11-13
| Nov. 13 - Announcement of Strickland's Phi Kappa Phi award tied to Nov. 17 event distributed via Social Media channels | Communications Staff - Web Team | 2009-11-13
Week of Nov. 16 | Renda "Indiana in the Morning" -- Nov. 16 with Gian Pagnucci | Communications Staff - Michelle Fryling | sent to webteam 11/11/09
| Nov. 16 - News post to Common Freshman Reader website (re: announcement Strickland on campus w/schedule of events; Join us Tuesday night) | Communications Staff - Regan Houser | Done
| Nov. 17 - Announcement of event in IUP Daily (re: announcement Strickland on campus w/schedule of events; Join us Tuesday night) | Communications Staff - Web Team | Done
| Nov. 17 - Announcement of Strickland on campus w/schedule of events; Join us Tuesday night distributed via Social Media channels. Also includes after-the-fact photo/caption to appear on website and Facebook. | Communications Staff - Web Team | Done
| Indiana Gazette interview with Strickland (tentative) -- Nov. 17 | Communications Staff - Michelle Fryling | Done
| Nov. 17 - Video services of lecture provided | Communications Staff - Bill Hamilton
| Nov. 17 - Audio recording services for podcast provided | Communications Staff - Ken Ciroli | Determined to be unnecessary, since we cannot distribute the file. (Added by Regan)
| Nov. 17 - PowerPoint background delivered to David Surtasky | Communications Staff - Stephanie Keppich
| Script for event | Michelle Fryling | completed 11/11/09
Please Note: The August, September, and October IUP Reporters carried press release information promoting Bill Strickland's Nov. 17 visit. Additionally, Press releases were also sent regionally to major media in March, April and August. Items in red identify deliverables/services in support of event.