## Sheet1
|  |  | Bonneville Power Administration Interconnection Request Queue |  |  |  |  | 04/24/2014 04:02
Note: Requests with queue positions lower than 200 were submitted prior to adoption of LGIP/SGIP.
Request Number | Request Date | Project Name | Requestor | State | County | Point of Interconnection | Status | Connection Type | In Service Date | Max Outputs Summer | Winter | Generation Facility Location | Interconnection Type | Generating Facility Type | Related Transmission Request | Comments | Reason Not Completed
L0369 | 2014-03-21 09:00 | South Fork Substation | Public Utility District No. 2 of Pacific County |  |  | BPA Raymond Substation | RECEIVED | LL | 2017-10-01
L0368 | 2014-03-12 15:00 | Lower Monumental Substation | BPA Power Services |  |  | Lower Monumental Substation | STUDY | LL | 2017-10-01
L0367 | 2014-03-04 14:39 | Rachel Road | City of Richland, Washington |  |  | BPA's Badger Canyon Substation | RECEIVED | LL | 2017-10-01 | [7 empty] | Awaiting decision from customer
G0497 | 2014-01-12 09:46 |  |  | ID | Cassia | Bridge Substation (or new substation nearby) | STUDY | GI | 2016-01-01 | 38 | 45 | Cassia County, Idaho | NRIS & ERIS | Geothermal
L0366 | 2014-01-10 10:00 | New Commercial Load | Blachly-Lane Electric Cooperative |  |  | Albany-Eugene 115kV #1, mile 37, between towers 4&5. | STUDY | LL | 2017-10-02
G0496 | 2013-12-12 10:00 |  |  | WA | Pend Oreille | Boundary Switchyard, Approximately 1 mile south of Boundary Powerhouse | WITHDRAWN | GI | 2014-03-30 | 70 | 70 | Boundary Powerhouse located at Pend Oreille River | ERIS | Hydro
G0495 | 2013-12-09 06:18 |  |  | WA | Clark | Troutdale, OR or Camas, WA | STUDY | GI | 2016-01-01 | 60 | 60 | 401 NE Adams Street, Camas WA 98607 | ERIS | Combined cycle |  | FES Report issued
L0365 | 2013-10-25 10:00 | Blue Lake | Portland General Electric Company |  |  | BPA's Troutdale Substation | STUDY | LL | 2017-06-01
L0364 | 2013-09-17 12:00 | Long Canyon | Wells Rural Electric Company |  |  | BPA's West Wendover Substation | STUDY | LL | 2017-10-01
L0363 | 2013-08-27 17:00 | Oregon LNG | LNG Development Company, LLC |  |  | BPA's Clatsop Substation | RECEIVED | LL | 2016-10-03 |  |  | Warrenton, OR
G0494 | 2013-08-22 12:41 |  |  | OR | Malheur | Harney Substation | STUDY | GI | 2015-05-01 | 3 | 3 | 43 degrees, 35' 6.38"N, 118 degrees 12' 33.17"W | ERIS | Hydro |  | Generator Nameplate Rating: 2.75 MW
G0493 | 2013-08-06 13:01 |  |  | ID | Cassia | At or near BPA's Bridge Substation. | STUDY | GI | 2016-01-01 | 30 | 30 | Cassia County, Idaho | NRIS & ERIS | Geothermal
G0492 | 2013-08-02 15:22 | Dworshak Fourth Unit | BPA Power Services | ID | Clearwater | Dworshak Substation. | STUDY | GI | 2019-07-01 | 300 | 300 | Dworshak Dam. | NRIS | Hydro |  | ISIS Report issued 2/4/2014, no impact
G0491 | 2013-07-29 09:04 |  |  | OR | Gilliam | Alkali Canyon Substation on BPA's Tower Road-Alkali Canyon 115 kV line. | COMPLETED | GI | 2014-03-01 | 7 | 7 | Arlington, OR | ERIS | Biogas
L0362 | 2013-07-22 10:00 | Neskowin Substation | Tillamook People's Utility District |  |  | BPA Tillamook-Boyer 115 kV Line | STUDY | LL | 2016-10-03
G0490 | 2013-07-05 15:05 |  |  | WA | Douglas |  | STUDY | GI | 2022-01-02 | 345 | 345 | Highway 155, Grand Coulee, WA 99133 | ERIS | Hydro |  | FAS Report issued 12/8/2013, no impact
L0361 | 2013-06-27 10:00 | Network Load Expansion Phase 2 | Northern Wasco County People's Utility District |  |  | Discovery Substation | STUDY | LL | 2015-10-01
L0360 | 2013-06-12 12:23 | EWEB Leaburg | Eugene Water & Electric Board |  |  | CUGR THUR1 28 1 A | STUDY | LL | 2015-10-01
G0489 | 2013-06-06 11:02 |  |  | OR | Gilliam | Low side of existing Wheatfield Wind Power Project, LLC 34.5 kV / 230 kV substation. | WITHDRAWN | GI | 2015-12-15 | 5 | 5 | Adjacent to Wheatfield Wind Power Project: 73501 Blalock Canyon Road, Arlington, OR 97812 | ERIS | Solar
L0359 | 2013-06-05 14:05 | PSE Cherry Point | Puget Sound Energy, Inc. |  |  | Loop in of BPA Intalco-Custer #1 230 kV line | STUDY | LL | 2017-03-01
G0488 | 2013-05-30 08:51 |  |  | ID | Gem |  | STUDY | GI | 2016-07-01 | 13 | 13 | Black Canyon Dam and Powerplant, 3999 E Black Canyon Hwy, Emmet, ID 83617 | ERIS | Hydro |  | This is a proposed 12.5 MW addition to a 10.2 MW generating capacity of an existing facility, making a combined total of 22.7 MW.
G0484 | 2013-05-07 09:20 |  |  | WA | Snohomish | BPA's Snohomish Substation | STUDY | GI | 2014-06-02 | 1 | 1 | Hardeson Substation | ERIS | Energy Storage
G0483 | 2013-05-01 08:10 |  |  | WA | Skamania | Trout Creek Field @ Wind River Business Park, Hemlock WA | COMPLETED | GI | 2014-05-01 | 3 | 3 | Wind River Business Park, Hemlock, WA | ERIS | Biomass |  | Generator Nameplate Rating: 2,165 kW
G0482 | 2013-04-30 14:06 |  |  | WA | Lewis | 11814 Hwy 12, Randle, WA 98377 | COMPLETED | GI | 2013-07-01 | 1 | 1 | 11814 Hwy 12, Randle, WA 98377 | ERIS | Hydro |  | Generator Nameplate Rating: 500 kW
G0481 | 2013-04-25 16:55 |  |  | WA | Snohomish | Snohomish PUD's 12 kV distribution system (Harbour Pointe circuit 12-2277) | COMPLETED | GI | 2013-08-01 | 2 | 2 | 4333 Harbour Point Boulevard SW | ERIS | Energy Storage |  | Generator Nameplate Rating: 1.5 MW
G0480 | 2012-12-10 09:55 |  |  | OR | Tillamook | TPUD Distribution System | COMPLETED | GI | 2013-05-30 | 2 | 2 | 6018 Hanger "A" Road | ERIS | Biomass
L0358 | 2012-11-23 10:36 | L0358 City of Ellensburg Helena Avenue Sub | City of Ellensburg |  |  | A proposed new Helena Avenue substation tap on the existing 115 kV East Ellensburg Tap approx. 2.1 miles before East Ellensburg Sub. | COMPLETED | LL | 2015-12-31 |  |  | 2201 N Chestnut St., Ellensburg, WA
L0357 | 2012-11-15 10:00 | UEC McNary 115KV Breaker 3 | Umatilla Electric Cooperative |  |  | BPA McNary Substation | COMPLETED | LL | 2015-10-01
G0479 | 2012-10-22 16:30 |  |  | OR | Lake | Tap of 115 kV BPA line between LaPine and Fort Rock. POI approx. 1 mile N of the Fort Rock Substation. | WITHDRAWN | GI | 2014-12-31 | 100 | 100 | 9 miles SE of Fort Rock | NRIS & ERIS | Solar
L0356 | 2012-09-25 14:00 | Benton REA Huard Road | Benton Rural Electric Association |  |  | Prosser Tap off Grandview to Snipes 115kV Line | STUDY | LL | 2015-10-01
L0355 | 2012-09-10 12:00 | Network Load Expansion | Northern Wasco County People's Utility District |  |  | Chenoweth-The Dalles 115 kV Line | COMPLETED | LL | 2015-10-01
G0478 | 2012-09-06 14:13 |  |  | OR | Morrow | BPA's proposed Longhorn 500/230 kV Substation. | STUDY | GI | 2016-11-01 | 500 | 500 | 20 to 25 miles south of Boardman | NRIS & ERIS | Wind
G0477 | 2012-09-05 08:48 |  |  | OR | Deschutes | Pilot Butte to LaPine transmission line | STUDY | GI | 2015-12-31 | 38 | 38 | 20 miles south of Bend | ERIS | Geothermal
L0354 | 2012-08-09 14:01 | Cowlitz John Street | Public Utility District No. 1 of Cowlitz County |  |  | BPA Lexington Substation | WITHDRAWN | LL | 2015-11-06 | [6 empty] | Withdrawn by Customer 2/1/13
L0351 | 2012-08-03 09:00 | PDX-1 and PDX-4 Data Centers - Phase 2 | Umatilla Electric Cooperative |  |  | BPA's Boardman Substation | COMPLETED | LL | 2015-11-02
L0352 | 2012-08-03 09:00 | PDX-2 Data Center - Phase 2 | Umatilla Electric Cooperative |  |  | BPA McNary | COMPLETED | LL | 2015-11-02
L0353 | 2012-08-03 09:00 | Hat Rock | Umatilla Electric Cooperative |  |  | BPA Hat Rock | WITHDRAWN | LL | 2015-11-02 | [6 empty] | Withdrawn by Customer
G0476 | 2012-07-18 09:53 | The Dalles Northshore Fishway Project | Northern Wasco County People's Utility District | OR | Wasco | Existing Interconnection Point at Spearfish Substation | CONFIRMED | GI | 2012-11-12 | 7 | 7 | The Dalles Dam, Northshore Fishway | ERIS | Hydro |  | On-line January 2013
L0350 | 2012-07-11 13:25 | Skokomish Substation | Public Utility District No. 1 of Mason County |  |  |  | CONFIRMED | LL | 2013-10-31
L0349 | 2012-07-05 10:00 | Canby Substation | PacifiCorp |  |  | BPA's Canby Substation | COMPLETED | LL | 2014-10-31
L0348 | 2012-06-25 09:00 | McNary 115kV Breaker | Umatilla Electric Cooperative |  |  | McNary Substation | COMPLETED | LL | 2015-10-01
G0475 | 2012-06-21 11:42 |  |  | WA | Walla Walla | Walla Walla Substation point of delivery #4048. | COMPLETED | GI | 2013-01-01 | 3 | 3 | 518 Mill Creek road | ERIS | Hydro
L0347 | 2012-05-29 09:00 | LNG Compressor Load | Columbia River People's Utility District |  |  | St. Johns-Allston 115kV | WITHDRAWN | LL | 2017-10-01 | 40 | 40 |  |  |  |  | Withdrawn by customer.
L0346 | 2012-05-18 09:00 | Airport Road | Consumers Power, Inc. |  |  | Albany-Lebanon 115kV #1 | STUDY | LL | 2013-11-01
L0345 | 2012-05-15 14:00 | Big Eddy-Redmond 230kV Line | Central Electric Cooperative, Inc. |  |  | BPA Big Eddy-Redmond #1 230kV Line | STUDY | LL | 2015-06-01
G0473 | 2012-05-12 16:41 |  |  | OR | Wasco | Wasco Electric Cooperative's 115 kV Line. | WITHDRAWN | GI | 2013-07-15 | 10 | 10 | Wasco, Oregon | ERIS | Wind |  | Withdrawn on October 7, 2013.
G0474 | 2012-05-12 16:41 |  |  | OR | Wasco | Wasco Electric Cooperative's 115 kV line. | WITHDRAWN | GI | 2013-07-15 | 10 | 10 | Wasco, Oregon | ERIS | Wind |  | Withdrawn on June 29, 2012.
G0471 | 2012-04-11 16:44 |  |  | WA | Klickitat | Harvalum 230 kV Substation | WITHDRAWN | GI | 2016-03-01 | 590 | 590 | Near Harvalum 230 kV Substation | ERIS | Combined cycle |  | Withdrawn on March 8, 2013.
G0470 | 2012-03-21 14:07 | RES Ag Biomass Project | RES - Ag FGO LLC | OR | Yamhill | Breaker 51 out of Booth Bend. | CONFIRMED | GI | 2012-10-15 | 1 | 1 | 5801 S.E. Bansen Lane, Dayton, Oregon | ERIS | Biomass
L0344 | 2012-03-15 09:00 | Slatt Substation | PacifiCorp |  |  | At or near Slatt Substation | WITHDRAWN | LL | 2015-10-01 | [6 empty] | LLIR withdrawn by customer on February 19, 2013.
G0469 | 2012-01-27 10:07 | Whitefish In-Line Hydroelectric Project | City of Whitefish, Montana | MT | Flathead | BPA's Flathead Substation | CONFIRMED | GI | 2012-08-07 | 1 | 1 | 300 Reservoir Road, Whitefish, MT | ERIS | Hydro |  | Generator Nameplate: 261 kW
L0340 | 2011-12-13 17:00 | DLB2 | Umatilla Electric Cooperative |  |  | Boardman or Longhorn | COMPLETED | LL | 2015-10-01 | 90 | 90
L0341 | 2011-12-13 17:00 | Maverick Data Center | Umatilla Electric Cooperative |  |  | Boardman | WITHDRAWN | LL | 2015-10-01 | 30 | 30 |  |  |  |  | Withdrawn by customer 8/3/2012
L0342 | 2011-12-13 17:00 | PDX1&4 Data Centers | Umatilla Electric Cooperative |  |  | Boardman | COMPLETED | LL | 2015-10-01 | 60 | 60
L0343 | 2011-12-13 17:00 | PDX2 | Umatilla Electric Cooperative |  |  | McNary | COMPLETED | LL | 2015-10-01 | 30 | 30
L0339 | 2011-12-07 09:42 | Bertelsen-Seneca Upgrade | Eugene Water & Electric Board |  |  | BPA Eugene Substation | COMPLETED | LL | 2014-12-01
G0468 | 2011-12-06 15:57 | Stoltze Land and Lumber Project | F.H. Stoltze Land and Lumber Co. | MT | Flathead | Flathead 12.5 kV Radial from Trumble Creek Substation. | CONFIRMED | GI | 2013-10-01 | 3 | 3 | 600 Halfmoon Road, Columbia Falls, MT | ERIS | Biomass |  | Generator Nameplate: 2.5 MW
L0338 | 2011-10-26 13:39 | Worden Substation | Columbia Rural Electric Association |  |  | BPA's Franklin-Walla Walla 115kV Line 13/6 | COMPLETED | LL | 2013-01-01 | [7 empty] | BPA workload
L0337 | 2011-10-24 09:18 | DLB1 | Umatilla Electric Cooperative |  |  | BPA's future Longhorn Substation | COMPLETED | LL | 2015-02-11 | 30 | 30
G0467 | 2011-10-19 14:42 |  |  | OR | Wasco | BPA's Maupin Substation from at or near Wasco's Antelope Substation. | WITHDRAWN | GI | 2015-12-31 | 101 | 101 | East of Highway 97 near the wotns of Shaniko and Antelope. | NRIS & ERIS | Wind |  | Withdrawn by Customer on December 19, 2011.
L0336 | 2011-10-05 15:37 | S. Tacoma-Southwest 230kV, Tacoma-Southwest 230kV | Tacoma Power |  |  | BPA Tacoma & BPA South Tacoma Substations | COMPLETED | LL | 2012-05-31
G0466 | 2011-10-04 10:36 | Sisters Irrigation Hydro Project | Three Sisters Irrigation District | OR | Deschutes | 68000 Hwy 20 W, Bend, OR 97701 | CONFIRMED | GI | 2013-09-03 | 1 | 1 | 68000 Hwy 20 West, Sisters, OR | ERIS | Hydro
G0465 | 2011-09-15 14:46 |  |  | OR | Wasco | Wasco Electric Cooperative's 115 kV line. | WITHDRAWN | GI | 2012-12-31 | 10 | 10 | Wasco County, Oregon | ERIS | Wind |  | Withdrawn on May 11,2012.
L0335 | 2011-09-13 09:43 | Project Maverick | Central Electric Cooperative, Inc. |  |  | BPA's Ponderosa Substation | COMPLETED | LL | 2012-10-01
G0464 | 2011-09-02 11:23 |  |  | WA | Clark | CPUD feeder connected to CPUD's King Station and closest BPA point of receipt is BPA's Ross Substation. | WITHDRAWN | GI | 2013-09-12 | 5 | 5 | Clark County, WA | ERIS | Biomass
G0463 | 2011-09-01 12:11 |  |  | OR | Lake, Harney | BPA's 230 kV transmission facilities at Ponderosa Substation. | WITHDRAWN | GI | 2014-12-31 | 400 | 400 | Glass Buttes, Wagontire Mountain. | NRIS & ERIS | Wind |  | Withdrawn on September 6, 2013.
G0462 | 2011-09-01 12:10 |  |  | OR | Lake, Harney | BPA's transmission facilities at Summer Lake Substation. | WITHDRAWN | GI | 2014-12-31 | 500 | 500 | Glass Buttes, Wagontire Mountain & Juniper Mountain. | NRIS & ERIS | Wind |  | Withdrawn by Customer on February 27, 2012.
G0461 | 2011-08-12 15:54 |  |  | OR | Wasco | Wasco Electric Cooperative's 115 kV Line. | WITHDRAWN | GI | 2012-12-31 | 10 | 10 | Substation will be adjacent to the Iberdrola School House Substation. | ERIS | Wind |  | Withdrawn on May 11,2012
L0334 | 2011-08-12 09:38 | Grand Coulee-Westside | Avista Corporation |  |  | BPA's Grand Coulee-Westside 230kV Transmission Line near mile 76, tower 3 | WITHDRAWN | LL | 2014-10-01 | [6 empty] | Withdrawn by Avista 11/20/12.
G0460 | 2011-08-10 15:32 |  |  | OR | Umatilla | BPA's McNary Substation. | WITHDRAWN | GI | 2015-01-01 | 220 | 220 | Umatilla County, Ore. approximately 2.5 miles SW of Hermiston. | NRIS & ERIS | Gas peaking generation |  | Withdrawn on September 6, 2013
G0459 | 2011-08-07 16:21 |  |  | OR | Linn | At a point on BPA's Albany-Salem 115 kV transmsission line within a mile either side of Conser Road. | WITHDRAWN | GI | 2013-05-01 | 65 | 45 | Millersburg, Ore. on the west side of the Old Salem Road. | NRIS & ERIS | Gas peaking generation |  | Withdrawn by Customer on December 20,2011.
L0333 | 2011-08-05 10:22 | La Grande Substation | Oregon Trail Electric Consumers Cooperative, Inc. |  |  | BPA's La Grande Substation | WITHDRAWN | LL | 2015-01-01 | [6 empty] | Withdrawn by Customer
G0458 | 2011-08-04 09:25 |  |  | OR | Union | Oregon Trail Electric Cooperative's Cove Avenue Substation | WITHDRAWN | GI | 2011-12-31 | 2 | 2 | Eastern OR University, 1 University Boulevard, La Grande, OR | ERIS | Solar |  | Withdrawn on May 2, 2012
G0457 | 2011-07-28 09:10 |  |  | OR | Morrow | Slatt substation. | COMPLETED | GI | 2015-05-01 | 36 | 36 | Boardman, Morrow Co. Oregon | NRIS | Combined cycle |  | Increment to Interconnection Request G0380; studies complete, contract offered.
L0332 | 2011-06-30 09:57 | Baldwin Data Center | Central Electric Cooperative, Inc. |  |  | BPA Ponderosa Substation | COMPLETED | LL | 2014-10-01
G0456 | 2011-06-08 15:35 |  |  | WA | Jefferson | At existing interconnection facilities in BPA's Fairmount Substation. | WITHDRAWN | GI | 2013-12-31 | 25 | 25 | At existing mill site, Mill Road, Port Townsend, Wash. | NRIS & ERIS | Biomass
G0455 | 2011-05-20 11:31 |  |  | OR | Morrow | In the area of Ione Substation/Kinger Tap. | WITHDRAWN | GI | 2014-12-31 | 50 | 50 | Between approximately 3 to 7 miles north of Ione, Oregon | NRIS & ERIS | Wind
L0331 | 2011-05-12 12:59 | CEC POD at Ponderosa | Central Electric Cooperative, Inc. |  |  | BPA Ponderosa Substation | COMPLETED | LL | 2014-10-01
G0454 | 2011-05-11 10:53 |  |  | OR | Morrow | Slatt Substation | WITHDRAWN | GI | 2012-12-01 | 20 | 20 | Morrow County, Oregon | ERIS | Wind
G0452 | 2011-05-09 10:45 |  |  | OR | Umatilla | BPA's McNary Substation at 500 kV. | STUDY | GI | 2015-06-01 | 410 | 390 | Next to Hermiston Generating Plant | NRIS & ERIS | Gas peaking generation |  | ISIS Report issued 10/10/2013
G0453 | 2011-05-06 11:53 | University of Oregon CoGeneration | University of Oregon | OR | Lane | EWEB's new U of O Substation | CONFIRMED | GI | 2012-06-01 | 11 | 11 | University of Oregon Campus | ERIS | Combined cycle |  | on-line September 2012
L0330 | 2011-04-28 09:00 | Addy | tester |  |  | BPA's Addy Substation | WITHDRAWN | LL | 2013-10-31 | [6 empty] | Withdrawn by customer 11/9/11.
L0329 | 2011-04-22 09:00 | Red Mountain-Reata 115kV/Dallas Road Substation | City of Richland, Washington |  |  | BPA's Red Mountain-Badger Canyon 115kV Transmission Line | STUDY | LL | 2013-10-31 | [7 empty] | Awaiting decision from customer.
L0327 | 2011-04-19 06:58 | Lower Snake Redundant PH Tie Lines | US Department of Army Corps of Engineers |  |  | Lower Monumental Little Goose Lower Granite | WITHDRAWN | LL | 2013-10-01
L0328 | 2011-04-14 11:20 | Ellensburg-Moxee Tap | Public Utility District No. 1 of Kittitas County |  |  | Columbia-Moxee 115kV Line | WITHDRAWN | LL | 2013-10-01 | [6 empty] | Withdrawn by customer 11/26/12
G0450 | 2011-03-16 16:04 | Tillamook Bay Methane | Farm Power Tillamook LLC | OR | Tillamook | Tillamook PUD's Feeder Circuit #63, connected to the Wilson River Substation. | CONFIRMED | GI | 2011-11-01 | 1 | 1 | The approximate location of the generating unit will be 45 deg. 26' 14" N, 123 deg. 48' 09" W | ERIS | Biomass
L0326 | 2011-03-07 14:46 | Ponderosa Substation | PAC |  |  | BPA Ponderosa Substation | CONFIRMED | LL | 2013-10-01
L0325 | 2011-02-15 10:41 | Alcoa Substation | Clark Public Utilities |  |  | BPA Alcoa Substation | COMPLETED | LL | 2013-09-01 | [7 empty] | BPA awaiting PRD changes
G0449 | 2011-02-11 15:01 | Tillamook Bay Methane | Farm Power Misty Meadow, LLC | OR | Tillamook | Tillamook PUD's Feeder Circuit #63, connected to the Wilson River Substation. | CONFIRMED | GI | 2011-11-01 | 1 | 1 | 45 deg.,27' 31" N, 123 deg.49' 36" W. | ERIS | Biomass
L0324 | 2011-01-10 11:47 | Knights Bridge Substation | Canby Utility Board |  |  | Knigts Bridge Rd & S. Barlow Rd (adjacent to PGE Canby Sub) | CONFIRMED | LL | 2013-10-01
G0447 | 2010-12-16 13:58 |  |  | OR | Morrow | A proposed new substation on BPA's McNary-Calpine 500 kV transmission line. | WITHDRAWN | GI | 2013-05-01 | 215 | 240 | 20 acre parcel in Section 11, T4N, R25 east of Willamette Meridian, bordering Boardman Substation. | NRIS & ERIS | Gas peaking generation |  | Withdrawn by Customer on November 19, 2011.
G0446 | 2010-12-16 13:57 |  |  | OR | Morrow | A proposed new substation on BPA's McNary-Coyote Springs 500 kV transmission line. | WITHDRAWN | GI | 2013-05-01 | 215 | 240 | 20 acre parcel in Section 11, T4N, R25 east of Willamette Meridian, bordering Boardman Substation. | NRIS & ERIS | Gas peaking generation |  | Withdrawn by customer; letter instructions received November 15, 2013.
L0323 | 2010-12-14 15:14 | Aurora Project | City of Richland, Washington |  |  | BPA Ashe Substation and Ashe-Coyote Springs Transmission Line | WITHDRAWN | LL | 2012-07-14 | [6 empty] | Withdrawn by customer 4/21/14
G0448 | 2010-12-13 11:12 |  |  | ID | Cassia | Idahome Substation | STUDY | GI | 2011-09-01 | 20 | 20 |  | ERIS | Wind
G0445 | 2010-12-06 10:09 |  |  | ID | Cassia | Idahome Substation | STUDY | GI | 2011-09-01 | 20 | 20 | Cassia County, Idaho | ERIS | Wind
G0441 | 2010-11-03 15:44 |  |  | WA | Franklin | Pole 66 G 129 at the Esquatzel Canal and Columbia River Road | COMPLETED | GI | 2011-02-01 | 2 | 2 | Esquatzel Division Canal, Franklin, WA | ERIS | Hydro
G0440 | 2010-11-02 16:52 |  |  | OR | Umatilla | Direct connect to Umatilla Electric Cooperative's distribution and through Butter Creek Substation to McNary Substation. | COMPLETED | GI | 2011-12-31 | 10 | 10 | Ward Butte | ERIS | Wind
G0439 | 2010-11-02 10:55 | Coffin Butte Biogas | JC-Biomethane LLC | OR | Lane | Blachly-Lane Electric Cooperative's Parker Substation | CONFIRMED | GI | 2011-10-31 | 2 | 2 | Junction City, Lane County, Oregon | ERIS | Biogas |  | on-line
G0443 | 2010-10-22 16:59 |  |  | ID | Cassia | Canal to Minidoka BPA 13.8kV line, 6-8 miles south of Minidoka. | WITHDRAWN | GI | 2011-12-31 | 20 | 20 | Delco Idaho Along Freeway East of Burley, Idaho just past the I-82 Y towards Utah. | ERIS | Wind
G0442 | 2010-10-22 16:57 |  |  | ID | Cassia | Canal to Minidoka BPA 13.8kV line, 6-8 miles South of Minidoka Dam | WITHDRAWN | GI | 2011-12-31 | 20 | 20 | Delco Idaho Along Freeway East of Burley, Idaho just past the I-82 Y towards Utah. | ERIS | Wind
G0438 | 2010-10-15 10:38 |  |  | OR | Polk and Lincoln | On BPA's Salem-Grande Ronde-Tillamook line in the vicinity of Grande Ronde Substation. | WITHDRAWN | GI | 2013-10-01 | 125 | 125 | Near Grande Ronde, Ore. | NRIS & ERIS | Wind
G0437 | 2010-09-30 14:13 |  |  | OR | Lake | BPA's Harney 115 kV transmission line | STUDY | GI | 2013-12-31 | 30 | 38 | 50 miles NW of Burns | ERIS | Geothermal |  | FAS Draft Report issued 1-31-2014, still in review with customer
L0322 | 2010-09-29 14:18 | Klondike/Blalock Reinforcement | Wasco Electric Cooperative, Inc. |  |  | BPA's DeMoss 115kV Substation | STUDY | LL | 2014-07-01 | [7 empty] | BPA awaiting project determinations
L0321 | 2010-09-29 13:56 | Fossil-Big Eddy Loop | Wasco Electric Cooperative, Inc. |  |  | 69kV loop from Fossil to Maupin and Maupin to Big Eddy | WITHDRAWN | LL | 2013-07-01 | [6 empty] | Withdrawn effective April 9, 2013
G0436 | 2010-09-27 13:16 |  |  | OR | Morrow and Umatilla | At 500 kV to BPA's 500 kV transmission line from McNary to Hermiston, at the point where ownership changes. | WITHDRAWN | GI | 2014-12-31 | 481 | 481 | East of Heppner, NW of Ukiah, 6 miles west of Hway 395 and 2 miles south of Hway 74. | NRIS & ERIS | Wind
G0444 | 2010-09-10 09:50 |  |  | WA | Cowlitz | Existing interconnection facilities in Cowlitz PUD service area. | WITHDRAWN | GI | 2011-10-01 | 35 | 35 |  | NRIS & ERIS | Biomass
G0435 | 2010-08-27 14:13 |  |  | OR | Morrow | New substation on 500 kV McNary-HPP Line | STUDY | GI | 2013-11-01 | 238 | 238 | 20-25 miles South of Boardman | NRIS & ERIS | Wind |  | Comprehensive FAS issued 3/7/2014 | Awaiting Customer Permits to complete NEPA Review
L0320 | 2010-08-23 15:49 | Woodland Tap | Public Utility District No. 1 of Cowlitz County |  |  | BPA Woodland Tap, Ross-Lexington 230kV Line | WITHDRAWN | LL | 2012-10-01 | [6 empty] | Request withdrawn by customer on 10/24/12.
G0434 | 2010-08-19 13:49 |  |  | OR | Linn | At generator breaker, on new 12.47 kV bus A-3. Bus A-3 will be tied to mill bus A-1 through mill switchgear. Main breaker at A-1 is owned by EPUD. Emerald PUD Facility | WITHDRAWN | GI | 2012-03-01 | 11 | 11 | Linn County, Oregon | ERIS | Biomass |  | Withdrawn on January 28, 2011.
G0433 | 2010-08-02 10:24 | Outback | Outback Solar, LLC | OR | Lake | Midstate Electric 24.9 kV distribution system | CONFIRMED | GI | 2010-11-15 | 1 | 1 | Lake County, Oregon | ERIS | Solar
G0432 | 2010-07-08 13:21 |  |  | WA | Kittitas | BPA's Bettas Road 230 kV Substation (currently under construction). | COMPLETED | GI | 2012-12-01 | 18 | 18 | Eight miles NW of Ellensburg, Wash. | ERIS | Wind |  | Incremental to Request No. G105. May 25, 2011: reduced from 31 to 18 MW | Customer Delayed
G0431 | 2010-06-30 14:47 |  |  | OR | Lake | Fort Rock Substation | COMPLETED | GI | 2012-06-29 | 20 | 20 | Christmas Valley | ERIS | Solar |  | Awaiting Customer permits
G0430 | 2010-05-14 12:48 |  |  | WA | Benton | Red Mountain Substation | WITHDRAWN | GI | 2013-12-31 | 200 | 200 | In the area of Badger Canyon immediately south of Red Mountain Substation. | NRIS & ERIS | Wind |  | Withdrawn by customer by letter received May 4, 2011. | Withdrawn by customer by letter received May 4, 2011.
G0429 | 2010-05-06 17:08 |  |  | OR | Wasco | BPA's 230 kV Maupin-Redmond Transmission Line. | WITHDRAWN | GI | 2012-12-31 | 135 | 135 |  | NRIS & ERIS | Wind
G0428 | 2010-05-06 12:23 |  |  | OR | Morrow | New substation on 500 kV McNary-HPP Line | COMPLETED | GI | 2014-12-01 | 201 | 201 | Five to Ten miles east Heppner | NRIS & ERIS | Wind |  | Comprehensive FAS issued 3/7/2014 | Awaiting Customer Permits to complete NEPA Review
G0427 | 2010-04-30 14:26 |  |  | OR | Wheeler | TBD | WITHDRAWN | GI | 2013-04-01 | 300 | 300 | Approximately 6 miles North of Spray, Oregon. | NRIS & ERIS | Wind |  | Withdrawn by Customer on June 18, 2010.
G0426 | 2010-04-23 12:34 |  |  | WA | Mason | BPA's transmission facilities in or near Shelton substation. | WITHDRAWN | GI | 2013-06-01 | 31 | 31 | Shelton, Mason Co. Wash. | ERIS | Biomass |  | Withdrawn by Customer on March 17, 2011.
G0424 | 2010-04-22 11:34 |  |  | OR | Lake | Summer Lake substation. | WITHDRAWN | GI | 2013-12-31 | 103 | 103 | Approximately 40 miles west of Burns, Ore. | ERIS | Wind |  | Withdrawn on September 27, 2010.
G0425 | 2010-04-22 11:34 |  |  | OR | Lake | Summer Lake Subtstation. | WITHDRAWN | GI | 2013-12-31 | 103 | 103 | Approximately 40 miles west of Burns, Ore. | ERIS | Wind |  | Withdrawn on September 27, 2010.
G0423 | 2010-04-09 14:37 |  |  | OR | Grant | 115 kV BPA De Moss-Big Eddy line (4.2 miles west of De Moss Substation) | WITHDRAWN | GI | 2011-07-26 | 10 | 10 |  | ERIS | Wind
G0422 | 2010-04-09 13:07 |  |  | OR | Wheeler | Fossil Substation | WITHDRAWN | GI | 2013-04-01 | 100 | 100 | Approximately 1.5 miles east of Fossil, Ore. | NRIS & ERIS | Wind |  | Withdrawn by Customer on June 18, 2010, following Scoping Meeting.
G0420 | 2010-04-06 12:58 |  |  | WA | Klickitat | BPA's proposed Wood Creek Substation | COMPLETED | GI | 2012-12-01 | 60 | 60 |  | Energy | Wind |  | FAS Study Issued 5/16/2013 | Awaiting Customer Permits to complete NEPA Review
G0421 | 2010-04-05 07:16 |  |  | OR | Douglas | BPA's Gardiner Substation via Douglas Electric Cooperative's Transmission/Distribution Facility. | STUDY | GI | 2012-06-01 | 2 | 2 | Sparrow Park Road (nearest road to Reedsport OPT Wave Park project, located approx. 2.7 miles offshore of Reedsport, Oregon) | ERIS | Wave
G0419 | 2010-04-01 14:22 |  |  | WA | Clallam | At the 69kV bus in BPA's Port Angeles Substation. | COMPLETED | GI | 2012-04-30 | 20 | 20 | Marine Drive, Port Angeles. | NRIS | Biomass |  | Awaiting Customer permits
G0418 | 2010-03-29 10:50 |  |  | OR | Morrow | Ione Substation | COMPLETED | GI | 2011-06-15 | 20 | 20 | Morrow County, Oregon | ERIS | Wind |  |  | Customer Delayed
G0417 | 2010-03-25 10:31 |  |  | UT | Box Elder | Into the Wendover-Minidoka 138 kV transmission line. | WITHDRAWN | GI | 2013-10-01 | 50 | 50 | Near Curlew, Utah. | NRIS & ERIS | Wind |  | Request reduced to 50 MW per letter received on January 3, 2011.
G0416 | 2010-03-23 18:04 |  |  | OR | Lake | To BPA's Transmission Facilities through the 115 kV facilities of Midstate Electric Cooperative. Midstate Electric Coop 115 kV line | COMPLETED | GI | 2012-09-30 | 20 | 20 | Approximately four miles northwest of the Town of Christmas Valley, Ore. | NRIS & ERIS | Solar |  | effective July 30, 2010, G0416 seeks interconnection of a reduced nameplate generating capacity of 20 MW (in lieu of 75 MW). | Integration - Customer Delayed
G0415 | 2010-03-22 11:21 |  |  | OR | Clatsop | BPA's 115 kV Transmission Facilities at or near Fern Hill Substation. | WITHDRAWN | GI | 2012-04-01 | 20 | 20 | Clatsop County, Oregon | ERIS | Biomass |  | Withdrawn on January 28, 2011
G0413 | 2010-03-19 09:28 |  |  | OR | Lake | BPA's Summer Lake Substation at 230 kV | WITHDRAWN | GI | 2012-12-31 | 103 | 103 | Lake Co. Ore. approx 40 miles west of Burns. | NRIS & ERIS | Wind |  | Withdrawn by Customer on September 1, 2011.
G0414 | 2010-03-19 09:28 |  |  | OR | Lake | BPA's Summer Lake Substation at 230 kV | WITHDRAWN | GI | 2012-12-31 | 103 | 103 | Lake Co. Ore. approximately 40 miles west of Burns. | NRIS & ERIS | Wind |  | Withdrawn by Customer on September 1, 2011.
G0412 | 2010-03-12 14:37 |  |  | ID | Cassia | Minidoka-Unity 138 kV line | WITHDRAWN | GI | 2011-12-01 | 20 | 20 | Cassia County, Idaho | ERIS | Wind |  | Withdrawn on April 13, 2010
G0411 | 2010-03-12 14:35 |  |  | ID | Cassia | Minidoka-Unity 138 kV line | WITHDRAWN | GI | 2011-12-01 | 20 | 20 | Cassia, Idaho | ERIS | Wind |  | Withdrawn on April 13, 2010
G0409 | 2010-02-26 09:20 |  |  | OR | Lake | TO THE MIDSTATE ELECTRIC 24.9 KV DISTRIBUTION SYSTEM ON THE EAST BORDER OF THE PROPERTY, ALONG OIL DRI ROAD. | COMPLETED | GI | 2010-12-07 | 5 | 5 | LAKE COUNTY, OR | ERIS | Solar |  | Awaiting Customer permits | Integration - Agreement executed
G0410 | 2010-02-26 09:20 |  |  | OR | Lake | TO THE MIDSTATE ELECTRIC 24.9 KV DISTRIBUTION SYSTEM ON THE WEST BORDER OF THE PROPERTY, ALONG FOSSIL LAKE ROAD. | COMPLETED | GI | 2010-12-07 | 5 | 5 | APPROXIMATELY 8.9 MILES EAST-NORTHEAST OF CHRISTMAS VALLEY, OREGON. | ERIS | Solar |  | Awaiting Customer permits. | Integration - Agreement executed
G0408 | 2010-02-09 09:43 |  |  | OR | Umatilla | New substation on 500 kV McNary-HPP Line | COMPLETED | GI | 2012-12-01 | 400 | 400 | Ten miles SW of Pendleton | NRIS & ERIS | Wind |  | Comprehensive FAS issued 3-7-2014 | Awaiting FAS review meeting
G0407 | 2010-02-04 09:41 | Coastal Energy Project | Coastal Energy Project, LLC | WA | Grays Harbor | Grays Harbor PUD 15 kV Distribution Pole Number P1/64 | CONFIRMED | GI | 2010-05-17 | 6 | 6 | Grayland, Washington | ERIS | Wind |  | on-line June 2010
G0406 | 2010-02-01 15:08 |  |  | WA | Klickitat | BPA’s Big Eddy-McNary 230 kV Transmission Line in Klickitat County, Wash. | WITHDRAWN | GI | 2012-12-31 | 99 | 99 | Klickitat Co. Wash. | ERIS | Wind |  | Withdrawn by Customer on September 14, 2010.
G0405 | 2010-01-29 12:45 |  |  | ID | Madison | BPA’s Goshen-Drummond No. 1 161 kV Transmission Line in Madison Co. Idaho | WITHDRAWN | GI | 2010-11-30 | 240 | 240 | Madison Co. Idaho, east of Rexburg adjacent to BPA’s Transmission Line. | NRIS | Wind |  | Withdrawn by Customer on November 1, 2010.
G0403 | 2010-01-27 16:51 |  |  | OR | Morrow | New substation on 500 kV McNary-HPP Line | STUDY | GI | 2014-11-01 | 302 | 302 | 20-25 miles south of Boardman | NRIS | Wind |  | Comprehensive FAS issued 3/7/2014 | Awaiting FAS review meeting
G0404 | 2010-01-27 16:51 |  |  | OR | Morrow | New substation on 500 kV McNary-HPP Line | STUDY | GI | 2014-11-01 | 302 | 302 | 20-25 miles south of Boardman | NRIS | Wind |  | Comprehensive FAS issued 3/7/2014 | Awaiting FAS review meeting
G0402 | 2010-01-12 09:19 |  |  | OR | Sherman | BPA’s Transmission Facilities at or close to John Day Substation. | WITHDRAWN | GI | 2013-10-01 | 110 | 110 | Sherman County, OR | ERIS | Wind |  | Withdrawn on July 1, 2013
G0401 | 2010-01-11 11:44 |  |  | OR | Wasco | 230 kV Big Eddy - Maupin or Buckley 500 kV | STUDY | GI | 2013-12-31 | 299 | 299 | Wasco County, OR | NRIS & ERIS | Wind |  | FAS Study Issued 9/16/2011 | Awaiting Customer Permits to complete NEPA Review
G0400 | 2010-01-06 09:23 |  |  | OR | Lake | 115 kV Fort Rock Line(between LaPine Substation and Midstate’s Fort Rock Substation) | WITHDRAWN | GI | 2011-12-31 | 20 | 20 | Lake County, OR | ERIS | Solar |  | Withdrawn on January 5, 2011
G0399 | 2009-12-16 15:00 |  |  | OR | Morrow | The 69 kV transmission system of Columbia Basin Electric Cooperative, approximately 15 line miles from BPA’s Ione Substation | WITHDRAWN | GI | 2010-08-01 | 10 | 10 | Morrow, Ore. | Energy | Biomass |  | Withdrawn on July 21, 2010
G0397 | 2009-12-15 09:31 |  |  | WA | Klickitat | BPA’s Goldendale-Chenoweth Transmission Line at 115 kV | WITHDRAWN | GI | 2011-12-31 | 202 | 202 | One mile west of Centerville, Wash. | Energy | Wind |  | Withdrawn by Customer on September 14, 2010.
G0398 | 2009-12-15 09:31 |  |  | WA | Klickitat | BPA’s Transmission Facilities at or near Centerville, Wash. at 230 kV | WITHDRAWN | GI | 2011-12-31 | 101 | 101 | Klickitat County, Wash. one mile west of Centerville | Energy | Wind |  | Withdrawn by Customer on April 29, 2010.
L0318 | 2009-12-14 13:39 | McNary Substation | Umatilla Electric Cooperative |  |  |  | WITHDRAWN | LL | 2012-09-01 | [6 empty] | Request withdrawn by customer 9/19/11
L0317 | 2009-12-14 13:30 | Decatur Island Tap | Orcas Power & Light Cooperative |  |  |  | COMPLETED | LL | 2013-09-01
G0396 | 2009-11-30 16:07 |  |  | WA | Klickitat | BPA’s transmission facilities in/near Goldendale, Wash. | WITHDRAWN | GI | 2013-01-01 | 56 | 56 | Klickitat Co., Wash. | NRIS | Wind |  | Withdrawn on November 19, 2012
G0394 | 2009-11-24 12:49 |  |  | OR | Deschutes | BPA’s Lapine Substation | COMPLETED | GI | 2012-03-01 | 28 | 28 | Deschutes Co. Ore. | NRIS | Biomass |  | FAS Study Issued 11/21/2011 | Awaiting Customer Permits to complete NEPA Review
G0395 | 2009-11-23 14:37 |  |  | ID | Cassia | Minidoka-Unity 138 kV line | STUDY | GI | 2010-10-15 | 20 | 20 | Cassia County, Idaho | ERIS | Wind
G0393 | 2009-11-17 09:30 |  |  | WA | Kittitas | 345 kV Rocky Reach - Maple Valley transmission line | WITHDRAWN | GI | 2010-12-15 | 75 | 75 | Kittitas County, Wash. | NRIS | Solar |  | Withdrawn on 4/8/2014
G0392 | 2009-11-09 08:49 |  |  | OR | Gilliam | 345 kV Rocky Reach - Maple Valley transmission line | WITHDRAWN | GI | 2013-12-01 | 300 | 300 | Gilliam Co. Ore. | NRIS | Wind |  | Withdrawn on October 24, 2012 | Awaiting Customer Permits to complete NEPA Review
G0391 | 2009-11-03 16:44 |  |  | OR | Gilliam | BPA’s Transmission Facilities on the Slatt-Buckley or Ashe-Marion transmission lines approx. 9 miles SW of Slatt | WITHDRAWN | GI | 2013-03-01 | 425 | 425 | Gilliam Co. Ore., east of Olex, 16 miles south of Arlington. | NRIS | Wind |  | Withdrawn by Customer on February 25, 2014.
G0389 | 2009-11-02 12:02 |  |  | OR | Morrow | New Substation near McNary 500 kV | STUDY | GI | 2013-11-01 | 207 | 207 | 20-25 miles south of Boardman | NRIS | Wind |  | Comprehensive FAS issued 3/7/2014 | Awaiting FAS review meeting
G0390 | 2009-11-02 12:02 |  |  | OR | Morrow | New Substation near McNary 500 kV | STUDY | GI | 2013-11-01 | 207 | 207 | 20-25 miles south of Boardman | NRIS | Wind |  | Comprehensive FAS issued 3/7/2014 | Awaiting FAS review meeting
G0388 | 2009-11-02 10:45 |  |  | ID | Cassia | BPA’s Idahome Substation | STUDY | GI | 2010-10-15 | 20 | 20 | Cassia County, Idaho | ERIS | Wind
G0386 | 2009-10-28 08:47 |  |  | WA | Garfield | BPA’s Pomeroy Substation | WITHDRAWN | GI | 2011-12-01 | 20 | 20 | Garfield County, Washington | ERIS | Wind |  | Withdrawn by Customer on June 1, 2011.
G0387 | 2009-10-26 15:49 |  |  | OR | Lake | Midstate Electric 24.9kV distribution system at Christmas Valley Substation | COMPLETED | GI | 2009-12-31 | 10 | 10 | Lake County, Oregon | ERIS | Solar |  |  | Integration - Customer Delayed
G0385 | 2009-10-08 11:07 |  |  | OR | Lake | Midstate Electric’s Fort Rock Substation at 115 kV at the 115 kV bus | COMPLETED | GI | 2011-12-01 | 15 | 15 | Lake County, Oregon | ERIS | Solar |  | Integration; Studies completed | Integration - Customer Delayed
G0383 | 2009-10-06 09:06 |  |  | WA | Pacific | Raymond 115 kV Substation | COMPLETED | GI | 2012-12-31 | 100 | 100 | Pacific County, Wash. | NRIS | Wind |  | FAS Study Issued 8/4/2012 | Awaiting Customer Permits to complete NEPA Review
G0384 | 2009-10-06 09:06 |  |  | OR | Coos | Bandon 115 kV Substation | WITHDRAWN | GI | 2011-06-01 | 101 | 101 | Coos County, Ore. | NRIS | Wind |  | Withdrawn by Customer on July 12, 2010.
G0382 | 2009-09-21 14:51 |  |  | WA | Yakima & Benton | At BPA’s Midway 230 kV substation | WITHDRAWN | GI | 2012-10-30 | 100 | 100 | Yakima and Benton Counties, Wash. | NRIS | Wind |  | Withdrawn by Customer on March 31, 2011.
G0381 | 2009-09-21 09:19 |  |  | OR | Harney | On Harney Electric Cooperative’s 115 kV transmission system approximately 30 miles south of Burns, Ore. | WITHDRAWN | GI | 2012-12-31 | 103 | 103 | Harney Co. Oregon. | ERIS | Wind |  | Withdrawn by Customer on September 1, 2011.
G0380 | 2009-09-15 09:40 | Carty CCCT | Portland General Electric Company | OR | Morrow | 500 kV Slatt Substation | CONFIRMED | GI | 2014-05-01 | 413 | 464 | Boardman, Morrow Co. Oregon. | NRIS | Combined cycle |  | FAS Issued 3/8/2012, NEPA CX issued | Contract offered; construction underway
G0379 | 2009-09-02 15:30 |  |  | OR | lake | Midstate Electric 24.9 kV distribution system | COMPLETED | GI | 2010-07-30 | 4 | 4 | Lake County, Oregon | ERIS | Solar |  | Integration, Study issued 5/12/2010
L0316 | 2009-08-28 14:25 | McNary Substation | PacifiCorp |  |  | BPA's McNary Substation | COMPLETED | LL | 2011-10-01 | [7 empty] | Waiting for McNary transformer addition.
L0314 | 2009-08-27 09:25 | Merchant Txm Line-Townsend | Tonbridge Power Inc |  |  | BPA Colstrip line at or near Townsend, MT | STUDY | LL | 2013-10-01 | [7 empty] | Awaiting WECC path review
L0315 | 2009-08-27 09:25 | Merchant Txm Line-Garrison | Tonbridge Power Inc |  |  | BPA Colstrip 500kV Line at Garrison Substation | STUDY | LL | 2013-10-01 | [7 empty] | Awaiting WECC path review
G0378 | 2009-08-27 09:22 |  |  | WA | Mason | BPA’s Substation at Shelton, Wash. | WITHDRAWN | GI | 2012-12-31 | 65 | 65 | Shelton, Mason Co. Wash. | ERIS | Biomass |  | Withdrawn by Customer on March 18, 2011
L0313 | 2009-08-20 11:34 | Bridge Substation | Raft River Rural Electric Cooperative, Inc. |  |  | BPA's Bridge Substation | WITHDRAWN | LL | 2010-11-01 | [7 empty] | Project cancelled by customer
L0311 | 2009-08-10 16:53 | Lancaster Substation | Avista Corporation |  |  | Lancaster 230 | CONFIRMED | LL | 2012-09-01
L0312 | 2009-08-10 10:48 | Bell-Boundary #1 230 kV | Inland Power & Light Company |  |  | Bell-Boundary #1 transmission line. | CONFIRMED | LL | 2011-10-01 |  |  | Spokane Washington
G0376 | 2009-08-06 10:09 |  |  | OR | Lake | Midstate Electric 24.9 kV distribution system | COMPLETED | GI | 2010-07-30 | 4 | 4 | Lake County, Oregon | ERIS | Solar |  | Integration, Study Issued 3/12/10
G0377 | 2009-08-06 10:09 | Outback | Outback Solar, LLC | OR | Lake | Midstate Electric 24.9 kV distribution system | CONFIRMED | GI | 2010-07-30 | 4 | 4 | Lake County, Oregon | ERIS | Solar |  | Integration; on-line November 2012
L0310 | 2009-07-30 14:52 | Mount Adams Substation | Yakama Power |  |  | Feeder #2 out of BPA's Alfalfa Substation | CONFIRMED | LL | 2009-12-01
G0375 | 2009-07-14 13:18 |  |  | WA | Klickitat | BPA’s proposed Wood Creek 230 kV Substation | WITHDRAWN | GI | 2011-10-01 | 50 | 50 | Klickitat Co. Wash. | ERIS | Wind |  | Withdrawn on September 17, 2012
G0374 | 2009-06-30 09:53 | Horse Butte Wind | Horse Butte Wind I LLC | ID | Bonneville | 115 kV Goshen-Palisades transmission line | CONFIRMED | GI | 2010-12-31 | 100 | 100 | Bonneville County, Idaho | NRIS | Wind |  | on-line August 2012
G0373 | 2009-06-29 10:27 |  |  | MT | Flathead & Lincoln | 230 kV Libby-Haskill line | WITHDRAWN | GI | 2012-04-30 | 200 | 200 | Flathead and Lincoln Counties, Montana | NRIS | Wind |  | Withdrawn on June 5, 2013
G0371 | 2009-06-03 14:15 |  |  | WA | Grays Harbor | TBA | WITHDRAWN | GI | 2012-12-31 | 65 | 65 | Satsop, Grays Harbor Co. Wash. | ERIS | Biomass |  | Withdrawn on May 4, 2010
G0372 | 2009-06-03 14:15 |  |  | ID | Latah | TBA | WITHDRAWN | GI | 2012-12-31 | 65 | 65 | In the vicinity of Bovill, Latah Co. Idaho | ERIS | Biomass |  | Withdrawn by Customer on June 14, 2010.
G0369 | 2009-06-02 12:55 |  |  | WA | Benton | BPA's Red Mountain Substation. | WITHDRAWN | GI | 2012-12-31 | 65 | 65 | Benton Co. Wash. | ERIS | Wind |  | Withdrawn by Customer on September 8, 2011.
G0368 | 2009-06-01 12:04 |  |  | OR | Wasco | Maupin 230 kV substation | COMPLETED | GI | 2013-08-01 | 101 | 101 | Wasco County, Ore. | NRIS | Wind |  | FAS Issued 4/27/2011 | Awaiting Customer Permits to complete NEPA Review
G0367 | 2009-06-01 12:03 |  |  | OR | Wasco | Maupin 230 kV substation | COMPLETED | GI | 2012-12-01 | 202 | 202 | Wasco County, Ore. | NRIS | Wind |  | FAS Study Issued 4/27/2011 | Awaiting Customer Permits to complete NEPA Review
G0370 | 2009-06-01 10:39 | Young’s Creek Hydro Project | Public Utility District No. 1 of Snohomish County | WA | Snohomish | Sultan Substation | CONFIRMED | GI | 2010-12-31 | 8 | 8 | Monroe, Washington | ERIS | Hydro |  | on-line December 2010
G0366 | 2009-05-18 14:41 |  |  |  |  | New Substation near McNary 500 kV. | COMPLETED | GI | 2014-11-01 | 302 | 302 | Morrow County, Ore. | NRIS | Wind |  | FAS Study Issued 7/6/2011 | Awaiting Customer Permits to complete NEPA Review
G0365 | 2009-05-18 14:40 |  |  |  |  | New Substation near McNary 500 kV. | COMPLETED | GI | 2013-11-01 | 302 | 302 | Morrow County, Ore. | NRIS | Wind |  | FAS Study Issued 11/1/2012 | Awaiting Customer Permits to complete NEPA Review
L0309 | 2009-05-18 14:01 | Benton City Substation | Benton Rural Electric Association |  |  | Grandview-Red Mountain #1 115kV | CONFIRMED | LL | 2012-11-01 |  |  | Benton County, WA
L0308 | 2009-05-18 10:43 | Transmission Reinforcement | Peninsula Light Company |  |  | Shelton-Kitsap 115kV Line | COMPLETED | LL | 2012-11-01 |  |  | Mason County, WA |  |  |  |  | Awaiting customer permitting.
G0364 | 2009-04-24 13:41 |  |  | WA | Kittitas | TBD | WITHDRAWN | GI | 2011-12-31 | 50 | 50 | Kittitas Co. Wash. | NRIS | Biomass |  | Withdrawn by Customer on August 7, 2009.
G0363 | 2009-04-03 15:40 |  |  | OR | Gilliam | New Substation near McNary 500 kV. | COMPLETED | GI | 2012-11-01 | 204 | 204 | Morrow County, Ore. | NRIS | Wind |  | Study Issued 11/1/2012 | Awaiting Customer Permits to complete NEPA Review
G0362 | 2009-04-03 15:39 |  |  | OR | Gilliam | New Substation near McNary 500 kV | COMPLETED | GI | 2012-11-01 | 204 | 204 | Morrow and Gilliam Counties, Ore. | NRIS | Wind |  | FAS Study Issued 7/6/2011 | Awaiting Customer Permits to complete NEPA Review
G0361 | 2009-04-02 15:29 |  |  | OR | Umatilla | New substation on 500 kV McNary-HPP Line | COMPLETED | GI | 2011-10-01 | 201 | 201 | Morrow County, Ore | NRIS | Wind |  | FAS Study Issued 12/22/2010 | Awaiting Customer Permits to complete NEPA Review
G0360 | 2009-03-25 11:26 |  |  | WA | Grays Harbor | Grays Harbor PUD’s 15 kV Distribution line | WITHDRAWN | GI | 2009-07-01 | 6 | 6 | Grayland, WA | ERIS | Wind |  | Withdrawn on December 16, 2009.
G0359 | 2009-03-25 09:53 |  |  | OR | Umatilla | Sacajawea 115 kV Substation | WITHDRAWN | GI | 2012-10-01 | 101 | 101 | Umatilla County, Ore. | NRIS | Wind |  | Withdrawn by Customer on February 27, 2012.
G0358 | 2009-03-24 09:13 | Flathead LFGTE Project | Flathead Electric Cooperative, Inc. | OR | Flathead | Flathead’s LaSalle Substation | CONFIRMED | GI | 2009-05-01 | 2 | 2 | Flathead County, Montana | ERIS | Biogas |  | on-line June 2009
G0357 | 2009-03-18 20:10 |  |  | OR | Harney | Diamond Junction near the Harney-Catlow line | WITHDRAWN | GI | 2010-12-31 | 104 | 104 | Harney County, Ore. | NRIS | Wind |  | Withdrawn by Customer on October 4, 2010.
L0307 | 2009-03-16 11:02 | Flathead Substation 230kV Bay | Flathead Electric Cooperative, Inc. |  |  | BPA's Flathead Substaion 230kV | CONFIRMED | LL | 2010-11-01 |  |  | Flathead County, Montana
G0356 | 2009-03-09 15:49 |  |  | MT | Wheatland | 500kV Broadview-Townsend transmission line | WITHDRAWN | GI | 2015-12-31 | 200 | 200 | Near Ringling, Montana | NRIS | Wind |  | Withdrawn by Customer on June 26, 2012.
G0355 | 2009-03-09 15:47 |  |  | MT | Meagher | 500kV Broadview-Townsend transmission line | WITHDRAWN | GI | 2014-12-31 | 200 | 200 | Near Ringling, Montana | NRIS | Wind |  | Withdrawn by Customer on June 26, 2012.
G0354 | 2009-03-09 15:45 |  |  | MT | Meagher | 500kV Broadview-Townsend transmission line | WITHDRAWN | GI | 2014-12-31 | 200 | 200 | Near Ringling, Montana | NRIS | Wind |  | Withdrawn by Customer on June 26, 2012.
G0353 | 2009-03-09 15:42 |  |  | MT | Meagher | 500kV Broadview-Townsend transmission line. | WITHDRAWN | GI | 2013-12-31 | 200 | 200 | Meagher and Wheatland Counties, near Ringling, Montana | NRIS | Wind |  | Withdrawn by Customer on June 26, 2012.
L0306 | 2009-02-17 12:38 | Dayton Substation | Columbia Rural Electric Association |  |  | Walla Walla-Tucannon 115kV Line | CONFIRMED | LL | 2011-10-01 |  |  | Columbia County, WA
L0305 | 2009-02-06 09:32 | Westside Phase II | City of Idaho Falls |  |  | BPA's Westside Substation | WITHDRAWN | LL | 2011-10-01 |  |  | Bonneville County, Id. |  |  |  |  | Project was cancelled.
G0352 | 2009-01-26 16:09 |  |  | OR | Coos | Reedsport-Fairview 115 kV transmission line | WITHDRAWN | GI | 2013-12-31 | 120 | 120 | Coos County, Ore. | ERIS | Combined cycle |  | Withdrawn by Customer on April 12, 2010. 8/12/09: FES review meeting held; FES report available on request. ISIS completed. April 12, 2010: Following review of the ISIS report, customer withdrew the Request by letter.
G0350 | 2008-12-02 09:34 |  |  | WA | Klickitat | BPA's Harvalum 230 kV substation | WITHDRAWN | GI | 2099-01-01 | 1200 | 1200 | Klickitat County, Wash. | NRIS | Energy Storage |  | Withdrawn by Customer on January 12, 2009.
G0351 | 2008-12-02 09:34 |  |  |  |  | BPA's Rock Creek substation | WITHDRAWN | GI | 2099-01-01 | 1200 | 1200 | Klickitat County, Wash. | NRIS | Energy Storage |  | Withdrawn November 28, 2012
G0349 | 2008-11-18 09:23 | Senaca Sawmill | Blachly-Lane Electric Cooperative | OR | Blachly Lane | Blachly Lane Substation | CONFIRMED | GI | 2010-10-01 | 20 | 20 | Eugene, Oregon | N/A | Biomass |  | on-line
G0348 | 2008-10-23 08:52 |  |  | OR | Umatilla | Umatilla Electric Cooperative’s 12.47kV Line, Pole #3N 27E 138000 | WITHDRAWN | GI | 2008-12-31 | 2 | 2 | Umatilla County, Oregon | Energy | Wind |  | Withdrawn on October 29, 2010
G0347 | 2008-09-24 12:43 |  |  | OR | Harney | Harney Electric Cooperative's Harney-Fields 115 kV transmission line. Withdrawn by Customer on February 20, 2009. | WITHDRAWN | GI | 2013-12-31 | 76 | 76 | Harney County, Ore. In T37S, T38S and T39S | NRIS | Wind |  | Withdrawn on Febuary 20, 2009
G0346 | 2008-09-24 12:42 |  |  | OR | Harney | Harney Electric Cooperative's Harney-Fields 115 kV transmission line. Withdrawn by Customer on February 20, 2009. | WITHDRAWN | GI | 2013-12-31 | 76 | 76 | Harney County, Ore. In T37S, T38S and T39S | NRIS | Wind |  | Withdrawn on February 20, 2009
L0304 | 2008-09-24 11:14 | Saddleback Mountain Interconnection | Public Utility District No. 1 of Klickitat County |  |  | BPA's Midway-North Bonneville 230kV Line | WITHDRAWN | LL | 2010-10-01 |  |  | Skamania County, OR
G0345 | 2008-09-16 09:50 |  |  |  |  | Big Eddy-Redmond 230 kV line | COMPLETED | GI | 2010-08-30 | 201 | 201 | Wasco County, Ore. | ERIS | Wind |  | FAS Study Issued 8/8/2010 | Awaiting Customer Permits to complete NEPA Review
G0344 | 2008-09-04 09:35 |  |  |  |  | At BPA's Slatt Substation | STUDY | GI | 2011-09-01 | 488 | 488 | Gilliam and Morrow Counties, Ore. | NRIS | Wind
L0302 | 2008-09-03 12:15 | Tower Road Substation | Umatilla Electric Cooperative |  |  | BPA's Boardman-Alkali 115kV Line | WITHDRAWN | LL | 2010-09-01 |  |  | Morrow County, OR
L0303 | 2008-09-03 12:15 | Port of Morrow Substation | Umatilla Electric Cooperative |  |  | BPA's Boardman-Tower Rd 115kV Line | WITHDRAWN | LL | 2010-09-01 |  |  | Morrow County, OR |  |  |  | Request withdrawn by customer 9/19/11
G0343 | 2008-09-02 09:33 |  |  | OR | Wasco | BPA's Big Eddy-Maupin 230 kV transmission line | WITHDRAWN | GI | 2010-12-01 | 107 | 107 | Wasco County, Ore. | NRIS | Wind |  | Withdrawn by Customer on June 9, 2009.
G0341 | 2008-08-27 09:17 |  |  | OR | Morrow | At a point on BPA's Boardman to Ione 69 kV line approximately 6 miles south of Boardman, Ore. | WITHDRAWN | GI | 2012-10-01 | 200 | 200 | Morrow County, Ore. | NRIS | Wind |  | Deemed Withdrawn on April 5, 2011. Customer did not meet terms of LGIP, Section 3.3.5.
G0342 | 2008-08-27 09:17 |  |  | OR | Gilliam | New Substation near Slatt 500 kV. | STUDY | GI | 2011-10-01 | 200 | 200 | Gilliam County, Ore. | NRIS | Wind |  | Re-study underway | Awaiting Customer Permits to complete NEPA Review
G0340 | 2008-08-07 19:42 |  |  | WA | Grant | Midway-Rocky Ford 230 kV Transmission line | WITHDRAWN | GI | 2011-12-31 | 185 | 185 | Grant County, Wash | NRIS | Wind |  | Withdrawn on July 30, 2013
G0338 | 2008-07-28 16:05 |  |  | OR | Umatilla | Walla Walla-Pendleton 69 kV line | WITHDRAWN | GI | 2013-12-31 | 100 | 100 | Umatilla County, Ore. | NRIS | Wind |  | Withdrawn on January 24, 2013
G0339 | 2008-07-28 16:05 |  |  | OR | Umatilla | Walla Walla-Pendleton 69 kV line | WITHDRAWN | GI | 2013-12-31 | 152 | 152 | Umatilla County, Ore. | NRIS | Wind |  | Withdrawn by Customer on August 31, 2009.
G0337 | 2008-07-11 14:49 |  |  | WA | Klickitat & Yakima | New substation on BPA's 500 kV McNary-John Day 500 kV line | WITHDRAWN | GI | 2011-10-01 | 200 | 200 | Klickitat Co. & Yakima Co., Wash. | NRIS | Wind |  | Withdrawn by Customer on June 10, 2009.
G0336 | 2008-07-11 14:48 |  |  | WA | Klickitat & Yakima | New substation on BPA's 500 kV McNary-John Day 500 kV line | WITHDRAWN | GI | 2011-10-01 | 200 | 200 | Klickitat Co. & Yakima Co., Wash. | NRIS | Wind |  | Withdrawn by Customer on June 10, 2009.
L0301 | 2008-07-03 09:31 | Spearfish Substation Expansion | Public Utility District No. 1 of Klickitat County |  |  | BPA's Chenoweth-Goldendale 115kV Line | WITHDRAWN | LL | 2010-10-01
L0300 | 2008-06-20 11:28 | Pinecreek Substation | Okanogan County Public Utility District No. 1 |  |  | Omak-Tonasket #1 & #2 Txm Line, Twr 11/1 | CONFIRMED | LL | 2009-09-01 |  |  | Okanogan County, WA
L0299 | 2008-06-18 11:00 | Skamania PUD Transmission Reinforcement | Public Utility District #1 of Skamania County |  |  | BPA's Midway-N.Bonneville 230kV line in the vicinity of Underwood Substation. | WITHDRAWN | LL | 2010-10-01 |  |  | Sherman County, OR
G0334 | 2008-05-30 09:18 |  |  |  |  | New Substation near Slatt 500 kV. | STUDY | GI | 2010-10-01 | 300 | 300 | Gilliam County, Oregon | NRIS | Wind |  | Re-study underway | Awaiting Customer Permits to complete NEPA Review
G0333 | 2008-05-20 16:08 |  |  | OR | Wasco | Big Eddy-Maupin 230 kV line | WITHDRAWN | GI | 2010-12-01 | 200 | 200 | Wasco County, Oregon | NRIS | Wind |  | Withdrawn by Customer on March 19, 2009.
G0332 | 2008-05-19 15:41 | King Estate Solar Generator Project | Lane Electric Cooperative, Inc. | OR | Lane | Integrating in Lane Electric Coop's system (Fox Hollow Substation) | CONFIRMED | GI | 2008-12-01 | 1 | 1 | Lane County, OR | NRIS | Solar |  | on-line November 2009
L0298 | 2008-05-14 12:50 | NorthernLights Transmission Project | NorthernLights Transmission, Inc. |  |  | BPA's Buckley Substation | WITHDRAWN | LL | 2014-05-01 |  |  | Sherman County, OR
G0328 | 2008-05-12 16:28 |  |  | WA | Garfield | At a point on BPA's 500 kV Little Goose-Lower Granite Transmission line in Garfield Co, Wash. | WITHDRAWN | GI | 2012-07-01 | 252 | 252 | Garfield Co. Wash. | ERIS | Wind |  | Withdrawn on July 12, 2013
G0329 | 2008-05-12 16:28 |  |  | WA | Garfield | At a point on BPA's 500 kV Little Goose-Lower Granite Transmission line in Garfield Co, Wash. | WITHDRAWN | GI | 2013-08-01 | 252 | 252 | Garfield Co. Wash. | ERIS | Wind |  | Withdrawn on July 12, 2013
G0330 | 2008-05-12 16:28 |  |  | WA | Garfield | At a point on BPA's 500 kV Little Goose-Lower Granite Transmission line in Garfield Co, Wash. | WITHDRAWN | GI | 2014-10-01 | 116 | 116 | Garfield Co. Wash. | ERIS | Wind |  | Withdrawn by Customer on August 1, 2011.
G0327 | 2008-05-09 13:30 | Columbia Ridge Landfill | WM Renewable Energy, LLC | OR | Gilliam | At or near Alkali Substation | CONFIRMED | GI | 2009-01-01 | 7 | 7 | Gilliam County, Oregon | Energy | Biomass |  | on-line December 2009
G0326 | 2008-05-05 16:29 |  |  | UT | Box Elder | At BPA's 138 kV Bridge Substation | COMPLETED | GI | 2010-06-30 | 42 | 42 | Box Elder County, Utah | NRIS | Wind |  | FAS Study Issued 8/17/2010 | Awaiting Customer Permits to complete NEPA Review
G0325 | 2008-04-29 12:25 |  |  | WA | Grant | A point on BPA’s Midway-Rocky Ford 230kV line | WITHDRAWN | GI | 2011-12-31 | 130 | 130 | Grant County, Washington | NRIS | Wind |  | Withdrawn by Customer on March 5, 2009.
L0297 | 2008-04-24 10:00 | Data Center | Umatilla Electric Cooperative |  |  | BPA's McNary, Hatrock or Boardman Substation | WITHDRAWN | LL | 2010-09-01 |  |  | Umatilla or Morrow County, OR
L0296 | 2008-04-18 11:00 | Sunriver | Midstate Electric Cooperative, Inc. |  |  | BPA LaPine-Pilot Butte 230kV Line | COMPLETED | LL | 2012-09-01 |  |  | Deschutes County, Oregon |  |  |  |  | Awaiting customer permitting
L0295 | 2008-04-17 15:57 | St.Johns-Allston Interconnection | Columbia River People's Utility District |  |  | St.Johns-Allston 115kV Line | COMPLETED | LL | 2012-10-01 |  |  | Columbia County, OR
L0294 | 2008-04-14 09:34 | New Commercial/Industrial Substation | Blachly-Lane Electric Cooperative |  |  | Between BPA Parker and Junction City Substations | COMPLETED | LL | 2010-09-01 |  |  | Lane County, OR |  |  |  | All studies for this request are complete (3/30/10).
G0324 | 2008-04-08 13:55 |  |  | WA | Garfield | BPA's Tucannon River-North Lewiston No. 1 115 kV transmission line | WITHDRAWN | GI | 2010-12-01 | 300 | 300 | Garfield County, Washington | NRIS | Wind |  | Withdrawn on February 26, 2010
G0323 | 2008-04-08 13:53 |  |  | OR | Sherman | New Substation near John Day 500 kV Substation | COMPLETED | GI | 2011-12-01 | 300 | 300 | Sherman County, Oregon | NRIS | Wind |  | FAS Study Issued 9/20/2009 | Awaiting Customer Permits to complete NEPA Review
L0293 | 2008-04-08 08:19 | Vantage Substation | PacifiCorp |  |  | BPA Vantage Substation | STUDY | LL | 2009-09-01 |  |  | Grant County, WA |  |  |  |  | Awaiting customer permitting process
G0322 | 2008-04-07 08:55 |  |  | WA | Klickitat | At a point in BPA's Harvalum Substation, at 230 kV | WITHDRAWN | GI | 2009-12-31 | 51 | 51 | Klickitat County, Wash. | ERIS | Wind |  | Withdrawn on June 3, 2008
L0292 | 2008-04-01 09:10 | Bakers Corner Tap | Public Utility District No. 1 of Cowlitz County |  |  | Lexington-Longview 115 kV Line | CONFIRMED | LL | 2009-09-01 |  |  | Cowlitz County, WA |  |  |  | Studies complete
G0321 | 2008-03-27 15:19 |  |  | WA | Grays Harbor | Satsop 230 kV | WITHDRAWN | GI | 2010-06-01 | 290 | 295 | Grays Harbor County, Wash. | NRIS | Combined cycle |  | Withdrawn by Customer on March 5, 2010. On February 20, 2009, Customer was notified that the FES Report would be delayed until March 27, 2009, to allow more detailed study of line routings and constraints for a preferred plan of service.
L0291 | 2008-03-27 14:59 | Chenowith Tap | Northern Wasco County People's Utility District |  |  | Big Eddy - Chenowith 115 kV | WITHDRAWN | LL | 2009-09-01 |  |  | Wasco County, Or
G0318 | 2008-03-27 14:38 |  |  | WA | Klickitat | Goldendale 115 kV | WITHDRAWN | GI | 2010-07-01 | 20 | 20 | Klickitat County, Wash. | Energy | Wind |  | Withdrawn by Customer on March 8, 2012.
G0319 | 2008-03-27 14:38 |  |  | WA | Klickitat | Goldendale 115 kV | WITHDRAWN | GI | 2010-07-01 | 20 | 20 | Klickitat County, Wash. | Energy | Wind |  | Withdrawn by Customer on March 8, 2012.
G0320 | 2008-03-27 14:38 |  |  | WA | Klickitat | Goldendale 115 kV | WITHDRAWN | GI | 2010-07-01 | 20 | 20 | Klickitat County, Wash. | Energy | Wind |  | Withdrawn by Customer on March 8, 2012.
L0290 | 2008-03-27 12:58 | Ethanol Facility | Public Utility District No. 1 of Franklin County |  |  | Franklin Substation | WITHDRAWN | LL | 2009-09-01 |  |  | Franklin County, Wa
G0335 | 2008-03-20 09:20 | W Hill Landfill Gas Plant | Public Utility District No. 1 of Klickitat County | WA | Klickitat | Roosevelt 115 kV | CONFIRMED | GI | 2010-09-01 | 17 | 17 | Klickitat County, WA | Energy | Biogas |  | on-line October 2011
G0317 | 2008-03-17 12:05 | Libby 6th Unit | BPA Power Services | MT | Lincoln | Existing T-3 at the Libby Project | WITHDRAWN | GI | 2010-09-07 | 120 | 120 | Lincoln County, Montana at Libby Dam. | NRIS | Hydro |  | Withdrawn by Customer on April 9, 2010.
L0289 | 2008-03-17 09:41 | Gardiner-Reedsport | Central Lincoln People's Utility District |  |  | Gardiner Substation | COMPLETED | LL | 2009-09-01 |  |  | Douglas County, Or |  |  |  | Studies complete | Waiting for cust to receive permits.
L0288 | 2008-03-14 13:00 | Industrial Park | Columbia Rural Electric Association |  |  | Franklin-Walla Walla 115 kV/Sacajawea Sub | WITHDRAWN | LL | 2009-09-01 |  |  | Walla Walla, Wa.
G0316 | 2008-03-12 10:11 |  |  | OR | Yamhill | 230 kV Tillamook-Carlton line | WITHDRAWN | GI | 2011-07-01 | 100 | 100 | Yamhill County, Oregon | ERIS | Wind |  | Withdrawn February 9, 2009
G0315 | 2008-03-03 11:25 |  |  | WA | Lewis | 115 kV line at Pe Ell Substation | WITHDRAWN | GI | 2012-12-01 | 150 | 150 | Lewis County, Washington | NRIS | Wind |  | Withdrawn February 9, 2009
G0314 | 2008-02-29 16:21 |  |  |  |  | Noxon-Hot Springs 230 kV line near Thompson Falls, MT | COMPLETED | GI | 2010-07-01 | 95 | 95 | Sanders County, Montana | NRIS | Hydro |  | FAS Study Issued 12/8/2009 | NEPA in progress
G0313 | 2008-02-07 14:57 |  |  | WA | Lewis | Lewis County PUD facilities near BPA's 115 kV Pe Ell Substation | COMPLETED | GI | 2011-12-01 | 128 | 128 | Lewis County, Washington | NRIS | Wind |  | FAS Study Issued 11/1/2010 Integration project. | Customer delayed
L0286 | 2008-02-05 11:00 | Mt. Si | Puget Sound Energy, Inc. |  |  | Tanner 115 kV Tap | WITHDRAWN | LL | 2009-01-01 |  |  | King County, Wa. |  |  |  | Project name formerly Tanner Tap
L0287 | 2008-02-05 11:00 | Novelty Substation | Puget Sound Energy, Inc. |  |  | Monroe-Sammamish 230 kV Line | WITHDRAWN | LL | 2009-09-01 |  |  | King County, Wa.
G0309 | 2008-01-29 10:33 |  |  | WA | Klickitat & Yakima | New substation on BPA's 500 kV McNary-John Day line | WITHDRAWN | GI | 2011-10-01 | 200 | 200 | Klickitat and Yakima Counties, Washington | NRIS | Wind
G0310 | 2008-01-29 10:33 |  |  | WA | Klickitat & Yakima | New substation on BPA's 500 kV McNary-John Day line near Alderdale, Washington | WITHDRAWN | GI | 2011-10-01 | 200 | 200 | Klickitat and Yakima Counties, Washington | NRIS | Wind
G0311 | 2008-01-29 10:33 |  |  | OR | Klickitat & Yakima | New substation on BPA's 500 kV McNary-John Day line near Roosevelt and Alderdale, Washington | WITHDRAWN | GI | 2011-10-01 | 200 | 200 | Klickitat and Yakima Counties, Washington | NRIS | Wind |  | Withdrawn on July 30, 2013
G0312 | 2008-01-29 10:33 |  |  | WA | Klickitat & Yakima` | New substation on BPA's 500 kV McNary-John Day line near Alderdale, Washington | WITHDRAWN | GI | 2011-10-01 | 200 | 200 | Klickitat and Yakima Counties, Washington | NRIS | Wind |  | Withdrawn on July 30, 2013
G0307 | 2008-01-28 10:52 |  |  | OR | Gilliam | A 500 kV interconnection in Gilliam County, Oregon | WITHDRAWN | GI | 2011-10-01 | 250 | 250 | Gilliam County, Oregon | NRIS | Wind
G0308 | 2008-01-28 10:52 |  |  |  |  | A 500 kV interconnection in Gilliam County, Oregon | WITHDRAWN | GI | 2012-10-01 | 250 | 250 | Gilliam County, Oregon | NRIS | Wind
G0306 | 2008-01-24 16:39 |  |  | OR | Harney Lake Crook Deschutes | BPA's Harney/Redmond transmission line near Harney. | WITHDRAWN | GI | 2009-12-01 | 600 | 600 | Harney, Lake, Crook and Deschutes Counties, Oregon | NRIS | Wind |  | Withdrawn by Customer on October 6, 2008.
G0305 | 2008-01-18 09:58 |  |  | OR | Union | BPA's 230 kV LaGrande Substation | WITHDRAWN | GI | 2010-01-15 | 200 | 200 | Union County, Oregon | ERIS | Wind |  | Withdrawn on September 2, 2010
L0285 | 2008-01-15 11:12 | McNary Substation | PacifiCorp |  |  | McNary Substation | WITHDRAWN | LL | 2010-12-01 |  |  | Umatilla County, Or
G0304 | 2008-01-09 12:09 |  |  | OR | Harney | BPA's Harney/Redmond transmission line near Harney | WITHDRAWN | GI | 2009-12-01 | 416 | 416 | Harney County, Oregon | NRIS | Wind |  | Withdrawn by Customer on December 15, 2009.
L0284 | 2008-01-09 09:07 | Merchant Transmission Line | Green Pacific Highway, LLC |  |  | Merchant Transmission Line | WITHDRAWN | LL | 2009-07-01 | 0 | 0 | Columbia County, OR
G0301 | 2008-01-08 16:00 |  |  | OR | Harney | BPA's Harney/Redmond transmission line near Harney | WITHDRAWN | GI | 2009-12-01 | 104 | 104 | Harney County, Oregon | NRIS | Wind |  | Withdrawn by Customer on December 13, 2012.
G0302 | 2008-01-08 16:00 |  |  | OR | Harney | BPA's Harney/Redmond transmission line near Harney | WITHDRAWN | GI | 2010-12-01 | 104 | 104 | Harney County, Oregon | NRIS | Wind |  | Withdrawn by Customer on October 4, 2010.
G0303 | 2008-01-08 16:00 |  |  | OR | Harney | BPA's Harney/Redmond transmission line near Harney | WITHDRAWN | GI | 2011-12-01 | 104 | 104 | Harney Ccounty, Oregon | NRIS | Wind |  | Withdrawn by Customer on October 4, 2010.
G0300 | 2007-12-18 08:47 |  |  | OR | Crook | At a point on BPA's Brasada-Harney 115 kV transmission line | COMPLETED | GI | 2010-10-30 | 104 | 104 | Deschutes & Crook Counties, Oregon | ERIS | Wind |  | FAS Study Issued 7/1/2009 | Awaiting Cusotmer Permits to complete NEPA Review
L0283 | 2007-12-17 10:50 | Kalispell Substation | Flathead Electric Cooperative, Inc. |  |  | BPA Kalispell Substation 115kV Bay #9 | WITHDRAWN | LL | 2009-06-01 |  |  | Flathead County, MT
G0331 | 2007-12-17 09:30 |  |  | OR | Harney | Harney-Brasada 115 kV line near Hampton Substation | COMPLETED | GI | 2009-07-01 | 8 | 8 | Harney Co. Oregon | ERIS | Wind |  | FAS Study Issued March 29, 2008 | Awaiting Customer Permits to complete NEPA Review
G0299 | 2007-11-19 17:10 |  |  | WA | Columbia | BPA’s Lower Granite/Little Goose 500 kV line | WITHDRAWN | GI | 2010-12-15 | 300 | 300 | Columbia County, WA | ERIS | Wind |  | Withdrawn by Customer on March 11, 2008
G0298 | 2007-11-19 17:03 |  |  | WA | Columbia | Little Goose 500 kV Substation | WITHDRAWN | GI | 2009-12-15 | 300 | 300 | Columbia County, WA | ERIS | Wind |  | Withdrawn by Customer on March 11, 2008
G0297 | 2007-11-01 11:46 | Biglow Canyon Wind Farm Addition | Portland General Electric Company | OR | Sherman |  | CONFIRMED | GI | 2009-10-01 | 50 | 50 | Sherman County, Oregon | ERIS | Wind |  | on-line May 2010 (combined with Phase 3 of G099 for 125 MW)
G0296 | 2007-10-29 08:45 |  |  | OR | Morrow | BPA's McNary-Roundup 230 kV line | WITHDRAWN | GI | 2012-10-01 | 300 | 300 | Morrow County, Oregon | NRIS | Wind |  | Withdrawn on November 17, 2008
G0294 | 2007-10-25 09:06 |  |  | WA | Columbia & Garfield | Central Ferry Substation | COMPLETED | GI | 2011-12-31 | 250 | 250 | Columbia County, Washington | NRIS | Wind |  | Site Permits, NEPA complete; LGIA pending, future install
G0295 | 2007-10-25 09:06 |  |  | WA | Columbia & Garfield | A new 230/500 kV substation on BPA’s Lower Granite-Little Goose transmission line. | COMPLETED | GI | 2011-12-31 | 250 | 250 | Garfield County, Washington | NRIS | Wind |  | Site Permits, NEPA complete, LGIA pending, future install
G0293 | 2007-10-24 13:50 |  |  |  |  | BPA's LaGrande 230 kV Substation | WITHDRAWN | GI | 2015-10-01 | 200 | 200 | Union County, Oregon | NRIS | Wind |  | Withdrawn on July 31, 2013
G0292 | 2007-10-17 09:30 |  |  | WA | Benton | Prosser 115 kV Substation | WITHDRAWN | GI | 2011-07-01 | 180 | 180 | Benton County, Washington | ERIS | Wind |  | Withdrawn on November 23, 2009
G0291 | 2007-10-15 09:48 | Shepherds Flat Wind Farm addition | Caithness Shepherds Flat, LLC | OR | Gilliam | Slatt 500 kV Substation | CONFIRMED | GI | 2009-07-01 | 96 | 96 | Gilliam & Morrow Counties, Oregon | NRIS | Wind |  | on-line June 2012
L0282 | 2007-09-26 11:29 | Cowlitz Substation | Tacoma Power |  |  | Reterminate BPA's South Tacoma-Cowlitz 230kV Line | WITHDRAWN | LL | 2010-01-01 |  |  | Pierce County, WA |  |  |  | BPA's S.Tacoma 230kV line to be disconnected from Cowlitz and connect directly to Tacoma's Southwest #4 line.
L0281 | 2007-09-14 16:04 | Grant Rocky Ford | Public Utility District No. 2 of Grant County, Washington |  |  | Columbia 115/230kV Substation | CONFIRMED | LL | 2010-01-01 |  |  | Douglas county to Grant county
G0290 | 2007-09-06 09:19 |  |  | OR | Wasco | Wasco Co., Oregon | WITHDRAWN | GI | 2011-10-01 | 75 | 75 | Wasco County, Oregon | NRIS | Wind |  | Withdrawn by Customer on November 17, 2008
G0289 | 2007-08-28 12:08 | Grays Harbor 2 Project | Grays Harbor Energy II, LLC |  |  | Satsop Substation | CONFIRMED | GI | 2010-12-31 | 628 | 659 | Grays Harbor County, Washington | NRIS | Combined cycle |  | on-line June 2012
G0288 | 2007-08-24 09:09 |  |  | WA | Pacific | One mile from Naselle 115 kV Substation | WITHDRAWN | GI | 2011-07-01 | 82 | 82 | Pacific County, Washington | ERIS | Wind |  | Withdrawn on December 12, 2011
L0279 | 2007-08-23 09:24 | Victor Transformer | Fall River Rural Electric Cooperative, Inc. |  |  | Victor Substation | CONFIRMED | LL | 2010-01-01 |  |  | Teton County, ID
L0278 | 2007-08-22 10:05 | North Loop | City of Idaho Falls |  |  | Westside Substation | CONFIRMED | LL | 2010-01-01 |  |  | Bonneville County, ID
G0287 | 2007-08-17 08:59 |  |  | WA | Klickitat | Midway-N. Bonneville 230 kV line north of Goldendale, Wa. | WITHDRAWN | GI | 2010-09-01 | 200 | 200 | Klickitat County, Washington | ERIS | Wind |  | Withdrawn by Customer on July 8, 2008.
G0284 | 2007-08-13 10:51 | Lower Snake Phase 1 | Puget Sound Energy, Inc. | WA | Columbia | Central Ferry Substation | CONFIRMED | GI | 2011-12-31 | 250 | 250 | Columbia County, Washington | NRIS | Wind |  | Phase I for 250 MW; on-line January 2010
G0285 | 2007-08-13 10:51 | Lower Snake Phase 1 | Puget Sound Energy, Inc. | WA | Columbia & Garfield | Central Ferry Substation | CONFIRMED | GI | 2011-12-31 | 250 | 250 | Garfield & Columbia Counties, Washington | NRIS | Wind |  | Phase I for 93 MW; on-line January 2012
G0286 | 2007-08-13 10:51 | Tucannon River Wind Farm | Portland General Electric Company | WA | Columbia & Garfield | Central Ferry Substation | CONFIRMED | GI | 2011-12-31 | 250 | 250 | Garfield County, Washington | NRIS | Wind |  | Phase 2 for 267 MW acquired by PGE; on-line scheduled for December 2014.
G0283 | 2007-08-10 10:25 |  |  |  |  | DeMoss Springs | WITHDRAWN | GI | 2009-04-01 | 40 | 40 | Sherman County, Oregon | ERIS | Wind |  | Withdrawn by Customer on June 24, 2011.
G0282 | 2007-08-10 09:11 |  |  |  |  | Chandler 115 kV line | WITHDRAWN | GI | 2011-10-01 | 100 | 100 | Benton County, Washington | NRIS | Wind |  | Withdrawn on November 29, 2012
L0277 | 2007-08-03 10:05 | Oceanside | Tillamook People's Utility District |  |  | Tillamook Substation | CONFIRMED | LL | 2010-01-01 |  |  | Tillamook County, OR
L0276 | 2007-07-25 09:28 | Network Connection, 230 kV loop line | Puget Sound Energy, Inc. |  |  | St Clair or Spurgeon Creek Substation | COMPLETED | LL | 2008-08-01 |  |  | Thurston County, WA |  |  |  | In construction phase.
G0279 | 2007-07-17 14:15 |  |  | OR | Sherman | To be determined | WITHDRAWN | GI | 2010-08-01 | 105 | 105 | Sherman County, Oregon | NRIS | Wind
G0280 | 2007-07-17 14:15 |  |  |  |  | To be determined | WITHDRAWN | GI | 2011-07-01 | 242 | 242 | Sherman County, Oregon | NRIS | Wind
G0281 | 2007-07-17 09:00 |  |  | WA | Walla Walla | Lower Monumental-McNary 500kV line in vicinity of Wallula, WA. | WITHDRAWN | GI | 2013-06-01 | 760 | 760 | Walla Walla County, WA | NRIS | Combined cycle |  | Withdrawn by Customer on February 12, 2008.
G0278 | 2007-07-12 08:56 |  |  | WA | Klickitat | Midway-North Bonneville 230kV Line | WITHDRAWN | GI | 2009-12-01 | 75 | 75 | Klickitat County, WA | ERIS | Wind |  | Withdrawn by Customer on March 5, 2009.
G0277 | 2007-07-10 16:25 |  |  |  |  | to be determined | WITHDRAWN | GI | 2010-12-31 | 250 | 250 | Gilliam County, Oregon | ERIS | Wind |  | Withdrawn on July 30, 2013
G0276 | 2007-07-06 09:55 |  |  | WA | Douglas | Grand Coulee-Columbia 230kV Line | WITHDRAWN | GI | 2010-12-01 | 300 | 300 | Douglas County, WA | NRIS | Wind |  | Withdrawn on January 27, 2009
L0275 | 2007-07-06 07:05 | Merchant Transmission Line | Green Pacific Highway, LLC |  |  | Allston Substation | WITHDRAWN | LL | 2009-07-01 |  |  | Columbia County, OR
G0275 | 2007-07-03 16:44 |  |  |  |  | 20Miles West of Milton-Freewater | WITHDRAWN | GI | 2009-11-01 | 100 | 100 | Umatilla County, OR | NRIS | Wind |  | Withdrawn on January 7, 2013
G0274 | 2007-06-29 10:00 | Hopkins Ridge Addition | Puget Sound Energy, Inc. | WA | Columbia | Tucannon River Switching Station | CONFIRMED | GI | 2008-08-01 | 7 | 7 | Columbia County, WA | NRIS | Wind |  | on-line August 2008
G0273 | 2007-06-14 09:36 |  |  | WA | Kittitas | Vantage Substation | WITHDRAWN | GI | 2008-09-01 | 104 | 104 | Kittitas County, WA | ERIS | Wind |  | Witrhdrawn by Customer on July 18, 2008.
L0273 | 2007-05-25 09:16 | Beverly Park Expansion | Public Utility District No. 1 of Snohomish County |  |  | Snohomish Substation | WITHDRAWN | LL | 2008-10-01 | 178 | 178 | Snohomish County Wa.
L0272 | 2007-05-17 09:20 | Columbia Substation | Public Utility District No. 1 of Douglas County |  |  | BPA's Columbia Substation | WITHDRAWN | LL | 2008-06-01 | 5 | 5 | Douglas County, WA
G0271 | 2007-05-04 10:00 |  |  | WA | Yakima | BPA's Wautoma 230 kV Line | WITHDRAWN | GI | 2009-09-01 | 300 | 300 | Yakima County, WA | ERIS | Wind |  | Withdrawn on May 30, 2008
G0272 | 2007-05-04 10:00 |  |  | WA | Yakima | BPA's Wautoma 230kV Line | WITHDRAWN | GI | 2008-08-01 | 300 | 300 | Yakima County,WA | ERIS | Wind |  | Withdrawn on May 30, 2008.
L0271 | 2007-03-29 11:26 | Brothers Tap Upgrade | Midstate Electric Cooperative, Inc. |  |  | Christmas Valley 115 kV | WITHDRAWN | LL | 2008-05-01 | 14 | 14 | Lake Co, OR
G0263 | 2007-03-08 17:03 |  |  | OR | Sherman | N/A | WITHDRAWN | GI | 2009-11-01 | 200 | 200 | Sherman County, Oregon | NRIS | Wind |  | Withdrawn August 28, 2007
G0262 | 2007-03-07 10:21 |  |  | OR | Wasco | Big Eddy-DeMoss 115 kV Line | WITHDRAWN | GI | 2007-12-01 | 3 | 3 | Wasco County, Oregon | Energy | Wind |  | Withdrawn September 10, 2007
G0261 | 2007-02-22 17:06 |  |  | WA | Klickitat | Ashe-Marion 500 kV | WITHDRAWN | GI | 2010-09-01 | 1200 | 1200 | Klickitat Co, WA | ERIS | Wind |  | Withdrawn November 8, 2007
L0259 | 2007-02-06 09:19 | Wahkiakum PUD 115kV Tap | Public Utility District No. 1 of Wahkiakum County |  |  | Naselle Tap to Allston-Astoria #1 115kV | CONFIRMED | LL | 2009-02-01 | 0 | 0 |  |  |  |  | Studies complete
G0258 | 2007-02-02 09:56 |  |  | WA | Cowlitz | Longview Substation | WITHDRAWN | GI | 2012-01-01 | 320 | 375 | Cowlitz Co, WA | ERIS | Combined cycle |  | Withdrawn on September 6, 2013.
G0255 | 2007-01-25 12:26 | Willow Creek and Horn Butte | Invenergy Wind Development, LLC | OR | Gilliam | Boardman-Alkali 115 kV Line | CONFIRMED | GI | 2008-05-01 | 72 | 72 | Gilliam, OR | ERIS | Wind |  | LGIA executed for Phase 1, 72 MW; on-line November 2008.
L0260 | 2007-01-18 16:49 | Midstate LaPine Addition | Midstate Electric Cooperative, Inc. |  |  | LaPine Substation | CONFIRMED | LL | 2008-12-01 | 163 | 163
L0257 | 2007-01-18 08:28 | West Wendover | Wells Rural Electric Company |  |  | West Wendover POD | CONFIRMED | LL | 2008-01-01 | 0 | 0
L0256 | 2007-01-12 13:33 | Targhee Substation | Fall River Rural Electric Cooperative, Inc. |  |  | Targhee Substation | CONFIRMED | LL | 2008-01-01 | 0 | 0
G0252 | 2006-12-19 08:54 |  |  | WA | Yakima | Wautoma 500 kV Substation | WITHDRAWN | GI | 2008-09-01 | 350 | 350 | Yakima, WA | ERIS | Wind |  | Withdrawn by Customer on February 29, 2008.
G0253 | 2006-12-19 08:54 |  |  | WA | Klickitat | Horse Heaven Substation 115 kV | WITHDRAWN | GI | 2008-09-01 | 100 | 100 | Klickitat, WA | ERIS | Wind |  | Withdrawn on July 18, 2007
G0251 | 2006-12-14 09:15 |  |  | WA |  | New substation on BPA's 500 kV McNary-John Day line | COMPLETED | GI | 2010-09-01 | 700 | 700 | Klickitat, WA | ERIS | Wind |  | FAS Study Issued 5/27/2009 | Awaiting Customer Permits to complete NEPA Review
L0250 | 2006-12-13 09:25 | Pacific Ethnanol Tap | United Electric Co-op, Inc. |  |  | Unity-West Burley 138 kV | CONFIRMED | LL | 2008-12-01 | 0 | 0
G0249 | 2006-12-07 05:54 |  |  | WA | Klickitat | Midway-Big Eddy 230 kV | WITHDRAWN | GI | 2008-12-01 | 75 | 75 | Klickitat, WA | Energy | Wind |  | Withdrawn on July 11, 2008
L0244 | 2006-11-01 08:11 | PSE Alderton Substation | Puget Sound Energy, Inc. |  |  | Olympia-White River 230 kV | WITHDRAWN | LL | 2008-11-01 | 0 | 0 |  |  |  |  | Generation Facility Location Pierce County, WA
G0248 | 2006-11-01 04:00 |  |  | ID | Cassia | Idahome Substation | WITHDRAWN | GI | 2007-12-31 | 20 | 20 | Cassia County, ID | Energy | Wind |  | Withdrawn on March 31, 2009
G0247 | 2006-11-01 03:58 |  |  | ID | Cassia | Idahome Substation | WITHDRAWN | GI | 2007-12-31 | 20 | 20 | Cassia County, ID | Energy | Wind |  | Withdrawn on March 31, 2009
G0246 | 2006-11-01 03:52 |  |  | ID | Cassia | Idahome Substation | WITHDRAWN | GI | 2007-12-31 | 20 | 20 | Cassia County, ID | Energy | Wind |  |  | Withdrawn on March 31, 2009
G0245 | 2006-11-01 03:49 |  |  | ID | Cassia | Idahome Substation | WITHDRAWN | GI | 2007-12-31 | 20 | 20 | Cassia County, ID | Energy | Wind |  | Withdrawn on March 31, 2009
L0243 | 2006-10-26 09:12 | Canyon Substation | Tacoma Power |  |  | South Tacoma Substation | CONFIRMED | LL | 2008-10-01 | 0 | 0
G0238 | 2006-10-10 16:01 |  |  | OR | Gilliam County | Slatt Substation | COMPLETED | GI | 2010-09-01 | 202 | 202 | Arlington, OR | ERIS | Wind |  | FAS Study Issued 7/20/2008 | NEPA in progress
G0239 | 2006-10-10 16:01 |  |  | OR | Gilliam County | Slatt Substation | COMPLETED | GI | 2010-07-01 | 202 | 202 | Arlington, OR | ERIS | Wind |  | FAS Study Issued 7/20/2008 | NEPA in progress
G0240 | 2006-10-10 16:01 |  |  | OR | Morrow | Boardman Substation | WITHDRAWN | GI | 2010-07-01 | 202 | 202 |  | NRIS | Wind |  | Withdrawn on August 31, 2007
G0241 | 2006-10-10 16:01 |  |  | OR | Morrow | Boardman Substation | WITHDRAWN | GI | 2010-09-01 | 202 | 202 |  | NRIS | Wind |  | Withdrawn on August 31, 2007
G0242 | 2006-10-10 16:01 |  |  | WA | Klickitat County | Horse Heaven-Harvalum 230 kV line | COMPLETED | GI | 2009-07-01 | 101 | 101 |  | NRIS | Wind |  | FAS Study Issued 4/22/2009 | Awaiting Customer Permits to complete NEPA Review
G0237 | 2006-10-10 09:33 |  |  |  | Sherman | New Substation near John Day 500kV Substation | COMPLETED | GI | 2009-11-01 | 100 | 100 | Sherman, OR | NRIS | Wind |  | FAS Study Issued 7/2/2008 | Awaiting Customer Permits to complete NEPA Review
L0236 | 2006-10-06 02:38 | Clatskanie Tap | Clatskanie People's Utility District |  |  | Clatskanie Tap | CONFIRMED | LL | 2007-11-01 | 0 | 0 |  |  |  |  | Clatskanie PUD
G0235 | 2006-09-25 09:08 |  |  | OR | Sherman | New Substation near John Day 500kV Substation | COMPLETED | GI | 2009-11-01 | 200 | 200 | Sherman,OR | NRIS | Wind |  | FAS Study Issued 7/2/2008 | Awaiting Customer Permits to complete NEPA Review
G0234 | 2006-09-05 12:39 |  |  | WA |  | Station Z 230kV | WITHDRAWN | GI | 2007-12-01 | 300 | 300 | Klickitat County | Energy | Wind |  | Withdrawn by Customer on July 8, 2008
G0233 | 2006-09-05 12:38 |  |  | WA |  | Rock Creek Substation | COMPLETED | GI | 2007-12-01 | 150 | 150 | Klickitat County | Energy | Wind |  | FAS Study Issued 9/27/2008; NEPA complete 10/1/2008 | Customer delayed
G0232 | 2006-08-25 15:41 |  |  | OR | Wasco | Big Eddy-DeMoss 115 kV Line | WITHDRAWN | GI | 2007-10-01 | 10 | 10 | Wasco County, OR | Energy | Wind |  | Withdrawn September 3, 2008
L0231 | 2006-08-23 09:37 | Albany Lebanon | Consumers Power, Inc. |  |  | Tap on Albany-Lebanon 115 kV line | WITHDRAWN | LL | 2007-09-01 | 10 | 10
L0274 | 2006-07-20 11:23 | Lauderdale Project | Public Utility District No. 1 of Kittitas County |  |  | Columbia-Ellensburg 115kV Line | CONFIRMED | LL | 2009-06-01 |  |  | Kittitas County, WA
G0230 | 2006-07-19 15:58 |  |  | OR | Gilliam | Jones Canyon 230 kV Substation | WITHDRAWN | GI | 2008-06-01 | 200 | 200 | Arlington | ERIS | Wind |  | Withdrawn July 17, 2007
L0229 | 2006-06-28 09:00 | Bradwood Tap | PacifiCorp |  |  | Allston -Astoria #1 115 kV Line near Cathlamet Tap | WITHDRAWN | LL | 2008-01-01 | 40 | 40
G0228 | 2006-06-27 09:33 |  |  | OR | Wasco County | Hood River-The Dalles 115 KV Transmission Line | WITHDRAWN | GI | 2008-06-30 | 80 | 80 |  | NRIS | Wind
L0227 | 2006-06-08 14:58 | Zephyr Heights | Public Utility District No. 1 of Benton County |  |  | Franklin-Badger Canyon 115 kV | CONFIRMED | LL | 2006-12-01 | 0 | 0
G0226 | 2006-05-24 09:30 | Leaning Juniper II | Iberdrola Renewables, LLC | OR | Gilliam County | Jones Canyon Substation | CONFIRMED | GI | 2009-06-01 | 200 | 200 | Arlington OR | ERIS | Wind |  | on-line April 2011
G0225 | 2006-05-18 12:00 |  |  | WA | Douglas | to be determind | WITHDRAWN | GI | 2008-06-01 | 127 | 127 |  | NRIS | Wind |  | Withdrawn January 11, 2006
G0224 | 2006-05-09 09:57 | Big Horn 2 | Iberdrola Renewables, LLC | WA |  | Spring Creek Substation | CONFIRMED | GI | 2007-06-01 | 50 | 50 | Klickitat County | NRIS | Wind |  | on-line September 2010
G0223 | 2006-04-19 15:56 | Hay Canyon/Star Point | Iberdrola Renewables, LLC | OR | Sherman | John Day Substation | CONFIRMED | GI | 2008-12-01 | 201 | 201 | Sherman County | NRIS | Wind |  | Hay Canyon on-line December 2008 for 101 MW; Star Point on-line January 2010. Two LGIAs provided.
G0222 | 2006-03-24 10:17 | Windy Flats -Dooley Wind | Windy Point Partners, LLC | WA | Klickitat | Rock Creek Substation | CONFIRMED | GI | 2008-12-31 | 250 | 250 | Klickitat, | NRIS | Wind |  | on-line November 2009, combined with G0122, in part
L0254 | 2006-03-13 10:39 | Joyce Substation | Public Utility District No. 1 of Clallam County |  |  | Port Angeles-Sappho 115 kV Line | CONFIRMED | LL | 2008-09-30 | 9 | 9 |  |  |  |  | Studies complete
G0214 | 2006-01-05 11:59 |  |  | OR | Deschutes County | Lapine Substation 230kV | COMPLETED | GI | 2009-09-01 | 140 | 140 |  | ERIS | Geothermal |  | FAS Study Issued 9/11/2007 | Awaiting Customer permits to complete NEPA Review
G0213 | 2005-12-21 10:12 |  |  | WA | Cowlitz | Longview Substation 230kV | WITHDRAWN | GI | 2012-01-01 | 600 | 600 | Kalama | NRIS | Combined cycle
L0219 | 2005-11-17 | Sunset Substation | Portland General Electric Company |  |  | Keeler Substation | CONFIRMED | LL | 2007-01-01 | 0 | 0 |  |  |  |  | Studies complete
G0212 | 2005-11-15 14:25 |  |  | WA | Kittitas | To Be determined | WITHDRAWN | GI | 2008-01-01 | 100 | 100 |  | NRIS & ERIS | Wind |  | Withdrawn by Customer on January 23, 2006.
G0211 | 2005-11-14 15:38 |  |  | WA | Douglas | to be determined | WITHDRAWN | GI | 2007-10-01 | 127 | 127 |  | NRIS | Wind
L0221 | 2005-11-01 | Pacific West Coast Cable | Sea Breeze Pacific West Coast Cable LP |  |  | Allston 500 kV | WITHDRAWN | LL | 2007-01-01 | 1600 | 1600 |  |  |  |  | Sea Breeze Pacific West Coast Cable, LP - failed to execute Facility Study
L0216 | 2005-09-22 | Vintage Valley | PacifiCorp |  |  | Midway-Mabton 230 | CONFIRMED | LL | 2007-04-01 | 0 | 0 |  |  |  |  | Pacificorps
L0217 | 2005-09-22 | Yew Ave. Sub | PacifiCorp |  |  | Redmond-Harney 115 | CONFIRMED | LL | 2006-12-01 | 0 | 0 |  |  |  |  | Pacificorps
L0218 | 2005-09-22 | Bradwood Tap | PacifiCorp |  |  | Cathlamet Tap-Cathlamet 115 | WITHDRAWN | LL | 2007-01-01 | 25 | 25 |  |  |  |  | Pacificorps
G0210 | 2005-09-15 09:50 |  |  | WA | Lincoln | Grand Coulee-Bell 115 kV line, north of Reardan, WA. | WITHDRAWN | GI | 2006-10-31 | 75 | 75 |  | ERIS | Wind |  | Withdrawn by Customer on May 1, 2008.
L0215 | 2005-08-23 | Montanore Mine | Flathead Electric Cooperative, Inc. |  |  | Libby-Noxon 230 | WITHDRAWN | LL | 2007-06-01 | 26 | 26 |  |  |  |  | Withdrawn by FEC on 4/2/2013.
G0209 | 2005-08-22 12:28 |  |  | WA | Grant | Grand Coulee-Rocky Ford 230 kV line | WITHDRAWN | GI | 2008-02-01 | 124 | 0 |  | ERIS | Hydro |  | Withdrawn May 21, 2008
G0208 | 2005-07-18 13:12 | Tuolumne Wind (Windy Point 1) | Windy Point Partners, LLC | WA | Klickitat | Rock Creek Substation 230 kV | CONFIRMED | GI | 2007-03-01 | 125 | 125 | Adjacent to Rock Creek Substation | NRIS | Wind |  | on-line December 2008(sold to Turlock Irrigation District, operated as Tuolumne Wind)
G0207 | 2005-06-29 09:46 |  |  | OR | Gilliam | John Day Substation 230 kV | WITHDRAWN | GI | 2006-07-15 | 200 | 200 |  | NRIS | Wind
G0206 | 2005-06-24 |  |  | OR | Union County | Lagrande Substation 230 kV | WITHDRAWN | GI | 2008-10-01 | 110 | 110 |  | ERIS | Wind
G0205 | 2005-06-16 09:37 | Grays Harbor 1 | Grays Harbor Energy, LLC | WA | Grays Harbor | Satsop Substation | CONFIRMED | GI | 2006-12-31 | 628 | 659 | Grays Harbor | NRIS | Combined cycle
G0203 | 2005-05-26 09:56 | Juniper Canyon 1 | Iberdrola Renewables, LLC | WA | Klickitat | Rock Creek | CONFIRMED | GI | 2007-12-01 | 50 | 50 |  | NRIS | Wind |  | on-line February 2011
G0204 | 2005-05-26 09:56 | Juniper Canyon 1 | Iberdrola Renewables, LLC | WA | Klickitat | Rock Creek Substation 230 kV. | CONFIRMED | GI | 2007-12-01 | 100 | 100 |  | ERIS | Wind |  | on-line February 2012
L0201 | 2005-04-04 09:38 | Juan de Fuca HVDC (Port Angeles) | Olympic Converter, LP - Don'T Use |  |  | Port Angeles 230 kV | COMPLETED | LL | 2007-05-01 | 550 | 550 | Port Angeles |  |  |  | FAS complete. NEPA complete. | Awaiting customer acquiring txm & pwr purchase agmt.
L0202 | 2005-04-04 09:38 | Juan de Fuca HVDC (Fairmount) | Olympic Converter, LP - Don'T Use |  |  | Fairmount 230 kV | COMPLETED | LL | 2008-05-01 | 550 | 550 | Discovery Bay |  |  |  | Sea Breeze Olympic Converter, LP | Awaiting customer acquiring txm & pwr purchase agmt.
G135 | 2004-06-23 13:00 | White Creek Wind I | White Creek Wind I, LLC | WA | Klickitat | Rock Creek | CONFIRMED | GI | 2006-08-01 | 200 | 200 |  | Energy | Wind |  | on-line August 2007
G132 | 2004-06-07 11:16 | Sea Breeze Olympic Ph 1 | Olympic Converter, LP - Don'T Use | WA | Clallam | Port Angeles 230 kV | WITHDRAWN | GI | 2007-05-01 | 330 | 330 |  | Energy
G133 | 2004-06-07 11:16 | Sea Breeze Olympic Ph 2 | Olympic Converter, LP - Don'T Use | WA | Clallam | Port Angeles 230 kV or Fairmount 230 kV | WITHDRAWN | GI | 2008-05-01 | 330 | 330 |  | Energy
G134 | 2004-06-07 11:16 | Sea Breeze Olympic Ph 3 | Olympic Converter, LP - Don'T Use | WA | Clallam | Port Angeles 230 kV or Fairmount 230 kV | WITHDRAWN | GI | 2010-05-01 | 330 | 330 |  | Energy
L0220 | 2004-05-17 | Monmouth Tap | City of Monmouth |  |  | Salem-Albeni 115 | CONFIRMED | LL | 2006-12-01 | 0 | 0 |  |  |  |  | Ciy of Monmouth
G131 | 2004-04-27 03:54 | Windtricity Ventures LLC | Windtricity Ventures | WA | Klickitat | Rock Creek 230kV | CONFIRMED | GI | 2007-09-15 | 150 | 150 |  | ERIS | Wind
G130 | 2004-04-02 10:28 | N/A | BPA Power Services | OR | Umatilla | McNary 230 kV | WITHDRAWN | GI | 2005-10-01 | 200 | 200 | McNary Dam | Energy | Hydro |  | Withdrawn by Customer on December 1, 2008.
G129 | 2004-03-15 11:38 | River Road Generating Plant | Clark Public Utilities | WA | Clark | Interconnect between River Road Gen and BPA's Alcoa Sub | CONFIRMED | GI | 2005-07-01 | 240 | 240 | NW Lower River Road | Energy | Gas peaking generation |  | Plant constructed and operational
G128 | 2004-03-08 09:53 | Summit/Westward | Summit Power Northwest Project, LLC | OR | Clatsop | BPA’s Driscoll 230kV switchyard | WITHDRAWN | GI | 2009-03-10 | 536 | 536 |  | Energy | Combined cycle |  | March 11, 2010: This is provisionally posted as 'Withdrawn' pending confirmation that OR EFSC has terminated the site certificate.
G127 | 2004-03-04 16:47 | Orion Energy LLC | Orion Energy, LLC | OR | Wasco | DeMoss Substation | WITHDRAWN | GI | 2006-12-01 | 450 | 450 |  | Energy | Wind
G126 | 2004-03-04 09:53 | Iberdrola Renewables Inc | Iberdrola Renewables, LLC | OR | Wasco | Big Eddy-Midway 230 kV line | CONFIRMED | GI | 2005-12-01 | 200 | 200 |  | Energy | Wind
G125 | 2004-03-01 11:17 | USGeothermal | US Geothermal, Inc. | ID | Cassia | Bridge Substation, 34.5 kV ·or·138 kV Transmission line 2.5 miles SE of Bridge Substation (this line is not owned by BPA) | WITHDRAWN | GI | 2006-01-01 | 30 | 30 |  | Energy | Geothermal |  | on-line June 2006
G123 | 2004-02-13 09:28 | NextEra Energy Resources | NextEra Energy Resources LLC | OR | Umatilla | The Point of Interconnection for the existing Stateline Wind Project, which is a tap point on the Franklin-Walla Walla 115kVline. | WITHDRAWN | GI | 2005-01-01 | 17 | 17 |  | Energy | Wind
G124 | 2004-02-12 11:53 | Klondike 3 Wind | Klondike Wind Power III, LLC | OR | Wasco | Klondike Schoolhouse 230kV | CONFIRMED | GI | 2007-10-15 | 300 | 300 |  | ERIS | Wind |  | on-line October 2007, April 2008.
G122 | 2004-01-16 09:55 | Windy Point 1 Wind | Cannon Power Corporation | WA | Klickitat | Rock Creek 230kV | CONFIRMED | GI | 2009-07-01 | 125 | 125 |  | ERIS | Wind |  | on-line December 2008, as Tuolumue Wind.
G121 | 2003-12-05 11:06 | Willow Creek | Invenergy Wind Development, LLC | OR | Gilliam | McNary – Santiam 230 kV transmission line | WITHDRAWN | GI | 2005-12-01 | 180 | 180 |  | ERIS | Wind
G120 | 2003-11-24 11:06 | Invenergy Wind Development | Invenergy Wind Development, LLC | OR | Morrow | McNary – Santiam 230 kV transmission line | WITHDRAWN | GI | 2005-12-01 | 180 | 180 |  | Energy | Wind
G118 | 2003-09-17 10:00 | Shepherds Flat | Caithness Shepherds Flat, LLC | OR | Gilliam | BPA's Slatt 500kV Substation | CONFIRMED | GI | 2009-10-01 | 750 | 750 |  | ERIS | Wind |  | on-line August 2011; June 2012 (Phase 2 & 3)
G119 | 2003-09-17 10:00 | LifeLine Renewable Energy | Lifeline Renewable Energy, Inc. | OR | Morrow | BPA's McNary - Santiam 230kV Line 5 to 10 miles West of Slatt Substation. | WITHDRAWN | GI | 2004-10-01 | 200 | 200 |  | ERIS | Wind
G117 | 2003-07-31 11:45 | NextEra Energy Resources | NextEra Energy Resources LLC | OR | wasco | The point where the new 230kV Line from the Project terminates into BPA’s Big Eddy Substation at 230kV. | WITHDRAWN | GI | 2004-12-31 | 100 | 100 |  | Energy | Wind |  | Withdrawn by Customer on January 30, 2004.
G116 | 2003-05-19 11:06 | Oregon Wind | Oregon Wind, LLC | OR | Wasco | Hood River-The Dalles 115 KV Transmission Line.The exact location is Township/ Range 2N12E Section 27. | WITHDRAWN | GI | 2008-06-01 | 50 | 50 |  | ERIS | Wind |  | Withdrawn by Customer on January 8, 2009.
G115 | 2003-05-01 10:58 | Windland Inc | Windland, Inc. | ID | Cassia | Interconnect to either (1) Minidoka-Wendover 138 kV Line; or (2) Minidoka-Wendover and East Hills 138 kV Lines. | WITHDRAWN | GI | 2005-07-01 | 200 | 200 |  | Energy | Wind |  | Withdrawn by Customer on July 13, 2005.
G114 | 2003-01-22 11:44 | Horizon Wind Energy-WRidge | Wind Ridge Power Partners, LLC | WA | Kittitas | The location of Zilkha’s generating facilities will be approximately seven miles northeast of the town of Kittitas in Kittitas County, Washington | WITHDRAWN | GI | 2004-09-15 | 252 | 252 |  | Energy | Wind
G113 | 2002-11-20 09:28 | RES North America LLC | RES North America | OR | Sherman | Interconnection shall be John Day Substation approximately sections 6 and 7 of Township 2N, Range 17E, Sherman County, Oregon | WITHDRAWN | GI | 2004-06-01 | 250 | 250 |  | Energy | Wind
G111 | 2002-11-04 13:29 | Iberdrola Renewables Inc | Iberdrola Renewables, LLC | WA | klickitat | Midway – Big Eddy 230 kV Transmission Line·Will be approximately eight miles southwest of Bickleton, Washington in Klickitat County. | WITHDRAWN | GI | 2004-03-01 | 200 | 200 |  | Energy | Wind |  | Withdrawn on December 17, 2003.
G112 | 2002-11-01 13:29 | Iberdrola Renewables Inc | Iberdrola Renewables, LLC | OR | Klickitat | Hanford-JohnDay 500 kV Transmission Line·Will be approximately eight miles southwest of Bickleton, Washington in Klickitat County. | WITHDRAWN | GI | 2004-03-01 | 200 | 200 |  | Energy | Wind
G110 | 2002-09-18 11:12 | Shepherds Flat Wind | Caithness Shepherds Flat, LLC | OR | Morrow | BPA Slatt 500 kV Substation | WITHDRAWN | GI | 2003-10-01 | 250 | 250 |  | ERIS | Wind
G109-01 | 2002-09-16 14:03 | Iberdrola Renewables Inc | Iberdrola Renewables, LLC | OR | Gilliam | Slatt 500kV Substation approximately 5-10 miles SW of Arlington | WITHDRAWN | GI | 2003-12-30 | 100 | 100 |  | Energy | Wind |  | Withdrawn on December 19, 2003 by Customer.
G109 | 2002-07-24 09:52 | Combine Hills II | Eurus Combine Hills II LLC | OR | Umatilla | Walla Walla-Pendleton 69kV line | CONFIRMED | GI | 2009-12-10 | 63 | 63 |  | ERIS | Wind |  | on-line January 2010
G106 | 2002-06-24 10:25 | Pebble Springs Wind Project | Iberdrola Renewables, LLC | OR | Gilliam | McNary-Santiam 230kV Transmission line approximately 5-10 miles SW of Arlington | CONFIRMED | GI | 2004-01-01 | 200 | 200 |  | Energy | Wind |  | on-line November 2008
G107 | 2002-06-24 10:25 | Ib | Iberdrola Renewables, LLC |  | Gilliam | Slatt 500kV Substation approximately 5-10 miles SW of Arlington | WITHDRAWN | GI | 2004-01-01 | 200 | 200 |  | Energy | Wind |  | Withdrawn per 12/16/2003 letter from Customer.
G108 | 2002-06-24 10:22 | Whistling Ridge | Whistling Ridge Energy, LLC | OR | Skamania | Midway-North Bonneville 230kV Transmission line | COMPLETED | GI | 2009-12-31 | 70 | 70 |  | ERIS | Wind |  | Restudy of plan-of-service, site permit approved.
G105 | 2002-06-20 09:16 | Desert Claim | enXco Northwest | WA | Kittitas | Covington-Columbia 230kV transmission line | COMPLETED | GI | 2009-10-01 | 159 | 159 | 8 miles NW of Ellensburg, WA | ERIS | Wind |  | New plan-of-serivce per customer request, site permits approved | Need revised POS to complete NEPA Review
G102 | 2002-06-10 10:00 | Energy Northwest Inc | Energy Northwest Inc | WA | Benton | Interconnection with the Mabton-Big Eddy 230kV Transmission line. Associated with the proposed Wind Project in Klickitat County. | WITHDRAWN | GI | 2004-05-01 | 75 | 75 |  | Energy | Wind
G103 | 2002-06-07 08:30 | Telephone Flat | Calpine Energy Services, L.P. | OR | Klamath | BPA's 230kV Malin-Hilltop line | WITHDRAWN | GI | 2004-10-01 | 60 | 60 |  | Energy | Geothermal
G104 | 2002-06-07 08:30 | Fourmile Hill | Calpine Energy Services, L.P. | OR | Klamath | The BPA's 230kV Malin-Hilltop line | WITHDRAWN | GI | 2004-10-01 | 60 | 60 |  | Energy | Geothermal
G101 | 2002-06-03 14:10 | NextEra Energy Resources | NextEra Energy Resources LLC | WA | Garfield | Interconnection to the existing BPA 500kV McNary to Lower Monumental Line where the line crosses Highway 12. | WITHDRAWN | GI | 2003-09-01 | 300 | 300 |  | Energy | Wind
G100 | 2002-05-06 09:45 | Hopkins Ridge Wind | Puget Sound Energy, Inc. | WA | Columbia | BPA's 115 kV line Connecting the North Lewiston and Walla Walla Substations | CONFIRMED | GI | 2003-12-01 | 150 | 150 |  | Energy | Wind |  | on-line December 2005
G99 | 2002-04-05 14:12 | Biglow Canyon Wind | Portland General Electric Company | OR | Sherman County | Biglow Canyon | CONFIRMED | GI | 2008-12-01 | 400 | 400 |  | ERIS | Wind |  | on-line Phase I October 2007; Phase 2 June 2009; Phase 3 May 2010
G98-01 | 2002-04-05 09:20 | Summit Ridge Project | Seawest Windpower, Inc. | OR | Wasco | On the Big Eddy – DeMoss 115 kV transmission line approximately 8-9 miles east of The Dalles, Oregon. | WITHDRAWN | GI | 2003-10-31 | 75 | 75 |  | Energy | Wind |  | Withdrawn on December 17, 2003
G98-02 | 2002-04-05 09:20 | White Creek | Harvest Wind Project | OR | Klickitat | Rock Creek 230kV | CONFIRMED | GI | 2009-10-01 | 100 | 100 | Klickitat Co. Oregon | ERIS | Wind |  | on line January 2010
G97 | 2002-03-19 13:50 | Anderson Ranch Wind Farm | NextEra Energy Resources LLC | OR | Gilliam | The project is South of the Columbia River between Phillippi Canyon and Blalock Canyon. | WITHDRAWN | GI | 2002-09-01 | 100 | 100 |  | Energy | Wind |  | Withdrawn on November 1, 2002
G98 | 2002-03-19 13:50 | The Dalles Wind Farm | NextEra Energy Resources LLC | OR | Wasco | The project is to be East of Big Eddy Substation to the Deschutes River. Then extending South from Columbia River about 7 miles. | WITHDRAWN | GI | 2003-09-01 | 350 | 350 |  | Energy | Wind |  | Withdrawn on November 1, 2002
G96 | 2002-03-08 16:57 | Klondike 2 Wind | Klondike Wind Power II, LLC | OR | Wasco | BPA's DeMoss 115kV Substation | CONFIRMED | GI | 2003-09-01 | 50 | 50 |  | Energy | Wind |  | on-line June 2005 with G082
G95 | 2002-02-15 13:18 | Arlington Wind | EDP Renewables North America LLC | OR | Gilliam | Jones Canyon Substation | CONFIRMED | GI | 2008-10-01 | 200 | 200 |  | ERIS | Wind |  | on-line November 2008 & February 2009. LGIA split into two LGIAs. Arlington Wind Power Project, LLC for 103 MW and Wheat Field Wind Power Project, LLC for 97 MW.
G94 | 2002-02-08 13:00 | Peoples Energy Resources | Peoples Energy Resources Corporation | OR | Klamath | BPA’s 500 kV Grizzly – Malin transmission line approximately 30 miles north of Malin Substation | WITHDRAWN | GI | 2005-02-01 | 600 | 600 |  | Energy | Geothermal
G93 | 2002-01-09 13:15 | Duke Energy NA | Duke Energy North America, LLC | OR | Linn | Between Santiam and Wren Tap at 230kV Line. | WITHDRAWN | GI | 2005-01-01 | 600 | 600 |  | Energy | Combined cycle
G92 | 2002-01-04 10:45 | Plymouth Energy | Plymouth Energy, LLC | WA | Benton | BPA’s McNary - John Day 500kV Line in the vicinity of Plymouth, WA. | WITHDRAWN | GI | 2004-04-27 | 306 | 306 |  | Energy | Combined cycle
G91 | 2001-12-20 11:01 | Duke Energy NA | Duke Energy North America, LLC | OR | Deschutes | BPA's 230 kV transmission line between Redmond and Pilot Butte substations in Deschutes Co., OR | WITHDRAWN | GI | 2005-06-01 | 640 | 640 |  | Energy | Combined cycle
G90 | 2001-11-29 10:39 | Cal Geo | Cal Geo Company | CA | modoc | Cedarville Junction Substation | WITHDRAWN | GI | 2003-07-01 | 30 | 30 |  | Energy | Geothermal
G89 | 2001-11-23 14:32 | Enron Power Marketing | Enron Power Marketing, Inc. | WA | king | Approximately 7 miles east of BPA's Maple Valley 230 kV Substation | WITHDRAWN | GI | 2004-01-01 | 300 | 300 |  | Energy | Combined cycle |  | Withdrawn on December 7, 2001
G88 | 2001-11-21 10:00 | NextEra Energy Resources | NextEra Energy Resources LLC | WA | Walla Walla | Is to the existing BPA Sacajawea Substation | WITHDRAWN | GI | 2002-09-01 | 150 | 150 |  | Energy | Wind |  | Withdrawn on November 4, 2003
G87 | 2001-10-31 10:26 | Peoples Energy Resources | Peoples Energy Resources Corporation | OR | Klamath | BPA’s 500 kV Grizzly – Malin transmission line approximately 30 miles north of Malin Substation | WITHDRAWN | GI | 2005-03-01 | 1200 | 1200 |  | Energy | Combined cycle |  | Provisionally posted as 'Withdrawn' pending confirmation of site certification and owner entity status.
G84 | 2001-10-29 10:43 | Touchet Wind Farm | Winds Over Washington Energy Group | WA | Walla Walla | BPA's 500 kV Lower Monumental - McNary transmission line in the vicinity of Wallula, WA. | WITHDRAWN | GI | 2004-01-01 | 150 | 150 |  | Energy | Wind |  | Withdrawn on June 27, 2002
G85 | 2001-10-29 10:43 | Windy Ridge Wind Farm | Winds Over Washington Energy Group | WA | Garfield | BPA's 500 kV Lower Monumental Substation | WITHDRAWN | GI | 2004-01-01 | 150 | 150 |  | Energy | Wind |  | Withdrawn on January 12, 2004
G86 | 2001-10-29 10:43 | Eureka Flats Wind Farm | Winds Over Washington Energy Group | WA | Whatcom | BPA's 500 kV Lower Monumental McNary transmission line in the vicinity of Eureka, WA | WITHDRAWN | GI | 2004-01-01 | 150 | 150 |  | Energy | Wind |  | Withdrawn on June 27, 2002
G83 | 2001-10-24 08:05 | Sempra Generation | Sempra Generation, LLC | OR | Marion | BPA's Pearl - Marion 500 kV line in the vicinity of Aurora, OR | WITHDRAWN | GI | 2005-06-01 | 612 | 612 |  | Energy | Combined cycle |  | Withdrawn on August 4, 2004
G82 | 2001-10-18 13:33 | Klondike 1 Wind | Northwestern Wind Power, LLC | OR | Wasco | Interconnection is BPA's De Moss 115 kV Substation | CONFIRMED | GI | 2002-09-01 | 26 | 26 |  | Energy | Wind |  | on-line June 2005 combined with G096 for 76 MW as Klondike II.
G81 | 2001-10-10 18:39 | Clipper WindPower | Clipper Windpower Development, Inc. | OR | Curry | BPA's 115kV transmission line in the vicinity of Langlois Substation | WITHDRAWN | GI | 2002-06-01 | 53 | 53 |  | Energy | Wind |  | This was updated to study on 11/30/2001
G80 | 2001-09-28 11:54 | Kittitas Valley Wind | Sagebrush Power Partners, LLC | WA | Kittitas County | Columbia Covington 230kV in the vicinity of Cle Elum, Washington | CONFIRMED | GI | 2009-12-31 | 108 | 108 |  | ERIS | Wind |  | on-line December 2010
G79 | 2001-09-27 16:34 | Horizon Wind Energy-WRidge | Wind Ridge Power Partners, LLC | WA | Asotin | BPA's N. Lewiston - Franklin 115kV transmission line in the vicinity of Clarkston, Washington | WITHDRAWN | GI | 2003-06-15 | 200 | 200 |  | Energy | Wind |  | Withdrawn on December 11, 2001.
G78 | 2001-09-27 16:32 | Horizon Wind Energy-Wheat | Wheat Field Power Partners, LLC | OR | Wasco | BPA's Big Eddy - Maupin 230kV transmission line in the vicinity of Dufur, Oregon | WITHDRAWN | GI | 2005-10-01 | 195 | 195 |  | Energy | Wind |  | Withdrawn on July 11, 2003
G77 | 2001-09-21 17:49 | 300MW Lower Monumental-Starbuck | RES North America | WA | Columbia | BPA's proposed Lower Monumental - Starbuck 500 kV line. | WITHDRAWN | GI | 2004-06-01 | 300 | 300 |  | Energy | Wind
G76 | 2001-09-19 17:49 | 200MW North Lewiston-Walla Walla 2 | RES North America | WA | Walla Walla | BPA's 115 kV line connecting the North Lewiston and Walla Walla Substation. | WITHDRAWN | GI | 2002-12-01 | 200 | 200 |  | Energy | Wind
G75 | 2001-09-19 14:02 | 200MW North Lewiston-Walla Walla 1 | RES North America | WA | Walla Walla | BPA's 115 kV line connecting the North Lewiston and Walla Walla Substation. | WITHDRAWN | GI | 2002-12-01 | 200 | 200 |  | Energy | Wind
G74 | 2001-09-19 09:20 | Cielo Wind Power | Cielo Wind Power | WA | Klickitat | Big Eddy 230 kV line South of Goldendale. | WITHDRAWN | GI | 2003-08-01 | 80 | 80 |  | Energy | Wind
G73-01 | 2001-09-18 11:06 | Nine Canyon II | Energy Northwest | WA | Benton | Nine Canyon Wind McNary-Badger Canyon #1 Line approximately 10 miles SE of Badger Canyon Substation 115 kV. | CONFIRMED | GI | 2007-11-01 | 32 | 32 |  | ERIS | Wind |  | on-line January 2008 for 32 MW
G73 | 2001-09-12 10:03 | OR-CAL Power | Or-Cal Power, Inc. | OR | Deschutes | LaPine Substation | WITHDRAWN | GI | 2003-03-01 | 97 | 97 |  | Energy | Geothermal |  | This was updated to refused on December 10, 1001 on request from Altman.
G72 | 2001-08-20 17:19 | AES Pacific Inc | AES Pacific Inc | WA | Walla Walla | BPA's Proposed Wallula 500 kV Substation | WITHDRAWN | GI | 2002-06-01 | 300 | 300 |  | Energy | Combined cycle |  | This was updated to refused on December 10, 1001 on request from Altman.
G71-01 | 2001-08-20 09:30 | GNA Energy | GNA Energy, LLC | WA | Klickitat | BPA's Harvalum 230 kV Substation in Goldendal WA. | WITHDRAWN | GI | 2003-01-15 | 100 | 100 |  | Energy | Combined cycle |  | Withdrawn on December 3, 2010
G71 | 2001-08-17 15:50 | AES Pacific Inc | AES Pacific Inc | CA | Modoc | BPA's Canby 230 kV Substation in Modoc County, CA. | WITHDRAWN | GI | 2002-06-01 | 300 | 300 |  | Energy | Biomass
G70-01 | 2001-08-14 13:47 | 01 37MW Connell | Effective Energy Corporation | WA | Franklin | The project will connect at BPA's Connell Substation | WITHDRAWN | GI | 2002-06-01 | 37 | 37 |  | Energy | Combined cycle |  | Withdrawn on December 3, 2010
G70-02 | 2001-08-14 13:47 | 02 37MW Franklin PUD,Franklin Riverview | Effective Energy Corporation | WA | Franklin | The project will connect to BPA through Franklin PUD's new Oregon Street Substation and the 115 kV Franklin Riverview transmission line | WITHDRAWN | GI | 2002-06-01 | 37 | 37 |  | Energy | Combined cycle |  | Request submitted as 36.1 MW
G70 | 2001-07-24 10:32 | Frederickson Power LP | Frederickson Power, LP | WA | Pierce | South Tacoma Substation. | WITHDRAWN | GI | 2002-10-01 | 300 | 300 |  | Energy | Combined cycle
G69 | 2001-07-12 15:37 | National Energy and Gas Tx | National Energy & Gas Transmission, Inc. | OR | Morrow | A new looped tap on the existing Coyote Springs loop on the McNary/Slatt 500 kV | WITHDRAWN | GI | 2005-02-01 | 620 | 620 |  | Energy | Combined cycle
G68 | 2001-07-05 09:56 | Clatskanie | Clatskanie People's Utility District | OR | Clatsop | The Wauna Substation | WITHDRAWN | GI | 2001-11-15 | 65 | 65 |  | Energy |  |  | Withdrawn on March 11, 2010
G66 | 2001-06-29 12:07 | 100MW Harvalum | ABB Equity Ventures Inc | WA | Klickitat | Harvalum Substation | WITHDRAWN | GI | 2003-09-01 | 100 | 100 |  | Energy | Wind
G67 | 2001-06-29 12:07 | 100MW Midway-Bonneville | ABB Equity Ventures Inc | OR | Klickitat | BPA's Tap into Midway-Bonneville 230 kV line in the vicinity of Goldendale, Klickitat County, WA | WITHDRAWN | GI | 2003-09-01 | 100 | 100 |  | Energy | Wind |  | Withdrawn on April 1, 2003
G65 | 2001-06-22 07:12 | 310MW Cardwell | Cogentrix Energy, Inc. | WA | Cowlitz | Cardwell Substation | WITHDRAWN | GI | 2003-06-01 | 310 | 310 |  | Energy | Combined cycle
G64 | 2001-06-21 08:15 | US Elect Power Corp | US Electric Power Corporation | WA | Whatcom | The generation will be in the Cherry Point section of Whatcom County, Washington with an interconnection at Custer Substation | WITHDRAWN | GI | 2004-03-01 | 349 | 349 |  | Energy | Combined cycle
G62 | 2001-06-07 09:45 | 30MW Walla Walla-Pendleton | FPL Energy Power Marketing Inc | OR | Umatilla | Vansycle Tap on Walla Walla-Pendleton 69 kV transmission line (Duroc) | WITHDRAWN | GI | 2002-09-01 | 30 | 30 |  | Energy | Wind
G63 | 2001-06-07 09:45 | 70MW Walla Walla-Franklin | FPL Energy Power Marketing Inc | OR | Umatilla | Nine Mile Tap on the Walla Walla-Franklin 115 kV line | WITHDRAWN | GI | 2002-09-01 | 70 | 70 |  | Energy | Wind
G61 | 2001-06-05 14:25 | Black Hills Energy | Black Hills Energy Capital Inc | ID | Minidoka | Hay Mill 138 kV Substation, via dedicated line owned by City of Rupert (IPC Load Control) | WITHDRAWN | GI | 2002-07-01 | 55 | 55 |  | Energy | Combined cycle
G59 | 2001-05-31 14:33 | 700MW Sickler-Schultz | Calpine Energy Services, L.P. | WA | Benton | Sickler-Schultz 500 kV | WITHDRAWN | GI | 2005-06-01 | 700 | 700 |  | Energy | Combined cycle
G60 | 2001-05-31 14:33 | 1300MW Sickler-Schultz | Calpine Energy Services, L.P. | WA | Benton | Sickler-Schultz 500 kV | WITHDRAWN | GI | 2005-06-01 | 1300 | 1300 |  | Energy | Combined cycle
G58 | 2001-05-23 10:02 | 105MW McNary-Roundup | Seawest Windpower, Inc. | OR | Umatilla | McNary-Roundup 230 kV line | WITHDRAWN | GI | 2003-09-01 | 105 | 105 |  | Energy | Wind
G57 | 2001-05-22 15:15 | GNA Energy | Seawest Windpower, Inc. | OR | Sherman | Big Eddy-DeMoss 115 kV line | WITHDRAWN | GI | 2003-09-01 | 105 | 105 |  | Energy | Wind
G56 | 2001-05-11 17:54 | GNA Energy | GNA Energy, LLC | WA | Klickitat | Harvalum 230 kV Substation | WITHDRAWN | GI | 2002-02-01 | 45 | 45 |  | Energy | Combined cycle
G55 | 2001-05-11 16:34 | Cedar Hills Energy LLC | Cedar Hills Energy LLC | WA | king | Maple Valley 230 kV Substation | WITHDRAWN | GI | 2004-01-01 | 300 | 300 |  | Energy | Combined cycle
G54 | 2001-05-09 11:19 | Klondike Wind Power | Klondike Wind Power, LLC | OR | Sherman | De Moss 69 kV Substation | CONFIRMED | GI | 2001-10-31 | 24 | 24 |  | Energy | Wind |  | on-line December 2000 as Klondike Phase I.
G53 | 2001-05-04 11:37 | Tacoma Power TC-PSE | Tacoma Power | WA | Skagit | new interconnection point on BPA's 230 kV Sedro Wooley-Bellingham line | WITHDRAWN | GI | 2002-01-01 | 83 | 83 |  | Energy | Combined cycle
G51 | 2001-05-03 15:17 | Pierce County Project No 1 | Duke Energy North America, LLC | WA | Pierce | South Tacoma 230 kV Substation | WITHDRAWN | GI | 2003-01-01 | 170 | 170 |  | Energy | Combined cycle
G52 | 2001-05-03 15:17 | Pierce County Project No 2 | Duke Energy North America, LLC | WA | Pierce | South Tacoma 230 kV Substation | WITHDRAWN | GI | 2003-01-01 | 170 | 170 |  | Energy | Combined cycle |  | Pierce County Project No. 2
G48-01 | 2001-04-23 18:47 | 249MW Big Eddy-Midway,Hanford-John Day 1 | Washington Winds, Inc. | WA | BentoN | 230 kV Big Eddy-Midway line and/or the 500 kV Hanford-John Day line | WITHDRAWN | GI | 2002-11-15 | 249 | 249 |  | Energy | Wind |  | Withdrawn on January 28, 2004
G48 | 2001-04-23 18:47 | 150MW Big Eddy-Midway,Hanford-John Day | Washington Winds, Inc. | WA | Benton | 230 kV Big Eddy-Midway line and/or the 500 kV Hanford-John Day line | WITHDRAWN | GI | 2002-11-15 | 150 | 150 |  | Energy | Wind |  | Withdrawn on January 28, 2004
G49 | 2001-04-23 09:46 | 249MW Big Eddy-Midway,Hanford-John Day 2 | Washington Winds, Inc. | WA | Benton | 230 kV Big Eddy-Midway line and/or the 500 kV Hanford-John Day line | WITHDRAWN | GI | 2002-11-30 | 249 | 249 |  | Energy | Wind
G50 | 2001-04-23 09:46 | Pacific Winds Inc | Pacific Winds, Inc. | WA | Klickitat | 230/kV McNary - Horse Heaven BPA transmission line and/or the 345 kV McNary - Ross BPA transmission line | WITHDRAWN | GI | 2003-03-31 23:00 | 249 | 249 |  | Energy | Wind
G47 | 2001-04-19 09:52 | Nordic Energy Barge No 2 | Nordic Energy Barge #2, LLC | OR | Columbia | Trojan Switching Station | WITHDRAWN | GI | 2001-12-01 | 170 | 170 |  | Energy |  |  | Withdrawn by Customer
G46-03 | 2001-04-18 09:00 | 100MW Cowlitz-Cardwell | Avista Power, LLC | WA | Cowlitz | Cowlitz-Cardwell 115 kV line | WITHDRAWN | GI | 2001-12-01 | 100 | 100 |  | Energy | Combined cycle |  | Withdrawn by Customer
G46-01 | 2001-04-17 16:21 | Clark Public Utilities | Clark Public Utilities | WA | Clark | 115 kV bus at BPA Alcoa Substation | WITHDRAWN | GI | 2002-07-01 | 250 | 250 |  | Energy | Combined cycle
G46 | 2001-04-16 16:31 | Coburg Power | Coberg Power LLC | OR | Lane | Marion-Lane No. 1 500 kV line near Colburg | WITHDRAWN | GI | 2004-08-01 | 570 | 570 |  | Energy | Combined cycle |  | Withdrawn on October 16, 2004
G44 | 2001-04-11 17:50 | 100MW Longview 1 | Avista Power, LLC | WA | Cowlitz | BPA's Longview Substation | WITHDRAWN | GI | 2001-12-01 | 100 | 100 |  | Energy | Combined cycle |  | Withdrawn by Customer
G45 | 2001-04-11 17:50 | 100MW Longview 2 | Avista Power, LLC | WA | Cowlitz | BPA's Longview Substation | WITHDRAWN | GI | 2001-12-01 | 100 | 100 |  | Energy | Combined cycle |  | Withdrawn by Customer
G43 | 2001-04-06 17:03 | Clatskanie | Clatskanie People's Utility District | OR | Columbia | Alcoa Substation 115 kV | WITHDRAWN | GI | 2002-05-15 | 88 | 88 |  | Energy | Combined cycle |  | Withdrawn by Customer
G41 | 2001-04-06 12:25 | 100MW McNary | Calpine Energy Services, L.P. | OR | Umatilla | McNary Substation | WITHDRAWN | GI | 2001-12-01 | 100 | 100 |  | Energy | Combined cycle |  | Withdrawn by Customer
G42 | 2001-04-06 12:25 | 50MW Alcoa | Calpine Energy Services, L.P. | WA | Clark | Alcoa Substation 230 kV in the vicinity of Vancouver, WA | WITHDRAWN | GI | 2001-10-31 | 50 | 50 |  | Energy | Combined cycle |  | Withdrawn by Customer
G40 | 2001-04-06 12:24 | 250MW Covington-Chehalis,Tacoma-Olympia | Calpine Energy Services, L.P. | WA | Pierce | 230 kV Covington-Chehalis and/or Tacoma-Olympia lines | WITHDRAWN | GI | 2001-05-01 | 250 | 250 |  | Energy | Combined cycle |  | Withdrawn by Customer
G39 | 2001-04-04 12:04 | Grant Generation | Grant Generation, LLC | WA | Grant | Vantage-Hanford 500 kV line | WITHDRAWN | GI | 2005-02-01 | 1300 | 1300 |  | Energy | Combined cycle |  | Withdrawn by Customer
G46-02 | 2001-04-01 09:00 | 100MW Cowlitz PUD BHP at Kalama | Avista Power, LLC | WA | Cowlitz | Cowlitz PUD BHP at Kalama 115 kV line | WITHDRAWN | GI | 2001-12-01 | 100 | 100 |  | Energy | Combined cycle |  | Withdrawn by Customer
G38 | 2001-03-22 17:21 | 600 MW Monroe-Custer | Calpine Energy Services, L.P. | WA | Skagit | Monroe-Custer 500 kV line near Sedro Wooley | WITHDRAWN | GI | 2005-06-01 | 600 | 600 |  | Energy | Combined cycle |  | Withdrawn by Customer
G37 | 2001-03-20 08:12 | Nordic Energy Barge 1 | Nordic Energy Barge #1, LLC | WA | Cowlitz | Cowlitz Substation | WITHDRAWN | GI | 2001-08-01 | 100 | 100 |  | Energy | Combined cycle |  | Withdrawn by Customer
G36 | 2001-03-16 14:23 | Frontier Technology | Frontier Technology, Inc | OR | Lane | Marion-Lane No. 1 500 kV transmission line near Colburg | WITHDRAWN | GI | 2003-08-01 | 265 | 265 |  | Energy | Combined cycle |  | Withdrawn on October 11, 2002
G35 | 2001-03-06 18:36 | Grant Generation | Grant Generation, LLC | WA | Grant | Grand Coulee-Schultz 500 kV line | WITHDRAWN | GI | 2005-06-01 | 1300 | 1300 |  | Energy | Combined cycle |  | Withdrawn on October 11, 2002
G34 | 2001-03-06 16:08 | Competitive Power Venture | Newport Northwest, LLC | WA | Whatcom | Intalco 500 kV Substation | WITHDRAWN | GI | 2005-06-01 | 1300 | 1300 |  | Energy | Combined cycle
G33 | 2001-03-06 10:57 | Tenaska Inc | Tenaska, Inc. | OR | Klamath | Captain Jack 500 kV Substation | WITHDRAWN | GI | 2004-06-01 | 450 | 450 |  | Energy | Combined cycle |  | Withdrawn on July 15, 2002
G32 | 2001-03-05 08:28 | Kootenai Generation | Kootenai Electric Cooperative, Inc. | WA | Kootenai | BPA's Taft-Bell 500 kV line | WITHDRAWN | GI | 2005-06-01 | 1300 | 1300 |  | Energy | Combined cycle |  | Withdrawn on October 11, 2002
G30 | 2001-03-01 13:57 | Pacific Winds Inc | Pacific Winds, Inc. | WA | Benton | 230 kV Hanford-Mabton transmission line near Rattlesnake Hills | WITHDRAWN | GI | 2002-11-15 | 100 | 100 |  | Energy | Wind |  | Withdrawn by Customer
G31 | 2001-03-01 13:57 | Pacific Winds Inc | Pacific Winds, Inc. | WA | Benton | 230 kV Franklin-McNary line near Horse Heaven Hills | WITHDRAWN | GI | 2002-11-15 | 100 | 100 |  | Energy | Wind |  | Withdrawn by Customer
G29 | 2001-02-23 14:46 | BP Energy Company | BP Energy Company | OR | Grant | John Day | WITHDRAWN | GI | 2004-01-01 | 200 | 200 |  | Energy | Wind |  | Withdrawn on October 11, 2002
G28 | 2001-02-22 14:59 | N/A | Clark Public Utilities | WA | Clark | Alcoa Substation | WITHDRAWN | GI | 2001-01-01 | 100 | 100 |  | Energy | Combined cycle |  | Withdrawn on October 30, 2002
G27-01 | 2001-02-20 17:05 | Cherry Point Refinery | BP Energy Company | WA | Whatcom | Custer Substation | WITHDRAWN | GI | 2004-01-01 | 1000 | 1000 |  | Energy | Combined cycle |  | LGIA terminated on February 1, 2011.
G27 | 2001-02-15 16:26 | Benton PUD | Public Utility District No. 1 of Benton County | WA | Benton | Unocal Finley Substation | WITHDRAWN | GI | 2001-08-01 | 25 | 25 |  | Energy | Combined cycle
G26 | 2001-02-15 15:51 | Wanapa Energy Center | Confederated Tribes Umatilla Indian Resvation | OR | Umatilla | McNary 500 kV bus | STUDY | GI | 2003-07-01 | 1000 | 1000 |  | Energy | Combined cycle |  | Study suspended by customer due to ownership issues | Customer Delay
G24 | 2001-02-15 14:14 | 500MW Custer-[Intalco,Portal Way] 1 | Calpine Energy Services, L.P. | WA | Whatcon | Custer-Intalco/Portal Way 230 kV transmission line | WITHDRAWN | GI | 2005-06-01 | 500 | 500 |  | Energy | Combined cycle
G25 | 2001-02-15 14:14 | 500MW Custer-[Intalco,Portal Way] 2 | Calpine Energy Services, L.P. | WA | Whatcom | Custer-Inalco/Portal Way 230 kV transmission line | WITHDRAWN | GI | 2004-06-01 | 500 | 500 |  | Energy | Combined cycle
G22 | 2001-02-15 14:13 | 50MW Alcoa-St Johns | Calpine Energy Services, L.P. | WA | Clark | In the vicinity of Vancouver, WA on BPA's Alcoa-St. Johns 115 kV line | WITHDRAWN | GI | 2001-10-31 23:00 | 50 | 50 |  | Energy | Combined cycle
G23 | 2001-02-15 14:13 | 500MW St Johns-Ross | Calpine Energy Services, L.P. | WA | Clark | St. Johns-Ross 230 kV line | WITHDRAWN | GI | 2005-06-01 | 500 | 500 |  | Energy | Combined cycle
G20 | 2001-02-05 06:48 | Centralia Generation Addition | TransAlta Utilities Cooperative | WA | Lewis | In the vicinity of the Centralia Gen Station and C.W. Paul 500 kV SS, tapping the Centralia-Paul 500 kV line. | CONFIRMED | GI | 2002-01-01 | 248 | 248 |  | Energy | Combined cycle |  | on-line
G21 | 2001-02-05 06:48 | Condon Wind Farm | Seawest Windpower, Inc. | OR | Gilliam | At the Demoss-Fossil 69 kV line in the vicinity of Condon, OR | CONFIRMED | GI | 2002-01-01 | 25 | 25 |  | Energy | Wind |  | on-line 2000
G19-01 | 2001-01-25 16:06 | Summit PNW | Summit Power Northwest Project, LLC | OR | Clatsop | Allston 230 KV | WITHDRAWN | GI | 2003-10-31 | 520 | 520 |  | Energy | Combined cycle |  | Withdrawn on March 11, 2010.
G19 | 2001-01-18 10:18 | 500MW Snohomish | FPL Energy Power Marketing Inc | WA | Snohomish | Initially BPA's 115 kV Snohomish Substation, subsequently at Bonneville's Snohomish Substation at both 115 kV and 230kV | WITHDRAWN | GI | 2002-09-01 | 500 | 500 |  | Energy | Combined cycle
G18 | 2001-01-10 12:42 | 250MW Snohomish | FPL Energy Power Marketing Inc | WA | Snohomish | Snohomish 115 kV Substation | WITHDRAWN | GI | 2002-09-01 | 250 | 250 |  | Energy | Combined cycle
G17 | 2000-12-24 14:40 | JP Saylor and Associates | J P Saylor & Associates | OR | Curry | BPA's Fairview-Rogue 230 kV line in the vicinity of Curry County, OR | WITHDRAWN | GI | 2001-10-31 | 25 | 25 |  | Energy | Wind
G16 | 2000-12-22 13:31 | 500MW Taft-Bell | Cogentrix Energy, Inc. | ID | Kootenai | BPA's Taft-Bell 500 kV line in the vicinity of Kootenaid County, ID | WITHDRAWN | GI | 2004-12-01 | 500 | 500 |  | Energy | Combined cycle
G15 | 2000-12-18 14:51 | Oregon Energy Company | Oregon Energy Company LLC | OR | Columbia | on BPA's 115 kV Allston-St. Helens line in the vicinity of St. Helens, OR | WITHDRAWN | GI | 2002-08-01 | 170 | 170 |  | Energy | Combined cycle
G14 | 2000-11-30 15:38 | Stateline Wind Farm | FPL Energy Vansycle L.L.C. | OR | Umatilla | on BPA's Franklin-Walla Walla line in the vicinity of Touchet, WA | CONFIRMED | GI | 2001-09-01 | 90 | 90 |  | Energy | Wind |  | on-line October 2008
G13 | 2000-10-31 14:50 | Centralia Generation | TransAlta Utilities Cooperative | WA | Lewis | C.W. Paul 500 kV Substation | CONFIRMED | GI | 2001-06-01 | 50 | 50 |  | ERIS | Combined cycle
G11 | 2000-09-13 16:25 | Pacific Winds Inc | Pacific Winds, Inc. | WA | Benton | a new POR in the vicinity of the Franklin-McNary 230 kV line | WITHDRAWN | GI | 2002-07-01 | 76 | 76 |  | Energy | Wind
G12 | 2000-09-08 17:06 | Oregon Energy Company | Oregon Energy Company LLC | OR | Linn | a new POR in the vicinity of the Albany-Eugene 115 kV line near Halsey, OR | WITHDRAWN | GI | 2001-10-01 | 120 | 120 |  | Energy | Combined cycle |  | Withdrawn on July 8, 2002.
G10 | 2000-08-28 14:52 | 1100MW Grizzly | Cogentrix Energy, Inc. | OR | Jefferson | Grizzly 500 kV Substation | WITHDRAWN | GI | 2004-07-01 | 1100 | 1100 |  | Energy | Combined cycle
G9 | 2000-08-28 14:51 | 1100MW Paul | Cogentrix Energy, Inc. | WA | Lewis | Paul 500 kV Substation | WITHDRAWN | GI | 2004-07-01 | 1100 | 1100 |  | Energy | Combined cycle
G8 | 2000-08-28 14:50 | 1100MW Troutdale | Cogentrix Energy, Inc. | OR | Multnomah | Troutdale kV Substation | WITHDRAWN | GI | 2004-07-01 | 1100 | 1100 |  | Energy | Combined cycle |  | Withdrawn on July 15, 2002
G7 | 2000-08-25 14:19 | Pacific Winds Inc | Pacific Winds, Inc. | WA | Benton | at a new POR in the vicinity of the Hanford-Mapbton 230 kV line | WITHDRAWN | GI | 2002-10-31 23:00 | 76 | 76 |  | Energy | Wind
G6 | 2000-08-22 14:30 | Continental Energy Svcs | Continental Energy Services, Inc. | MT | Silver Bow | Silver Bow 230 kV Substation | WITHDRAWN | GI | 2002-03-31 23:00 | 400 | 400 |  | Energy | Combined cycle
G5 | 2000-08-02 07:56 | Nine Canyon Wind Project | Energy Northwest Inc | WA | Benton | Nine Canyon Substation through Benton County PUD 115kV tap line to BPA's McNary-Badger Canyon line. | CONFIRMED | GI | 2001-09-01 | 63 | 63 |  | Energy | Wind |  | on-line 2001
G4 | 2000-07-28 16:17 | Mint Farm Energy Center | Puget Sound Energy, Inc. | WA | Cowlitz | Longview 230 kV Substation | CONFIRMED | GI | 2007-11-28 | 320 | 320 | Longview, WA | Energy | Combined cycle |  | on-line
G3 | 2000-07-28 15:55 | Enron Power Marketing | Enron Power Marketing, Inc. | WA | Cowlitz | Longview 230 kV Substation | WITHDRAWN | GI | 2003-06-01 | 600 | 600 |  | Energy | Combined cycle |  | Withdrawn by Customer
G2 | 2000-06-23 | Goldendale Energy Center | Goldendale Energy Center, LLC | OR | klickitat | Harvalum 230 kV Substation | CONFIRMED | GI | 2002-01-01 | 247 | 247 |  | Energy | Combined cycle |  | on-line
G1 | 2000-06-09 16:12 | PG and E Generation | PG&E Energy Services | OR | Umatilla | McNary 230 kv Substation | WITHDRAWN | GI | 2000-06-09 | 581 | 581 |  | Energy | Combined cycle