## Sheet1
Need | Activity | 2011-11-01 | 2011-12-01 | 2012-01-01 | 2012-02-01 | 2012-03-01 | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | Ongoing
System Development
Work with other engagement initiatives | Series of information and exchange sessions (sector based ?)
Shared communication strategy and materials | Identify communication and information needs which can be more effectively met Pan London
Develop materials as agreed above
Develop knowledge and engagement in other organisations | Support emerging HealthWatches/LAs to identify target organisations
Develop materials/presentations for use by local LINks and LAs to engage with target organisations
Series of engagement events at cluster level as part of this plan and other local events organised by LAs/LINks
Development of host/support | To be identified following work on corporate bodies
Organisation Development
Commissioning framework | Establish a HealthWatch Commissioners Network to share progress to date and identify and action opportunities for shared working
Understand and develop corporate bodies | Work with LINks members to specify detail of support required
Commission package of support, advice and information
Contract and use
Understand how to provide complaints advocacy and signposting services | Establish a Working group
Produce guidance for emerging HeathWatches on what is involved in providing these services (resources and skills needed)
Checklist/assessment tool for individual emerging HealthWatches to assess their capacity and capability to deliver
Professional advice for Local HealthWatches | Identify (purchase) access to professional advice/insurance for emerging organisations
People Development
Agree programme
Commission/Plan activities
Develop Directory and circulate
Activities delivered